## PlanFileName (hidden)
WX1450521_56A0T4Y_20260609091526 | 56A0T4Y | V3 | 27 | 3539 | 3539 | M3T1A1969N1271200204597715199 | M3T1A1969N1271200212896407746
|  |  | {"headerType":"extarr","itemName":"Customer Site ID","itemChildName":"","activityId":"","id":"SITEID","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85136705103 | AMBA_102_KS020_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"DU ID","itemChildName":"","activityId":"","id":"DUCODE","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85136706103 | AMBA_102_KS172_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"DU ID Único","itemChildName":"","activityId":"","id":"taskFlowNode_1502265103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1502265103","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{952897103:\"No\",952896103:\"Si\"}","enumValueArray":["Si","No"],"beginRownum":1,"endRownum":3,"editFlag":false} | 85135707103 | AMBA_102_KS173_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Site coefficient","itemChildName":"","activityId":"","id":"taskFlowNode_1544867103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1544867103","fieldType":null,"attributeType":"2","sourceType":"2","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 85135708103 | AMBA_102_KS237_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR","itemChildName":"Plan Start Date","activityId":"116112103","id":"planStart_116112103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85135709103 | AMBA_102_KS243_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR","itemChildName":"Plan End Date","activityId":"116112103","id":"plan_116112103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Design","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85135710103 | AMBA_102_KS277_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR","itemChildName":"Actual Start Date","activityId":"116112103","id":"actualStart_116112103","width":null,"colStyle":null,"valueFormatter":null,"toolName":"勘测设计","sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Design","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85135711103 | AMBA_102_KS348_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR","itemChildName":"Actual End Date","activityId":"116112103","id":"actual_116112103","width":null,"colStyle":null,"valueFormatter":null,"toolName":"勘测设计","sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Design","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85132727103 | AMBA_102_KS349_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR","itemChildName":"Owner","activityId":"116112103","id":"resPonsible_116112103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Design","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85132728103 | AMBA_102_KS375_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR","itemChildName":"Remarks","activityId":"116112103","id":"remarks_116112103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"1","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Design","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85132729103 | AMBA_102_KS608_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR Approval(TSSR Approved by Customer)(Civil Work)","itemChildName":"Plan End Date","activityId":"116715103","id":"plan_116715103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85116712103 | AMBA_103_BS062_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR Approval(TSSR Approved by Customer)(Civil Work)","itemChildName":"Actual End Date","activityId":"116715103","id":"actual_116715103","width":null,"colStyle":null,"valueFormatter":null,"toolName":"勘测设计","sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85116713103 | AMBA_103_BS078_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR Approval(TSSR Approved by Customer)(Civil Work)","itemChildName":"Owner","activityId":"116715103","id":"resPonsible_116715103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85116714103 | AMBA_103_BS109_RSH_OPT
|  |  | {"headerType":"activity","itemName":"TSSR Approval(TSSR Approved by Customer)(Civil Work)","itemChildName":"Remarks","activityId":"116715103","id":"remarks_116715103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"1","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85116715103 | AMBA_103_BS199_RSH_OPT
|  |  | {"headerType":"activity","itemName":"ML","itemChildName":"Plan End Date","activityId":"116130103","id":"plan_116130103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85137727103 | AMBA_103_BS201_RSH_OPT
|  |  | {"headerType":"activity","itemName":"ML","itemChildName":"Actual End Date","activityId":"116130103","id":"actual_116130103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85137728103 | AMBA_103_BS204_RSH_OPT
|  |  | {"headerType":"activity","itemName":"ML","itemChildName":"Owner","activityId":"116130103","id":"resPonsible_116130103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85137729103 | AMBA_103_BS298_RSH_OPT
|  |  | {"headerType":"activity","itemName":"ML","itemChildName":"Remarks","activityId":"116130103","id":"remarks_116130103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"1","attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85137730103 | AMBA_103_BS374_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"ML Configuaration in ISDP","itemChildName":"","activityId":"","id":"taskFlowNode_1544874103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1544874103","fieldType":null,"attributeType":"2","sourceType":"4","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 85137731103 | AMBA_103_KS470_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Configuration Created","itemChildName":"","activityId":"","id":"taskFlowNode_1546889103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1546889103","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{978039103:\"Yes\",978038103:\"No\"}","enumValueArray":["No","Yes"],"beginRownum":4,"endRownum":6,"editFlag":true} | 85137752103 | AMBA_106_BN021_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Farm Remark","itemChildName":"","activityId":"","id":"taskFlowNode_1500901103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1500901103","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 85137753103 | AMBA_106_BN102_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Farm Batch","itemChildName":"","activityId":"","id":"taskFlowNode_1502197103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1502197103","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{950963103:\"Etapa 02\",950965103:\"Etapa 03\",950964103:\"Etapa 01\"}","enumValueArray":["Etapa 01","Etapa 02","Etapa 03"],"beginRownum":7,"endRownum":10,"editFlag":true} | 85137754103 | AMBA_106_BN105_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Row Farm","itemChildName":"","activityId":"","id":"taskFlowNode_1504229103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1504229103","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 85137755103 | AMBA_106_BN243_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Subrack Farm","itemChildName":"","activityId":"","id":"taskFlowNode_1504231103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1504231103","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 85137756103 | AMBA_106_BN266_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Room Farm","itemChildName":"","activityId":"","id":"taskFlowNode_1504228103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1504228103","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 85114717103 | AMBA_106_BN306_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Rack Farm","itemChildName":"","activityId":"","id":"taskFlowNode_1504230103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1504230103","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 88339697103 | AMBA_110_KO059_RSH_OPT
|  |  | {"headerType":"extarr","itemName":"Status BBU FARM","itemChildName":"","activityId":"","id":"taskFlowNode_1488945103","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":"","attrId":"1488945103","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{939824103:\"Survey Pending\",939828103:\"MR\",939832103:\"Installed with Issue\",939836103:\"Dismantled\",939825103:\"Survey Done\",939829103:\"ML\",939833103:\"Installed\",939826103:\"PPI Pending\",939830103:\"Dispatched\",939834103:\"Ready for Dismantle\",976981103:\"N/A\",939827103:\"PPI Approved\",939831103:\"SubRack Installed\",939835103:\"Swapped\"}","enumValueArray":["Survey Pending","Survey Done","PPI Pending","PPI Approved","MR","ML","Dispatched","SubRack Installed","Installed with Issue","Installed","Ready for Dismantle","Swapped","Dismantled","N/A"],"beginRownum":11,"endRownum":25,"editFlag":true} | 88339698103 | AMBA_110_KO066_RSH_OPT
|  |  |  | 86830730103 | AMBA_119_BN289_RSH_OPT
|  |  |  | 86830729103 | AMBA_119_BN430_RSH_OPT
|  |  |  | 86830765103 | AMBA_119_KN083_RSH_OPT
|  |  |  | 86830764103 | AMBA_119_KN228_RSH_OPT
|  |  |  | 85114718103 | AMBA_120_BN174_RSH_OPT
|  |  |  | 85114719103 | AMBA_120_BN249_RSH_OPT
|  |  |  | 85114720103 | AMBA_120_BN407_RSH_OPT
|  |  |  | 86830798103 | AMBA_121_KN103_RSH_OPT
|  |  |  | 86830818103 | AMBA_121_KN258_RSH_OPT
|  |  |  | 86830736103 | AMBA_121_KN260_RSH_OPT
|  |  |  | 86830735103 | AMBA_121_KN306_RSH_OPT
|  |  |  | 86830732103 | AMBA_121_KN310_RSH_OPT
|  |  |  | 86830790103 | AMBA_121_KN323_RSH_OPT
|  |  |  | 86830731103 | AMBA_121_KN330_RSH_OPT
|  |  |  | 86830806103 | AMBA_122_BN175_RSH_OPT
|  |  |  | 86830767103 | AMBA_122_BN221_RSH_OPT
|  |  |  | 86830761103 | AMBA_122_BN226_RSH_OPT
|  |  |  | 86830778103 | AMBA_122_BN397_RSH_OPT
|  |  |  | 86830814103 | AMBA_123_KN166_RSH_OPT
|  |  |  | 86830816103 | AMBA_123_KN202_RSH_OPT
|  |  |  | 86830784103 | AMBA_123_KN203_RSH_OPT
|  |  |  | 86830827103 | AMBA_123_KN225_RSH_OPT
|  |  |  | 86830734103 | AMBA_123_KN297_RSH_OPT
|  |  |  | 86830733103 | AMBA_123_KN300_RSH_OPT
|  |  |  | 86830773103 | AMBA_123_KN354_RSH_OPT
|  |  |  | 86830812103 | AMBA_123_KN364_RSH_OPT
|  |  |  | 86830741103 | AMBA_124_KN106_RSH_OPT
|  |  |  | 86830742103 | AMBA_124_KN126_RSH_OPT
|  |  |  | 86830740103 | AMBA_124_KN295_RSH_OPT
|  |  |  | 86830739103 | AMBA_124_KN356_RSH_OPT
|  |  |  | 86830771103 | AMBA_130_KN175_RSH_OPT
|  |  |  | 86830781103 | AMBA_130_KN209_RSH_OPT
|  |  |  | 86830744103 | AMBA_130_KN329_RSH_OPT
|  |  |  | 86830815103 | AMBA_130_KN351_RSH_OPT
|  |  |  | 86830820103 | AMBA_130_KN352_RSH_OPT
|  |  |  | 86830813103 | AMBA_131_CN016_RSH_OPT
|  |  |  | 86830808103 | AMBA_131_KN239_RSH_OPT
|  |  |  | 86830747103 | AMBA_131_KN290_RSH_OPT
|  |  |  | 86830745103 | AMBA_131_KN314_RSH_OPT
|  |  |  | 86830809103 | AMBA_131_KN363_RSH_OPT
|  |  |  | 86830755103 | AMBA_132_KN079_RSH_OPT
|  |  |  | 86830823103 | AMBA_132_KN080_RSH_OPT
|  |  |  | 86830792103 | AMBA_132_KN081_RSH_OPT
|  |  |  | 86830811103 | AMBA_132_KN134_RSH_OPT
|  |  |  | 86830762103 | AMBA_132_KN163_RSH_OPT
|  |  |  | 86830803103 | AMBA_132_KN206_RSH_OPT
|  |  |  | 86830825103 | AMBA_132_KN223_RSH_OPT
|  |  |  | 86830780103 | AMBA_132_KN303_RSH_OPT
|  |  |  | 86830738103 | AMBA_132_KN369_RSH_OPT
|  |  |  | 86830737103 | AMBA_132_KN376_RSH_OPT
|  |  |  | 86830712103 | AMBA_133_KN082_RSH_OPT
|  |  |  | 86830699103 | AMBA_133_KN099_RSH_OPT
|  |  |  | 86830721103 | AMBA_133_KN127_RSH_OPT
|  |  |  | 86830698103 | AMBA_133_KN254_RSH_OPT
|  |  |  | 86830711103 | AMBA_133_KN255_RSH_OPT
|  |  |  | 86830697103 | AMBA_133_KN259_RSH_OPT
|  |  |  | 86830710103 | AMBA_133_KN350_RSH_OPT
|  |  |  | 86830703103 | AMBA_133_KN359_RSH_OPT
|  |  |  | 87410710103 | AMBA_133_NPU211_RSH_OPT
|  |  |  | 87410709103 | AMBA_133_NPU259_RSH_OPT
|  |  |  | 87410708103 | AMBA_133_NPU325_RSH_OPT
|  |  |  | 87410707103 | AMBA_133_NPU346_RSH_OPT
|  |  |  | 87410706103 | AMBA_133_NPU508_RSH_OPT
|  |  |  | 87410705103 | AMBA_133_NPU513_RSH_OPT
|  |  |  | 87410704103 | AMBA_133_NPU514_RSH_OPT
|  |  |  | 86830713103 | AMBA_134_KN109_RSH_OPT
|  |  |  | 86830706103 | AMBA_134_KN154_RSH_OPT
|  |  |  | 86830708103 | AMBA_134_KN155_RSH_OPT
|  |  |  | 86830717103 | AMBA_134_KN207_RSH_OPT
|  |  |  | 86830709103 | AMBA_134_KN215_RSH_OPT
|  |  |  | 86830705103 | AMBA_134_KN240_RSH_OPT
|  |  |  | 86830716103 | AMBA_134_KN247_RSH_OPT
|  |  |  | 86830704103 | AMBA_134_KN311_RSH_OPT
|  |  |  | 88340700103 | AMBA_141_CN212_RSH_OPT
|  |  |  | 88340698103 | AMBA_141_CN259_RSH_OPT
|  |  |  | 88339705103 | AMBA_141_CN306_RSH_OPT
|  |  |  | 88339706103 | AMBA_141_CN444_RSH_OPT
|  |  |  | 88339704103 | AMBA_141_CN819_RSH_OPT
|  |  |  | 88341697103 | AMBA_142_CN159_RSH_OPT
|  |  |  | 88340701103 | AMBA_142_CN193_RSH_OPT
|  |  |  | 88341699103 | AMBA_142_CN253_RSH_OPT
|  |  |  | 88341698103 | AMBA_142_CN254_RSH_OPT
|  |  |  | 88341700103 | AMBA_142_CN312_RSH_OPT
|  |  |  | 88341701103 | AMBA_142_CN830_RSH_OPT
|  |  |  | 86830746103 | AMBA_143_CN307_RSH_OPT
|  |  |  | 86830793103 | AMBA_143_KN077_RSH_OPT
|  |  |  | 86830782103 | AMBA_143_KN120_RSH_OPT
|  |  |  | 86830783103 | AMBA_143_KN122_RSH_OPT
|  |  |  | 86830797103 | AMBA_143_KN191_RSH_OPT
|  |  |  | 86830795103 | AMBA_143_KN236_RSH_OPT
|  |  |  | 86830794103 | AMBA_143_KN237_RSH_OPT
|  |  |  | 86830796103 | AMBA_143_KN309_RSH_OPT
|  |  |  | 88341703103 | AMBA_145_CN169_RSH_OPT
|  |  |  | 88341704103 | AMBA_145_CN274_RSH_OPT
|  |  |  | 88341702103 | AMBA_145_CN493_RSH_OPT
|  |  |  | 88340697103 | AMBA_148_CN310_RSH_OPT
|  |  |  | 88340699103 | AMBA_148_CN360_RSH_OPT
|  |  |  | 88339701103 | AMBA_155_CN108_RSH_OPT
|  |  |  | 88339700103 | AMBA_155_CN144_RSH_OPT
|  |  |  | 88339699103 | AMBA_155_CN428_RSH_OPT
|  |  |  | 86830774103 | AMBA_156_CN272_RSH_OPT
|  |  |  | 86830822103 | AMBA_156_CN321_RSH_OPT
|  |  |  | 86830758103 | AMBA_156_CN343_RSH_OPT
|  |  |  | 86830791103 | AMBA_156_CN344_RSH_OPT
|  |  |  | 86830789103 | AMBA_159_CM001_RSH_OPT
|  |  |  | 86830779103 | AMBA_159_CM026_RSH_OPT
|  |  |  | 86830824103 | AMBA_159_CM029_RSH_OPT
|  |  |  | 86830770103 | AMBA_159_CM036_RSH_OPT
|  |  |  | 86830759103 | AMBA_159_CN291_RSH_OPT
|  |  |  | 88339702103 | AMBA_160_CN247_RSH_OPT
|  |  |  | 88339703103 | AMBA_160_CN374_RSH_OPT
|  |  |  | 86830766103 | AMBA_161_CN167_RSH_OPT
|  |  |  | 86830768103 | AMBA_161_CN244_RSH_OPT
|  |  |  | 86830785103 | AMBA_162_CN155_RSH_OPT
|  |  |  | 86830800103 | AMBA_162_CU003_RSH_OPT
|  |  |  | 86830760103 | AMBA_162_CU049_RSH_OPT
|  |  |  | 86830805103 | AMBA_163_CU007_RSH_OPT
|  |  |  | 86830775103 | AMBA_163_CU048_RSH_OPT
|  |  |  | 86830804103 | AMBA_163_CU067_RSH_OPT
|  |  |  | 86830810103 | AMBA_166_CS026_RSH_OPT
|  |  |  | 86830777103 | AMBA_166_CS289_RSH_OPT
|  |  |  | 86830776103 | AMBA_166_CS291_RSH_OPT
|  |  |  | 86830753103 | AMBA_166_CU005_RSH_OPT
|  |  |  | 86830763103 | AMBA_166_CU068_RSH_OPT
|  |  |  | 86830754103 | AMBA_169_CU004_RSH_OPT
|  |  |  | 86830819103 | AMBA_170_CM033_RSH_OPT
|  |  |  | 86830787103 | AMBA_170_CS004_RSH_OPT
|  |  |  | 86830817103 | AMBA_170_CS097_RSH_OPT
|  |  |  | 86830821103 | AMBA_170_CS210_RSH_OPT
|  |  |  | 85132730103 | AMBA_180_BS067_RSH_OPT
|  |  |  | 85132731103 | AMBA_180_BS148_RSH_OPT
|  |  |  | 85136707103 | AMBA_180_BS164_RSH_OPT
|  |  |  | 85136708103 | AMBA_180_KS120_RSH_OPT
|  |  |  | 85136709103 | AMBA_180_KS143_RSH_OPT
|  |  |  | 85136710103 | AMBA_180_KS289_RSH_OPT
|  |  |  | 85136711103 | AMBA_180_KS291_RSH_OPT
|  |  |  | 85133707103 | AMBA_180_KS292_RSH_OPT
|  |  |  | 85133708103 | AMBA_180_KS351_RSH_OPT
|  |  |  | 85133709103 | AMBA_180_KS390_RSH_OPT
|  |  |  | 85113722103 | AMBA_200_LP028_RSH_OPT
|  |  |  | 85113723103 | AMBA_200_LP029_RSH_OPT
|  |  |  | 85113724103 | AMBA_200_LP047_RSH_OPT
|  |  |  | 85113725103 | AMBA_200_LP048_RSH_OPT
|  |  |  | 85113726103 | AMBA_200_LP049_RSH_OPT
|  |  |  | 85135727103 | AMBA_200_LP050_RSH_OPT
|  |  |  | 85135728103 | AMBA_200_LP057_RSH_OPT
|  |  |  | 85135729103 | AMBA_200_LP059_RSH_OPT
|  |  |  | 85135730103 | AMBA_200_LP097_RSH_OPT
|  |  |  | 85135731103 | AMBA_200_LP099_RSH_OPT
|  |  |  | 85140697103 | AMBA_200_LP100_RSH_OPT
|  |  |  | 85140698103 | AMBA_200_LP110_RSH_OPT
|  |  |  | 85140699103 | AMBA_200_LP131_RSH_OPT
|  |  |  | 85140700103 | AMBA_201_LP052_RSH_OPT
|  |  |  | 85140701103 | AMBA_201_LP075_RSH_OPT
|  |  |  | 85113727103 | AMBA_201_LP076_RSH_OPT
|  |  |  | 85113728103 | AMBA_201_LP077_RSH_OPT
|  |  |  | 85113729103 | AMBA_201_LP101_RSH_OPT
|  |  |  | 85113730103 | AMBA_201_LP117_RSH_OPT
|  |  |  | 85113731103 | AMBA_201_LP130_RSH_OPT
|  |  |  | 85135732103 | AMBA_201_LP132_RSH_OPT
|  |  |  | 85135733103 | AMBA_202_LP054_RSH_OPT
|  |  |  | 85135734103 | AMBA_202_LP056_RSH_OPT
|  |  |  | 85135735103 | AMBA_202_LP058_RSH_OPT
|  |  |  | 85135736103 | AMBA_202_LP060_RSH_OPT
|  |  |  | 85135737103 | AMBA_202_LP061_RSH_OPT
|  |  |  | 85135738103 | AMBA_202_LP062_RSH_OPT
|  |  |  | 85135739103 | AMBA_202_LP105_RSH_OPT
|  |  |  | 85135740103 | AMBA_202_LP129_RSH_OPT
|  |  |  | 85135741103 | AMBA_202_LP157_RSH_OPT
|  |  |  | 85133712103 | AMBA_203_LC007_RSH_OPT
|  |  |  | 85133713103 | AMBA_203_LC016_RSH_OPT
|  |  |  | 85133714103 | AMBA_203_LC020_RSH_OPT
|  |  |  | 85133715103 | AMBA_203_LC045_RSH_OPT
|  |  |  | 85133716103 | AMBA_203_LC047_RSH_OPT
|  |  |  | 85136727103 | AMBA_203_LC058_RSH_OPT
|  |  |  | 85136728103 | AMBA_203_LC059_RSH_OPT
|  |  |  | 85133701103 | AMBA_204_LC014_RSH_OPT
|  |  |  | 85133702103 | AMBA_204_LC023_RSH_OPT
|  |  |  | 85133703103 | AMBA_204_LC025_RSH_OPT
|  |  |  | 85133704103 | AMBA_204_LC041_RSH_OPT
|  |  |  | 85131697103 | AMBA_204_LC043_RSH_OPT
|  |  |  | 85131698103 | AMBA_204_LC044_RSH_OPT
|  |  |  | 85133705103 | AMBA_204_LP136_RSH_OPT
|  |  |  | 85136729103 | AMBA_205_LC001_RSH_OPT
|  |  |  | 85136730103 | AMBA_205_LC036_RSH_OPT
|  |  |  | 85136731103 | AMBA_205_LC037_RSH_OPT
|  |  |  | 85140702103 | AMBA_205_LC046_RSH_OPT
|  |  |  | 85117708103 | AMBA_206_LP022_RSH_OPT
|  |  |  | 85117709103 | AMBA_206_LP034_RSH_OPT
|  |  |  | 85117710103 | AMBA_206_LP038_RSH_OPT
|  |  |  | 85117711103 | AMBA_206_LP074_RSH_OPT
|  |  |  | 85117712103 | AMBA_206_LP078_RSH_OPT
|  |  |  | 85132722103 | AMBA_206_LP079_RSH_OPT
|  |  |  | 85132723103 | AMBA_206_LP080_RSH_OPT
|  |  |  | 85132724103 | AMBA_206_LP115_RSH_OPT
|  |  |  | 85132725103 | AMBA_206_LP116_RSH_OPT
|  |  |  | 85133706103 | AMBA_207_LC021_RSH_OPT
|  |  |  | 85134697103 | AMBA_207_LC022_RSH_OPT
|  |  |  | 85131699103 | AMBA_207_LC024_RSH_OPT
|  |  |  | 85134698103 | AMBA_207_LC027_RSH_OPT
|  |  |  | 85134699103 | AMBA_207_LC031_RSH_OPT
|  |  |  | 85134700103 | AMBA_207_LC033_RSH_OPT
|  |  |  | 85134701103 | AMBA_207_LC034_RSH_OPT
|  |  |  | 85132702103 | AMBA_207_LC038_RSH_OPT
|  |  |  | 85132703103 | AMBA_207_LC039_RSH_OPT
|  |  |  | 85131700103 | AMBA_207_LC040_RSH_OPT
|  |  |  | 85132704103 | AMBA_207_LC052_RSH_OPT
|  |  |  | 85132705103 | AMBA_207_LC064_RSH_OPT
|  |  |  | 85133710103 | AMBA_209_LP030_RSH_OPT
|  |  |  | 85133711103 | AMBA_209_LP031_RSH_OPT
|  |  |  | 85139697103 | AMBA_209_LP066_RSH_OPT
|  |  |  | 85139698103 | AMBA_209_LP073_RSH_OPT
|  |  |  | 85139699103 | AMBA_209_LP090_RSH_OPT
|  |  |  | 85139700103 | AMBA_209_LP091_RSH_OPT
|  |  |  | 85139701103 | AMBA_209_LP093_RSH_OPT
|  |  |  | 85135712103 | AMBA_209_LP122_RSH_OPT
|  |  |  | 85135713103 | AMBA_209_LP126_RSH_OPT
|  |  |  | 85135714103 | AMBA_209_LP127_RSH_OPT
|  |  |  | 85135715103 | AMBA_209_LP135_RSH_OPT
|  |  |  | 85140703103 | AMBA_210_LP036_RSH_OPT
|  |  |  | 85140704103 | AMBA_210_LP087_RSH_OPT
|  |  |  | 85133699103 | AMBA_211_LC008_RSH_OPT
|  |  |  | 85140705103 | AMBA_211_LC013_RSH_OPT
|  |  |  | 85140706103 | AMBA_211_LC026_RSH_OPT
|  |  |  | 85139707103 | AMBA_211_LC029_RSH_OPT
|  |  |  | 85139708103 | AMBA_211_LC030_RSH_OPT
|  |  |  | 85139709103 | AMBA_211_LC032_RSH_OPT
|  |  |  | 85139710103 | AMBA_211_LC035_RSH_OPT
|  |  |  | 85139711103 | AMBA_211_LC053_RSH_OPT
|  |  |  | 85137732103 | AMBA_211_LC054_RSH_OPT
|  |  |  | 85137733103 | AMBA_211_LC055_RSH_OPT
|  |  |  | 85137734103 | AMBA_211_LC063_RSH_OPT
|  |  |  | 85137735103 | AMBA_211_LP010_RSH_OPT
|  |  |  | 85137736103 | AMBA_211_LP039_RSH_OPT
|  |  |  | 85137737103 | AMBA_211_LP040_RSH_OPT
|  |  |  | 85137738103 | AMBA_211_LP086_RSH_OPT
|  |  |  | 85132726103 | AMBA_212_LP024_RSH_OPT
|  |  |  | 85135702103 | AMBA_212_LP027_RSH_OPT
|  |  |  | 85132701103 | AMBA_212_LP037_RSH_OPT
|  |  |  | 85133697103 | AMBA_212_LP044_RSH_OPT
|  |  |  | 85133698103 | AMBA_212_LP072_RSH_OPT
|  |  |  | 85135703103 | AMBA_212_LP081_RSH_OPT
|  |  |  | 85135704103 | AMBA_212_LP082_RSH_OPT
|  |  |  | 85135705103 | AMBA_212_LP083_RSH_OPT
|  |  |  | 85135706103 | AMBA_212_LP084_RSH_OPT
|  |  |  | 85136702103 | AMBA_212_LP085_RSH_OPT
|  |  |  | 85136703103 | AMBA_212_LP118_RSH_OPT
|  |  |  | 85136704103 | AMBA_212_LP119_RSH_OPT
|  |  |  | 87725697103 | AMBA_215_LP001_OPT
|  |  |  | 85137739103 | AMBA_215_LP043_RSH_OPT
|  |  |  | 85137740103 | AMBA_215_LP045_RSH_OPT
|  |  |  | 85137741103 | AMBA_215_LP094_RSH_OPT
|  |  |  | 85114707103 | AMBA_215_LP134_RSH_OPT
|  |  |  | 85135716103 | AMBA_228_BS312_RSH_OPT
|  |  |  | 85117713103 | AMBA_228_KS220_RSH_OPT
|  |  |  | 85117714103 | AMBA_228_KS281_RSH_OPT
|  |  |  | 85117715103 | AMBA_228_KS282_RSH_OPT
|  |  |  | 85117716103 | AMBA_228_KS324_RSH_OPT
|  |  |  | 85117717103 | AMBA_228_KS350_RSH_OPT
|  |  |  | 85139702103 | AMBA_228_KS461_RSH_OPT
|  |  |  | 85139703103 | AMBA_228_KS476_RSH_OPT
|  |  |  | 85114708103 | AMBA_229_BS080_RSH_OPT
|  |  |  | 85114709103 | AMBA_229_BS113_RSH_OPT
|  |  |  | 85114710103 | AMBA_229_BS114_RSH_OPT
|  |  |  | 85114711103 | AMBA_229_BS143_RSH_OPT
|  |  |  | 85140707103 | AMBA_229_BS197_RSH_OPT
|  |  |  | 85140708103 | AMBA_229_BS230_RSH_OPT
|  |  |  | 85140709103 | AMBA_229_BS232_RSH_OPT
|  |  |  | 85140710103 | AMBA_229_BS233_RSH_OPT
|  |  |  | 86830826103 | AMBA_238_BH065_RSH_OPT
|  |  |  | 86830756103 | AMBA_238_BH309_RSH_OPT
|  |  |  | 85140711103 | AMBA_239_LP015_RSH_OPT
|  |  |  | 85116716103 | AMBA_239_LP046_RSH_OPT
|  |  |  | 85116717103 | AMBA_239_LP095_RSH_OPT
|  |  |  | 85116718103 | AMBA_239_LP098_RSH_OPT
|  |  |  | 85116719103 | AMBA_239_LP109_RSH_OPT
|  |  |  | 85116720103 | AMBA_239_LP111_RSH_OPT
|  |  |  | 85138707103 | AMBA_239_LP133_RSH_OPT
|  |  |  | 85138708103 | AMBA_239_LP903_RSH_OPT
|  |  |  | 86830714103 | AMBA_24_BN078_RSH_OPT
|  |  |  | 86830702103 | AMBA_24_BN149_RSH_OPT
|  |  |  | 86830700103 | AMBA_24_BN276_RSH_OPT
|  |  |  | 86830720103 | AMBA_24_BN277_RSH_OPT
|  |  |  | 86830701103 | AMBA_24_BN318_RSH_OPT
|  |  |  | 86830718103 | AMBA_24_BN468_RSH_OPT
|  |  |  | 86830719103 | AMBA_24_BN471_RSH_OPT
|  |  |  | 86830807103 | AMBA_253_BN095_RSH_OPT
|  |  |  | 86830786103 | AMBA_253_BN408_RSH_OPT
|  |  |  | 86830752103 | AMBA_253_BN454_RSH_OPT
|  |  |  | 86830751103 | AMBA_253_BN460_RSH_OPT
|  |  |  | 86830799103 | AMBA_253_BN461_RSH_OPT
|  |  |  | 86830757103 | AMBA_253_BN863_RSH_OPT
|  |  |  | 86830725103 | AMBA_254_KN049_RSH_OPT
|  |  |  | 86830727103 | AMBA_254_KN086_RSH_OPT
|  |  |  | 86830772103 | AMBA_254_KN104_RSH_OPT
|  |  |  | 86830726103 | AMBA_254_KN288_RSH_OPT
|  |  |  | 86830728103 | AMBA_254_KN307_RSH_OPT
|  |  |  | 86830724103 | AMBA_254_KN321_RSH_OPT
|  |  |  | 86830723103 | AMBA_254_KN345_RSH_OPT
|  |  |  | 86830722103 | AMBA_254_KN346_RSH_OPT
|  |  |  | 85114721103 | AMBA_55_BN127_RSH_OPT
|  |  |  | 85136732103 | AMBA_55_BN908_RSH_OPT
|  |  |  | 87394707103 | AMBA_56_BN116_RSH_OPT
|  |  |  | 87394711103 | AMBA_56_BN147_RSH_OPT
|  |  |  | 87394706103 | AMBA_56_BN209_RSH_OPT
|  |  |  | 87394705103 | AMBA_56_BN215_RSH_OPT
|  |  |  | 87394710103 | AMBA_56_BN250_RSH_OPT
|  |  |  | 87394704103 | AMBA_56_BN446_RSH_OPT
|  |  |  | 87394703103 | AMBA_56_BN448_RSH_OPT
|  |  |  | 87394708103 | AMBA_56_BN484_RSH_OPT
|  |  |  | 87394709103 | AMBA_56_BN489_RSH_OPT
|  |  |  | 87409699103 | AMBA_56_NPU038_RSH_OPT
|  |  |  | 87410716103 | AMBA_56_NPU1591_RSH_OPT
|  |  |  | 87410715103 | AMBA_56_NPU352_RSH_OPT
|  |  |  | 87409698103 | AMBA_56_NPU353_RSH_OPT
|  |  |  | 85136733103 | AMBA_61_BN297_RSH_OPT
|  |  |  | 85136734103 | AMBA_61_BN432_RSH_OPT
|  |  |  | 85136735103 | AMBA_62_BN403_RSH_OPT
|  |  |  | 85136736103 | AMBA_62_BN479_RSH_OPT
|  |  |  | 85138717103 | AMBA_62_BN903_RSH_OPT
|  |  |  | 85138718103 | AMBA_62_BN905_RSH_OPT
|  |  |  | 87394700103 | AMBA_63_BN092_RSH_OPT
|  |  |  | 87394702103 | AMBA_63_BN118_RSH_OPT
|  |  |  | 87394701103 | AMBA_63_BN148_RSH_OPT
|  |  |  | 87394698103 | AMBA_63_BN308_RSH_OPT
|  |  |  | 87394699103 | AMBA_63_BN325_RSH_OPT
|  |  |  | 85138719103 | AMBA_64_BN137_RSH_OPT
|  |  |  | 85138720103 | AMBA_64_BN262_RSH_OPT
|  |  |  | 85138721103 | AMBA_64_BN263_RSH_OPT
|  |  |  | 85137757103 | AMBA_64_BN288_RSH_OPT
|  |  |  | 85137758103 | AMBA_64_BN340_RSH_OPT
|  |  |  | 86830707103 | AMBA_67_BN172_RSH_OPT
|  |  |  | 86830715103 | AMBA_67_BN231_RSH_OPT
|  |  |  | 93595698103 | AMBA_BN112_Swap_MVS
|  |  |  | 93595699103 | AMBA_BN187_Swap_MVS
|  |  |  | 93595700103 | AMBA_BN240_Swap_MVS
|  |  |  | 93617702103 | AMBA_BN299_Swap_MVS
|  |  |  | 93617703103 | AMBA_BN304_Swap_MVS
|  |  |  | 93595701103 | AMBA_BN310_Swap_MVS
|  |  |  | 93595702103 | AMBA_BN329_Swap_MVS
|  |  |  | 93617697103 | AMBA_BN344_Swap_MVS
|  |  |  | 93617704103 | AMBA_BN417_Swap_MVS
|  |  |  | 93617705103 | AMBA_BN433_Swap_MVS
|  |  |  | 93617706103 | AMBA_BN447_Swap_MVS
|  |  |  | 93617698103 | AMBA_BN472_Swap_MVS
|  |  |  | 93617699103 | AMBA_BN475_Swap_MVS
|  |  |  | 93617700103 | AMBA_BO021_Swap_MVS
|  |  |  | 93617701103 | AMBA_BO059_Swap_MVS
|  |  |  | 93556699103 | AMBA_BO157_Swap_MVS
|  |  |  | 93556700103 | AMBA_BO168_Swap_MVS
|  |  |  | 93556701103 | AMBA_BO243_Swap_MVS
|  |  |  | 93556702103 | AMBA_BO255_Swap_MVS
|  |  |  | 93556703103 | AMBA_BO314_Swap_MVS
|  |  |  | 93617707103 | AMBA_BO365_Swap_MVS
|  |  |  | 93617708103 | AMBA_BO369_Swap_MVS
|  |  |  | 93617709103 | AMBA_BO372_Swap_MVS
|  |  |  | 93617710103 | AMBA_BO375_Swap_MVS
|  |  |  | 93617711103 | AMBA_BO440_Swap_MVS
|  |  |  | 93556704103 | AMBA_BO492_Swap_MVS
|  |  |  | 93617712103 | AMBA_BO494_Swap_MVS
|  |  |  | 93617713103 | AMBA_BO498_Swap_MVS
|  |  |  | 93617717103 | AMBA_BO832_Swap_MVS
|  |  |  | 93617718103 | AMBA_BO834_Swap_MVS
|  |  |  | 93617719103 | AMBA_BO836_Swap_MVS
|  |  |  | 93617720103 | AMBA_BO838_Swap_MVS
|  |  |  | 93617721103 | AMBA_BO841_Swap_MVS
|  |  |  | 93556705103 | AMBA_BO842_Swap_MVS
|  |  |  | 93556706103 | AMBA_BO846_Swap_MVS
|  |  |  | 93556707103 | AMBA_BO861_Swap_MVS
|  |  |  | 93617714103 | AMBA_BO862_Swap_MVS
|  |  |  | 93617715103 | AMBA_BO866_Swap_MVS
|  |  |  | 93617716103 | AMBA_BO873_Swap_MVS
|  |  |  | 93617722103 | AMBA_KN090_Swap_MVS
|  |  |  | 93617723103 | AMBA_KN131_Swap_MVS
|  |  |  | 93617724103 | AMBA_KN242_Swap_MVS
|  |  |  | 93556708103 | AMBA_KN249_Swap_MVS
|  |  |  | 93617727103 | AMBA_KN265_Swap_MVS
|  |  |  | 93617725103 | AMBA_KN287_Swap_MVS
|  |  |  | 93617726103 | AMBA_KO049_Swap_MVS
|  |  |  | 93556709103 | AMBA_KO211_Swap_MVS
|  |  |  | 93556710103 | AMBA_KO213_Swap_MVS
|  |  |  | 93556711103 | AMBA_KO235_Swap_MVS
|  |  |  | 93556712103 | AMBA_KO237_Swap_MVS
|  |  |  | 93556713103 | AMBA_KO241_Swap_MVS
|  |  |  | 87636697103 | BA_ARBA0018_FARM_Etapa1_MVS
|  |  |  | 87524704103 | BA_ARBA0121_FARM_Etapa1_MVS
|  |  |  | 87524699103 | BA_ARBA0135_FARM_Etapa1_MVS
|  |  |  | 87524702103 | BA_ARBA0169_FARM_Etapa1_MVS
|  |  |  | 87524703103 | BA_ARBA0222_FARM_Etapa1_MVS
|  |  |  | 87524710103 | BA_ARBA0250_FARM_Etapa1_MVS
|  |  |  | 87670697103 | BA_ARBA0440_FARM_Etapa1_MVS
|  |  |  | 87524708103 | BA_ARBA0464_FARM_Dismantle_MVS
|  |  |  | 87524709103 | BA_ARBA0471_FARM_Etapa1_MVS
|  |  |  | 87636701103 | BA_ARBA0571_FARM_Etapa1_MVS
|  |  |  | 87659697103 | BA_ARBA0575_FARM_Etapa1_MVS
|  |  |  | 87670698103 | BA_ARBA0588_FARM_Etapa1_MVS
|  |  |  | 87524707103 | BA_ARBA0591_FARM_Etapa1_MVS
|  |  |  | 87524705103 | BA_ARBA0642_FARM_Etapa1_MVS
|  |  |  | 87637697103 | BA_ARBA0707_FARM_Etapa1_MVS
|  |  |  | 87524706103 | BA_ARBA0729_FARM_Etapa1_MVS
|  |  |  | 87477702103 | BA_ARBA10312_FARM_Etapa1_MVS
|  |  |  | 87632697103 | BA_ARBA10477_FARM_Etapa1_MVS
|  |  |  | 87636700103 | BA_ARBA1189_FARM_Etapa1_MVS
|  |  |  | 87636699103 | BA_ARBA6698_FARM_Etapa1_MVS
|  |  |  | 87524700103 | BA_ARBA8171_FARM_Etapa1_MVS
|  |  |  | 87636698103 | BA_ARBA8267_FARM_Etapa1_MVS
|  |  |  | 87524698103 | BA_ARBA9114_FARM_Etapa1_MVS
|  |  |  | 87524701103 | BA_ARBA9306_FARM_Etapa1_MVS
|  |  |  | 86826701103 | BA_BB003_Swap_MVS
|  |  |  | 86826699103 | BA_BB004_Swap_MVS
|  |  |  | 87510704103 | BA_BB007_Swap_MVS
|  |  |  | 87511706103 | BA_BB008_Swap_MVS
|  |  |  | 86827697103 | BA_BB011_Swap_MVS
|  |  |  | 87497726103 | BA_BB019_Swap_MVS
|  |  |  | 87497725103 | BA_BB020_Swap_MVS
|  |  |  | 87511704103 | BA_BB028_Swap_MVS
|  |  |  | 87503704103 | BA_BB031_Swap_MVS
|  |  |  | 87511702103 | BA_BB032_Swap_MVS
|  |  |  | 87511701103 | BA_BB033_Swap_MVS
|  |  |  | 87499704103 | BA_BB039_Swap_MVS
|  |  |  | 87497714103 | BA_BB042_Swap_MVS
|  |  |  | 87497711103 | BA_BB045_Swap_MVS
|  |  |  | 87497707103 | BA_BB046_Swap_MVS
|  |  |  | 87503705103 | BA_BB048_Swap_MVS
|  |  |  | 87510700103 | BA_BB056_Swap_MVS
|  |  |  | 86789699103 | BA_BB058_Swap_MVS
|  |  |  | 87510702103 | BA_BB059_Swap_MVS
|  |  |  | 87497721103 | BA_BB062_Swap_MVS
|  |  |  | 87497716103 | BA_BB063_Swap_MVS
|  |  |  | 86827700103 | BA_BB064_Swap_MVS
|  |  |  | 86826697103 | BA_BB071_Swap_MVS
|  |  |  | 86789701103 | BA_BB075_Swap_MVS
|  |  |  | 86827698103 | BA_BB076_Swap_MVS
|  |  |  | 86827699103 | BA_BB077_Swap_MVS
|  |  |  | 86826700103 | BA_BB081_Swap_MVS
|  |  |  | 87497712103 | BA_BB086_Swap_MVS
|  |  |  | 87511703103 | BA_BB090_Swap_MVS
|  |  |  | 87503703103 | BA_BB094_Swap_MVS
|  |  |  | 87497717103 | BA_BB097_Swap_MVS
|  |  |  | 87511705103 | BA_BB098_Swap_MVS
|  |  |  | 87497710103 | BA_BB099_Swap_MVS
|  |  |  | 87511700103 | BA_BB101_Swap_MVS
|  |  |  | 87497724103 | BA_BB102_Swap_MVS
|  |  |  | 86827701103 | BA_BB109_Swap_MVS
|  |  |  | 87511699103 | BA_BB113_Swap_MVS
|  |  |  | 86789702103 | BA_BB122_Swap_MVS
|  |  |  | 87497709103 | BA_BB141_Swap_MVS
|  |  |  | 86826702103 | BA_BB173_Swap_MVS
|  |  |  | 86789700103 | BA_BB185_Swap_MVS
|  |  |  | 87503707103 | BA_BB190_Swap_MVS
|  |  |  | 87497719103 | BA_BB313_Swap_MVS
|  |  |  | 87497720103 | BA_BB314_Swap_MVS
|  |  |  | 87510699103 | BA_BB317_Swap_MVS
|  |  |  | 87497715103 | BA_BB319_Swap_MVS
|  |  |  | 87503706103 | BA_BB323_Swap_MVS
|  |  |  | 87497718103 | BA_BB324_Swap_MVS
|  |  |  | 87497713103 | BA_BB330_Swap_MVS
|  |  |  | 87511698103 | BA_BB336_Swap_MVS
|  |  |  | 87511697103 | BA_BB337_Swap_MVS
|  |  |  | 87499708103 | BA_BB338_Swap_MVS
|  |  |  | 87499707103 | BA_BB339_Swap_MVS
|  |  |  | 87499706103 | BA_BB340_Swap_MVS
|  |  |  | 87510701103 | BA_BB341_Swap_MVS
|  |  |  | 87510703103 | BA_BB344_Swap_MVS
|  |  |  | 87497708103 | BA_BB345_Swap_MVS
|  |  |  | 86789698103 | BA_BB351_Swap_MVS
|  |  |  | 87497723103 | BA_BB370_Swap_MVS
|  |  |  | 87497722103 | BA_BB371_Swap_MVS
|  |  |  | 86826698103 | BA_BB378_Swap_MVS
|  |  |  | 87499705103 | BA_BB400_Swap_MVS
|  |  |  | 87705698103 | BA_BM021_Swap_MVS
|  |  |  | 87740700103 | BA_BM039_Swap_MVS
|  |  |  | 87740706103 | BA_BM055_Swap_MVS
|  |  |  | 87503699103 | BA_BM056_Swap_MVS
|  |  |  | 87510697103 | BA_BM058_Swap_MVS
|  |  |  | 87740713103 | BA_BM099_Swap_MVS
|  |  |  | 87499703103 | BA_BM328_Swap_MVS
|  |  |  | 87740705103 | BA_BM331_Swap_MVS
|  |  |  | 87497706103 | BA_BM332_Swap_MVS
|  |  |  | 87741699103 | BA_BM334_Swap_MVS
|  |  |  | 87499702103 | BA_BM338_Swap_MVS
|  |  |  | 87740699103 | BA_BM339_Swap_MVS
|  |  |  | 87740698103 | BA_BM349_Swap_MVS
|  |  |  | 87503698103 | BA_BM353_Swap_MVS
|  |  |  | 87741698103 | BA_BM354_Swap_MVS
|  |  |  | 87499701103 | BA_BM358_Swap_MVS
|  |  |  | 87740710103 | BA_BM361_Swap_MVS
|  |  |  | 87497705103 | BA_BM362_Swap_MVS
|  |  |  | 87497704103 | BA_BM372_Swap_MVS
|  |  |  | 87741697103 | BA_BM394_Swap_MVS
|  |  |  | 87499700103 | BA_BM531_Swap_MVS
|  |  |  | 87740711103 | BA_BM576_Swap_MVS
|  |  |  | 87499699103 | BA_BM588_Swap_MVS
|  |  |  | 87510698103 | BA_BM648_Swap_MVS
|  |  |  | 87740701103 | BA_BM649_Swap_MVS
|  |  |  | 87509701103 | BA_BM653_Swap_MVS
|  |  |  | 87509700103 | BA_BM654_Swap_MVS
|  |  |  | 87497703103 | BA_BM659_Swap_MVS
|  |  |  | 87497702103 | BA_BM661_Swap_MVS
|  |  |  | 87503702103 | BA_BM663_Swap_MVS
|  |  |  | 87740712103 | BA_BM676_Swap_MVS
|  |  |  | 87740707103 | BA_BM680_Swap_MVS
|  |  |  | 87742701103 | BA_BM686_Swap_MVS
|  |  |  | 87742700103 | BA_BM688_Swap_MVS
|  |  |  | 87740704103 | BA_BM689_Swap_MVS
|  |  |  | 87740703103 | BA_BM690_Swap_MVS
|  |  |  | 87740702103 | BA_BM691_Swap_MVS
|  |  |  | 87740709103 | BA_BM694_Swap_MVS
|  |  |  | 87742699103 | BA_BM745_Swap_MVS
|  |  |  | 87742698103 | BA_BM746_Swap_MVS
|  |  |  | 87742697103 | BA_BM747_Swap_MVS
|  |  |  | 87705702103 | BA_BM748_Swap_MVS
|  |  |  | 87740697103 | BA_BM757_Swap_MVS
|  |  |  | 87503701103 | BA_BM759_Swap_MVS
|  |  |  | 87503700103 | BA_BM760_Swap_MVS
|  |  |  | 87509699103 | BA_BM761_Swap_MVS
|  |  |  | 87509698103 | BA_BM762_Swap_MVS
|  |  |  | 87509697103 | BA_BM763_Swap_MVS
|  |  |  | 87741701103 | BA_BM764_Swap_MVS
|  |  |  | 87741700103 | BA_BM765_Swap_MVS
|  |  |  | 87740708103 | BA_BM766_Swap_MVS
|  |  |  | 87705701103 | BA_BM783_Swap_MVS
|  |  |  | 87705700103 | BA_BM784_Swap_MVS
|  |  |  | 87705699103 | BA_BM785_Swap_MVS
|  |  |  | 84054700103 | CLUSTER_OPT_SUR_179
|  |  |  | 84054701103 | CLUSTER_OPT_SUR_180
|  |  |  | 84055697103 | CLUSTER_OPT_SUR_181
|  |  |  | 84053703103 | CLUSTER_OPT_SUR_184
|  |  |  | 83991713103 | CLUSTER_OPT_SUR_185
|  |  |  | 83991714103 | CLUSTER_OPT_SUR_186
|  |  |  | 83991715103 | CLUSTER_OPT_SUR_189
|  |  |  | 84055701103 | CLUSTER_OPT_SUR_190
|  |  |  | 83991706103 | CLUSTER_OPT_SUR_191
|  |  |  | 83991707103 | CLUSTER_OPT_SUR_192
|  |  |  | 83991708103 | CLUSTER_OPT_SUR_197
|  |  |  | 83991709103 | CLUSTER_OPT_SUR_198
|  |  |  | 84704697103 | CLUSTER_OPT_SUR_199
|  |  |  | 84054698103 | CLUSTER_OPT_SUR_200
|  |  |  | 84054699103 | CLUSTER_OPT_SUR_201
|  |  |  | 83991710103 | CLUSTER_OPT_SUR_204
|  |  |  | 84053704103 | CLUSTER_OPT_SUR_205
|  |  |  | 84053705103 | CLUSTER_OPT_SUR_206
|  |  |  | 84053706103 | CLUSTER_OPT_SUR_207
|  |  |  | 83991711103 | CLUSTER_OPT_SUR_208
|  |  |  | 83991712103 | CLUSTER_OPT_SUR_328
|  |  |  | 84054697103 | CLUSTER_OPT_SUR_330
|  |  |  | 84055698103 | CLUSTER_OPT_SUR_501
|  |  |  | 84053699103 | CLUSTER_OPT_SUR_514
|  |  |  | 84053698103 | CLUSTER_OPT_SUR_515
|  |  |  | 84053700103 | CLUSTER_OPT_SUR_521
|  |  |  | 84053697103 | CLUSTER_OPT_SUR_523
|  |  |  | 84055699103 | CLUSTER_OPT_SUR_524
|  |  |  | 84053702103 | CLUSTER_OPT_SUR_529
|  |  |  | 84053701103 | CLUSTER_OPT_SUR_531
|  |  |  | 84055700103 | CLUSTER_OPT_SUR_533
|  |  |  | 87111713103 | LP_DC005_Swap_MVS
|  |  |  | 87111712103 | LP_DC006_Swap_MVS
|  |  |  | 87170699103 | LP_DC011_Swap_MVS
|  |  |  | 87170701103 | LP_DC115_Swap_MVS
|  |  |  | 87170700103 | LP_DC310_Swap_MVS
|  |  |  | 87170702103 | LP_DE002_Swap_MVS
|  |  |  | 87171698103 | LP_DE004_Swap_MVS
|  |  |  | 87173706103 | LP_DE006_Swap_MVS
|  |  |  | 87170706103 | LP_DE007_Swap_MVS
|  |  |  | 87173705103 | LP_DE009_Swap_MVS
|  |  |  | 87170697103 | LP_DE011_Swap_MVS
|  |  |  | 87111716103 | LP_DE014_Swap_MVS
|  |  |  | 87106711103 | LP_DE017_Swap_MVS
|  |  |  | 87111714103 | LP_DE018_Swap_MVS
|  |  |  | 87171709103 | LP_DE019_Swap_MVS
|  |  |  | 87106710103 | LP_DE022_Swap_MVS
|  |  |  | 87173698103 | LP_DE025_Swap_MVS
|  |  |  | 87170704103 | LP_DE027_Swap_MVS
|  |  |  | 87171699103 | LP_DE028_Swap_MVS
|  |  |  | 87038726103 | LP_DE029_Swap_MVS
|  |  |  | 87171705103 | LP_DE031_Swap_MVS
|  |  |  | 87173704103 | LP_DE033_Swap_MVS
|  |  |  | 87171703103 | LP_DE039_Swap_MVS
|  |  |  | 87171711103 | LP_DE043_Swap_MVS
|  |  |  | 87111715103 | LP_DE045_Swap_MVS
|  |  |  | 87171701103 | LP_DE046_Swap_MVS
|  |  |  | 87038725103 | LP_DE049_Swap_MVS
|  |  |  | 87171706103 | LP_DE062_Swap_MVS
|  |  |  | 87173703103 | LP_DE067_Swap_MVS
|  |  |  | 87173702103 | LP_DE068_Swap_MVS
|  |  |  | 87173697103 | LP_DE072_Swap_MVS
|  |  |  | 87171697103 | LP_DE304_Swap_MVS
|  |  |  | 87170698103 | LP_DEM99_Swap_MVS
|  |  |  | 87038727103 | LP_DN001_Swap_MVS
|  |  |  | 87173701103 | LP_DN002_Swap_MVS
|  |  |  | 87106709103 | LP_DN012_Swap_MVS
|  |  |  | 87173700103 | LP_DN014_Swap_MVS
|  |  |  | 87170703103 | LP_DN024_Swap_MVS
|  |  |  | 87171708103 | LP_DN025_Swap_MVS
|  |  |  | 87171707103 | LP_DN026_Swap_MVS
|  |  |  | 87106713103 | LP_DN027_Swap_MVS
|  |  |  | 87106712103 | LP_DN032_Swap_MVS
|  |  |  | 87171710103 | LP_DN034_Swap_MVS
|  |  |  | 87173699103 | LP_DN038_Swap_MVS
|  |  |  | 87171702103 | LP_DN050_Swap_MVS
|  |  |  | 87038724103 | LP_DN052_Swap_MVS
|  |  |  | 87106708103 | LP_DS049_Swap_MVS
|  |  |  | 87106707103 | LP_DS050_Swap_MVS
|  |  |  | 87171700103 | LP_DW009_Swap_MVS
|  |  |  | 87171704103 | LP_DW011_Swap_MVS
|  |  |  | 87170705103 | LP_DW012_Swap_MVS
|  |  |  | 87169699103 | NQ_ARNQ0017_FARM_Etapa1_MVS
|  |  |  | 87169701103 | NQ_ARNQ0026_FARM_Etapa2_MVS
|  |  |  | 87091697103 | NQ_ARNQ0047_FARM_Etapa1_MVS
|  |  |  | 87169700103 | NQ_ARNQ0087_FARM_Etapa1_MVS
|  |  |  | 87169698103 | NQ_ARNQ0403_FARM_Etapa1_MVS
|  |  |  | 87169697103 | NQ_ARNQ0487_FARM_Etapa1_MVS
|  |  |  | 85013720103 | NQ_QC003_Swap_MVS
|  |  |  | 85187701103 | NQ_QC005_Swap_MVS
|  |  |  | 85187700103 | NQ_QC007_Swap_MVS
|  |  |  | 85187699103 | NQ_QC012_Swap_MVS
|  |  |  | 85187698103 | NQ_QC013_Swap_MVS
|  |  |  | 85187697103 | NQ_QC021_Swap_MVS
|  |  |  | 85186701103 | NQ_QC024_Swap_MVS
|  |  |  | 85186700103 | NQ_QC037_Swap_MVS
|  |  |  | 85186699103 | NQ_QC044_Swap_MVS
|  |  |  | 85186698103 | NQ_QC052_Swap_MVS
|  |  |  | 85186697103 | NQ_QC054_Swap_MVS
|  |  |  | 85013719103 | NQ_QC055_Swap_MVS
|  |  |  | 85013718103 | NQ_QC059_Swap_MVS
|  |  |  | 85013717103 | NQ_QC074_Swap_MVS
|  |  |  | 85013716103 | NQ_QC099_Swap_MVS
|  |  |  | 84982697103 | NQ_QC105_Swap_MVS
|  |  |  | 85013715103 | NQ_QC348_Swap_MVS
|  |  |  | 85151758103 | NQ_QCM39_Swap_MVS
|  |  |  | 85151757103 | NQ_QE037_Swap_MVS
|  |  |  | 84982698103 | NQ_QE039_Swap_MVS
|  |  |  | 84983703103 | NQ_QE041_Swap_MVS
|  |  |  | 84983702103 | NQ_QE042_Swap_MVS
|  |  |  | 84962700103 | NQ_QN017_Swap_MVS
|  |  |  | 84962703103 | NQ_QN026_Swap_MVS
|  |  |  | 85151756103 | NQ_QN045_Swap_MVS
|  |  |  | 85151755103 | NQ_QN082_Swap_MVS
|  |  |  | 84983700103 | NQ_QS007_Swap_MVS
|  |  |  | 84962702103 | NQ_QS013_Swap_MVS
|  |  |  | 84983701103 | NQ_QS019_Swap_MVS
|  |  |  | 84962699103 | NQ_QS025_Swap_MVS
|  |  |  | 84983699103 | NQ_QS026_Swap_MVS
|  |  |  | 84983698103 | NQ_QS027_Swap_MVS
|  |  |  | 84983697103 | NQ_QS028_Swap_MVS
|  |  |  | 84982701103 | NQ_QS029_Swap_MVS
|  |  |  | 84982700103 | NQ_QS030_Swap_MVS
|  |  |  | 84982699103 | NQ_QS031_Swap_MVS
|  |  |  | 84983704103 | NQ_QS038_Swap_MVS
|  |  |  | 84962701103 | NQ_QS304_Swap_MVS
|  |  |  | 85151754103 | NQ_QW009_Swap_MVS
|  |  |  | 87632698103 | RN_ARRN0050_FARM_Etapa1_MVS
|  |  |  | 85131704103 | SUR_179_BM004_OPT
|  |  |  | 85131706103 | SUR_179_BM506_OPT
|  |  |  | 85136697103 | SUR_179_BM584_OPT
|  |  |  | 85136698103 | SUR_179_BM749_OPT
|  |  |  | 85136699103 | SUR_179_BM750_OPT
|  |  |  | 85136700103 | SUR_179_BM751_OPT
|  |  |  | 85136701103 | SUR_179_BM752_OPT
|  |  |  | 85137697103 | SUR_179_BM805_OPT
|  |  |  | 85137698103 | SUR_179_BM806_OPT
|  |  |  | 85137699103 | SUR_179_BM808_OPT
|  |  |  | 85137700103 | SUR_179_BM809_OPT
|  |  |  | 87572710103 | SUR_181_BM600_OPT
|  |  |  | 87572709103 | SUR_181_BM602_OPT
|  |  |  | 87572708103 | SUR_181_BM603_OPT
|  |  |  | 85138709103 | SUR_184_BM031_RSH_OPT
|  |  |  | 85138710103 | SUR_184_BM102_RSH_OPT_4G
|  |  |  | 85138711103 | SUR_184_BM326_RSH_OPT
|  |  |  | 85116721103 | SUR_184_BM385_RSH_OPT
|  |  |  | 85116722103 | SUR_184_BM484_RSH_OPT
|  |  |  | 85116723103 | SUR_184_BM510_RSH_OPT
|  |  |  | 85116724103 | SUR_184_BM605_RSH_OPT
|  |  |  | 85116725103 | SUR_184_BM606_RSH_OPT
|  |  |  | 85113732103 | SUR_184_BM608_RSH_OPT
|  |  |  | 85113733103 | SUR_184_BM609_RSH_OPT
|  |  |  | 85113734103 | SUR_184_BM610_RSH_OPT
|  |  |  | 85133700103 | SUR_184_BM611_RSH_OPT
|  |  |  | 85113735103 | SUR_184_BM699_RSH_OPT
|  |  |  | 85139704103 | SUR_185_BM008_RSH_OPT
|  |  |  | 85139705103 | SUR_185_BM013_RSH_OPT
|  |  |  | 85139706103 | SUR_185_BM078_RSH_OPT
|  |  |  | 85137712103 | SUR_185_BM306_RSH_OPT
|  |  |  | 85137713103 | SUR_185_BM314_RSH_OPT
|  |  |  | 85137714103 | SUR_185_BM379_RSH_OPT
|  |  |  | 85137715103 | SUR_185_BM511_RSH_OPT
|  |  |  | 85137716103 | SUR_185_BM512_RSH_OPT
|  |  |  | 85135717103 | SUR_185_BM593_RSH_OPT
|  |  |  | 85135718103 | SUR_185_BM731_RSH_OPT
|  |  |  | 85135719103 | SUR_186_BM305_RSH_OPT
|  |  |  | 85135720103 | SUR_186_BM312_RSH_OPT
|  |  |  | 85135721103 | SUR_186_BM351_RSH_OPT
|  |  |  | 85137717103 | SUR_186_BM513_RSH_OPT
|  |  |  | 85137718103 | SUR_186_BM557_RSH_OPT
|  |  |  | 85137719103 | SUR_186_BM561_RSH_OPT
|  |  |  | 85137720103 | SUR_186_BM728_RSH_OPT
|  |  |  | 85137721103 | SUR_186_BM730_RSH_OPT
|  |  |  | 85136712103 | SUR_186_BM854_RSH_OPT
|  |  |  | 85136713103 | SUR_186_BM855_RSH_OPT
|  |  |  | 85136714103 | SUR_186_BM858_RSH_OPT
|  |  |  | 85136715103 | SUR_186_BM927_RSH_OPT
|  |  |  | 86807714103 | SUR_187_BM035_RSH_OPT
|  |  |  | 86819704103 | SUR_187_BM051_RSH_OPT
|  |  |  | 86819703103 | SUR_187_BM301_RSH_OPT
|  |  |  | 86807713103 | SUR_187_BM724_RSH_OPT
|  |  |  | 86819702103 | SUR_187_BM902_RSH_OPT
|  |  |  | 87724707103 | SUR_188_BM037_OPT
|  |  |  | 87724706103 | SUR_188_BM057_OPT
|  |  |  | 87724705103 | SUR_188_BM061_OPT
|  |  |  | 87724704103 | SUR_188_BM107_OPT
|  |  |  | 87724703103 | SUR_188_BM303_OPT
|  |  |  | 87724702103 | SUR_188_BM357_OPT
|  |  |  | 87724701103 | SUR_188_BM527_OPT
|  |  |  | 87724700103 | SUR_188_BM542_OPT
|  |  |  | 87724699103 | SUR_188_BM550_OPT
|  |  |  | 87724698103 | SUR_188_BM585_OPT
|  |  |  | 87724697103 | SUR_188_BM725_OPT
|  |  |  | 85136716103 | SUR_189_BM063_RSH_OPT
|  |  |  | 85132732103 | SUR_189_BM068_RSH_OPT
|  |  |  | 85132733103 | SUR_189_BM086_RSH_OPT_4G
|  |  |  | 85132734103 | SUR_189_BM304_RSH_OPT
|  |  |  | 85132735103 | SUR_189_BM347_RSH_OPT
|  |  |  | 85132736103 | SUR_189_BM520_RSH_OPT
|  |  |  | 85136717103 | SUR_189_BM522_RSH_OPT
|  |  |  | 85136718103 | SUR_189_BM523_RSH_OPT
|  |  |  | 85136719103 | SUR_189_BM524_RSH_OPT
|  |  |  | 85136720103 | SUR_189_BM554_RSH_OPT
|  |  |  | 85136721103 | SUR_189_BM555_RSH_OPT
|  |  |  | 85113717103 | SUR_189_BM697_RSH_OPT
|  |  |  | 85113718103 | SUR_189_BM726_RSH_OPT
|  |  |  | 86819714103 | SUR_190_BM050_RSH_OPT
|  |  |  | 86807709103 | SUR_190_BM090_RSH_OPT
|  |  |  | 86807699103 | SUR_190_BM308_RSH_OPT
|  |  |  | 98231697103 | SUR_190_BM308_RSH_OPT_5G
|  |  |  | 86807705103 | SUR_190_BM310_RSH_OPT
|  |  |  | 86807715103 | SUR_190_BM336_RSH_OPT
|  |  |  | 86807716103 | SUR_190_BM344_RSH_OPT
|  |  |  | 86807707103 | SUR_190_BM350_RSH_OPT
|  |  |  | 86807704103 | SUR_190_BM378_RSH_OPT
|  |  |  | 86828698103 | SUR_190_BM529_RSH_OPT
|  |  |  | 86807708103 | SUR_191_BM002_RSH_OPT
|  |  |  | 86828697103 | SUR_191_BM032_RSH_OPT
|  |  |  | 86819700103 | SUR_191_BM111_RSH_OPT
|  |  |  | 86807717103 | SUR_191_BM377_RSH_OPT
|  |  |  | 86807700103 | SUR_191_BM411_RSH_OPT
|  |  |  | 86807701103 | SUR_191_BM421_RSH_OPT
|  |  |  | 86807710103 | SUR_191_BM515_RSH_OPT
|  |  |  | 86807711103 | SUR_191_BM516_RSH_OPT
|  |  |  | 86807712103 | SUR_191_BM517_RSH_OPT
|  |  |  | 86807706103 | SUR_192_BM003_RSH_OPT
|  |  |  | 86807698103 | SUR_192_BM011_RSH_OPT
|  |  |  | 86819711103 | SUR_197_BM342_RSH_OPT
|  |  |  | 86819701103 | SUR_197_BM408_RSH_OPT
|  |  |  | 86819712103 | SUR_197_BM507_RSH_OPT
|  |  |  | 86819709103 | SUR_197_BM508_RSH_OPT
|  |  |  | 86819710103 | SUR_197_BM591_RSH_OPT
|  |  |  | 86819713103 | SUR_197_BM592_RSH_OPT
|  |  |  | 86819705103 | SUR_197_BM800_RSH_OPT
|  |  |  | 86819706103 | SUR_197_BM801_RSH_OPT
|  |  |  | 86819707103 | SUR_197_BM802_RSH_OPT
|  |  |  | 86819708103 | SUR_197_BM804_RSH_OPT
|  |  |  | 86807703103 | SUR_198_BM034_RSH_OPT
|  |  |  | 86807702103 | SUR_198_BM704_RSH_OPT
|  |  |  | 85973697103 | SUR_199_BM103_RSH_OPT
|  |  |  | 85137701103 | SUR_199_BM129_OPT
|  |  |  | 85131707103 | SUR_199_BM316_OPT
|  |  |  | 85131708103 | SUR_199_BM329_OPT
|  |  |  | 85131709103 | SUR_199_BM391_OPT
|  |  |  | 85131710103 | SUR_199_BM638_OPT
|  |  |  | 85132697103 | SUR_199_BM640_OPT
|  |  |  | 85132698103 | SUR_199_BM642_OPT
|  |  |  | 85132699103 | SUR_199_BM643_OPT
|  |  |  | 85132700103 | SUR_199_BM778_OPT
|  |  |  | 85132706103 | SUR_200_BM010_RSH_OPT
|  |  |  | 85134702103 | SUR_200_BM091_RSH_OPT
|  |  |  | 85131701103 | SUR_200_BM392_RSH_OPT
|  |  |  | 85134703103 | SUR_200_BM645_RSH_OPT
|  |  |  | 85134704103 | SUR_200_BM646_RSH_OPT
|  |  |  | 85134705103 | SUR_200_BM773_RSH_OPT
|  |  |  | 85134706103 | SUR_201_BM096_RSH_OPT
|  |  |  | 85134707103 | SUR_201_BM319_RSH_OPT
|  |  |  | 85134708103 | SUR_201_BM356_RSH_OPT
|  |  |  | 85134709103 | SUR_201_BM396_RSH_OPT
|  |  |  | 85134710103 | SUR_201_BM533_RSH_OPT
|  |  |  | 85134711103 | SUR_201_BM534_RSH_OPT
|  |  |  | 85135697103 | SUR_201_BM552_RSH_OPT
|  |  |  | 85135698103 | SUR_201_BM633_RSH_OPT
|  |  |  | 85135699103 | SUR_201_BM634_RSH_OPT
|  |  |  | 85135700103 | SUR_201_BM635_RSH_OPT
|  |  |  | 85135701103 | SUR_201_BM777_RSH_OPT
|  |  |  | 85131702103 | SUR_201_BM838_RSH_OPT
|  |  |  | 85131703103 | SUR_201_BM839_RSH_OPT
|  |  |  | 85131711103 | SUR_204_BM375_OPT
|  |  |  | 85113736103 | SUR_205_BM025_RSH_OPT
|  |  |  | 85114712103 | SUR_205_BM104_RSH_OPT
|  |  |  | 85114713103 | SUR_205_BM335_RSH_OPT
|  |  |  | 85114714103 | SUR_205_BM359_RSH_OPT
|  |  |  | 85114715103 | SUR_205_BM381_RSH_OPT
|  |  |  | 85114716103 | SUR_205_BM382_RSH_OPT
|  |  |  | 85116726103 | SUR_205_BM387_RSH_OPT
|  |  |  | 85116727103 | SUR_205_BM390_RSH_OPT
|  |  |  | 85116728103 | SUR_205_BM616_RSH_OPT
|  |  |  | 85116729103 | SUR_205_BM618_RSH_OPT
|  |  |  | 85116730103 | SUR_205_BM781_RSH_OPT
|  |  |  | 85132742103 | SUR_206_BM040_RSH_OPT
|  |  |  | 85132743103 | SUR_206_BM343_RSH_OPT
|  |  |  | 85132744103 | SUR_206_BM364_RSH_OPT
|  |  |  | 85132745103 | SUR_206_BM365_RSH_OPT
|  |  |  | 85132746103 | SUR_206_BM563_RSH_OPT
|  |  |  | 85138712103 | SUR_206_BM626_RSH_OPT
|  |  |  | 85138713103 | SUR_206_BM631_RSH_OPT
|  |  |  | 85138714103 | SUR_206_BM632_RSH_OPT
|  |  |  | 85138715103 | SUR_206_BM779_RSH_OPT
|  |  |  | 85138716103 | SUR_207_BM093_RSH_OPT
|  |  |  | 85137742103 | SUR_207_BM320_RSH_OPT
|  |  |  | 85137743103 | SUR_207_BM369_RSH_OPT
|  |  |  | 85137744103 | SUR_207_BM388_RSH_OPT
|  |  |  | 85137745103 | SUR_207_BM424_RSH_OPT
|  |  |  | 85137746103 | SUR_207_BM551_RSH_OPT
|  |  |  | 85140712103 | SUR_207_BM622_RSH_OPT
|  |  |  | 85140713103 | SUR_207_BM623_RSH_OPT
|  |  |  | 85140714103 | SUR_207_BM625_RSH_OPT
|  |  |  | 85140715103 | SUR_207_BM835_RSH_OPT
|  |  |  | 85138697103 | SUR_208_BM106_OPT
|  |  |  | 85138698103 | SUR_329_BM141_OPT
|  |  |  | 85138699103 | SUR_329_BM393_OPT
|  |  |  | 85138700103 | SUR_329_BM501_OPT
|  |  |  | 85138701103 | SUR_329_BM767_OPT
|  |  |  | 85138702103 | SUR_329_BM768_OPT
|  |  |  | 85140716103 | SUR_330_BM080_RSH_OPT
|  |  |  | 85137747103 | SUR_330_BM081_RSH_OPT
|  |  |  | 85137748103 | SUR_330_BM360_RSH_OPT
|  |  |  | 85137749103 | SUR_330_BM380_RSH_OPT
|  |  |  | 85137750103 | SUR_330_BM415_RSH_OPT
|  |  |  | 85137751103 | SUR_330_BM462_RSH_OPT
|  |  |  | 85140717103 | SUR_330_BM715_RSH_OPT
|  |  |  | 85140718103 | SUR_330_BM732_RSH_OPT
|  |  |  | 85140719103 | SUR_330_BM811_RSH_OPT
|  |  |  | 85140720103 | SUR_330_BM831_RSH_OPT
|  |  |  | 85140721103 | SUR_330_BM840_RSH_OPT
|  |  |  | 85113719103 | SUR_501_JS014_RSH_OPT
|  |  |  | 85113720103 | SUR_501_JS051_RSH_OPT
|  |  |  | 85113721103 | SUR_501_JS052_RSH_OPT
|  |  |  | 85138703103 | SUR_514_MO002_OPT
|  |  |  | 85138704103 | SUR_514_MS011_OPT
|  |  |  | 85138705103 | SUR_514_MS019_OPT
|  |  |  | 85138706103 | SUR_514_MS023_OPT
|  |  |  | 85132707103 | SUR_514_MS028_OPT
|  |  |  | 85132708103 | SUR_514_MS030_OPT
|  |  |  | 85132709103 | SUR_514_MS032_OPT
|  |  |  | 85132710103 | SUR_514_MS035_OPT
|  |  |  | 85132711103 | SUR_514_MS038_OPT
|  |  |  | 85117698103 | SUR_514_MS041_OPT
|  |  |  | 85117699103 | SUR_514_MS042_OPT
|  |  |  | 85117700103 | SUR_514_MS044_OPT
|  |  |  | 85117701103 | SUR_514_MS062_OPT
|  |  |  | 85117702103 | SUR_514_MS063_OPT
|  |  |  | 85117703103 | SUR_514_MS122_OPT
|  |  |  | 85117704103 | SUR_515_MS001_OPT
|  |  |  | 85117705103 | SUR_515_MS005_OPT
|  |  |  | 85117706103 | SUR_515_MS006_OPT
|  |  |  | 85117707103 | SUR_515_MS009_OPT
|  |  |  | 85132712103 | SUR_515_MS017_OPT
|  |  |  | 85132713103 | SUR_515_MS054_OPT
|  |  |  | 85132714103 | SUR_515_MS059_OPT
|  |  |  | 85132715103 | SUR_515_MS061_OPT
|  |  |  | 85132716103 | SUR_515_MS066_OPT
|  |  |  | 85137702103 | SUR_515_MS067_OPT
|  |  |  | 85137703103 | SUR_515_MSM24_OPT
|  |  |  | 86830788103 | SUR_516_MN006_RSH_OPT
|  |  |  | 86830749103 | SUR_516_MN022_RSH_OPT
|  |  |  | 86830748103 | SUR_516_MN054_RSH_OPT
|  |  |  | 86830801103 | SUR_516_MN091_RSH_OPT
|  |  |  | 86830750103 | SUR_516_MN149_RSH_OPT
|  |  |  | 86830743103 | SUR_516_MN220_RSH_OPT
|  |  |  | 86830769103 | SUR_516_MN338_RSH_OPT
|  |  |  | 86830802103 | SUR_516_MO065_RSH_OPT
|  |  |  | 87409710103 | SUR_519_A33-O006_RSH_OPT
|  |  |  | 87409708103 | SUR_519_A33-O058_RSH_OPT
|  |  |  | 87409707103 | SUR_519_A33-O059_RSH_OPT
|  |  |  | 87409709103 | SUR_519_A33-O111_RSH_OPT
|  |  |  | 87409706103 | SUR_519_A33-O112_RSH_OPT
|  |  |  | 87409705103 | SUR_519_A33-O143_RSH_OPT
|  |  |  | 87409704103 | SUR_519_A33-O177_RSH_OPT
|  |  |  | 87409703103 | SUR_519_A33-O195_RSH_OPT
|  |  |  | 87409702103 | SUR_519_A33-O384_RSH_OPT
|  |  |  | 87409701103 | SUR_519_A33-O389_RSH_OPT
|  |  |  | 87409700103 | SUR_519_A33-O737_RSH_OPT
|  |  |  | 87393702103 | SUR_519_MC024_RSH_OPT
|  |  |  | 87393701103 | SUR_519_MC028_RSH_OPT
|  |  |  | 87393700103 | SUR_519_MC037_RSH_OPT
|  |  |  | 87393705103 | SUR_519_MC054_RSH_OPT
|  |  |  | 87393699103 | SUR_519_MC077_RSH_OPT
|  |  |  | 87393697103 | SUR_519_MC126_RSH_OPT
|  |  |  | 87393703103 | SUR_519_MC301_RSH_OPT
|  |  |  | 87393698103 | SUR_519_MC303_RSH_OPT
|  |  |  | 87393704103 | SUR_519_MC345_RSH_OPT
|  |  |  | 85137722103 | SUR_521_MC002_RSH_OPT
|  |  |  | 85137723103 | SUR_521_MC005_RSH_OPT
|  |  |  | 85137724103 | SUR_521_MC025_RSH_OPT
|  |  |  | 85137725103 | SUR_521_MC066_RSH_OPT
|  |  |  | 85137726103 | SUR_521_MC098_RSH_OPT
|  |  |  | 85117718103 | SUR_521_MC147_RSH_OPT
|  |  |  | 85117719103 | SUR_521_MC171_RSH_OPT
|  |  |  | 85117720103 | SUR_521_MC333_RSH_OPT
|  |  |  | 85117721103 | SUR_521_MC350_RSH_OPT
|  |  |  | 85117722103 | SUR_523_MC035_OPT
|  |  |  | 85116706103 | SUR_523_MC041_OPT
|  |  |  | 85116707103 | SUR_523_MC080_OPT
|  |  |  | 85116708103 | SUR_523_MC091_OPT
|  |  |  | 85116709103 | SUR_523_MC093_OPT
|  |  |  | 85116710103 | SUR_523_MC094_OPT
|  |  |  | 85135722103 | SUR_523_MC300_OPT
|  |  |  | 85135723103 | SUR_523_MC401_OPT
|  |  |  | 85135724103 | SUR_523_MC403_OPT
|  |  |  | 85135725103 | SUR_523_MC409_OPT
|  |  |  | 85135726103 | SUR_524_MC310_RSH_OPT
|  |  |  | 85132737103 | SUR_524_MC405_RSH_OPT
|  |  |  | 85132738103 | SUR_524_MN071_RSH_OPT
|  |  |  | 85132739103 | SUR_524_MN086_RSH_OPT
|  |  |  | 85132740103 | SUR_524_MN099_RSH_OPT
|  |  |  | 85132741103 | SUR_524_MN113_RSH_OPT
|  |  |  | 87409714103 | SUR_529_A32-O092_RSH_OPT
|  |  |  | 87409712103 | SUR_529_A32-O094_RSH_OPT
|  |  |  | 87409713103 | SUR_529_A32-O101_RSH_OPT
|  |  |  | 87409717103 | SUR_529_A32-O148_RSH_OPT
|  |  |  | 87409716103 | SUR_529_A32-O403_RSH_OPT
|  |  |  | 87409715103 | SUR_529_A32-O425_RSH_OPT
|  |  |  | 87394697103 | SUR_529_MS010_RSH_OPT
|  |  |  | 87365702103 | SUR_529_MS012_RSH_OPT
|  |  |  | 87365713103 | SUR_529_MS015_RSH_OPT
|  |  |  | 87365712103 | SUR_529_MS020_RSH_OPT
|  |  |  | 87365711103 | SUR_529_MS025_RSH_OPT
|  |  |  | 87365710103 | SUR_529_MS033_RSH_OPT
|  |  |  | 87365709103 | SUR_529_MS034_RSH_OPT
|  |  |  | 87365708103 | SUR_529_MS036_RSH_OPT
|  |  |  | 87365707103 | SUR_529_MS051_RSH_OPT
|  |  |  | 87365705103 | SUR_529_MS053_RSH_OPT
|  |  |  | 87365704103 | SUR_529_MS109_RSH_OPT
|  |  |  | 87365703103 | SUR_529_MS304_RSH_OPT
|  |  |  | 87365706103 | SUR_529_MS322_RSH_OPT
|  |  |  | 85137704103 | SUR_531_JS002_OPT
|  |  |  | 85137705103 | SUR_531_JS012_OPT
|  |  |  | 85137706103 | SUR_531_JS015_OPT
|  |  |  | 85132717103 | SUR_531_JS017_OPT
|  |  |  | 85132718103 | SUR_531_JS026_OPT
|  |  |  | 85132719103 | SUR_531_JS027_OPT
|  |  |  | 85132720103 | SUR_531_JS028_OPT
|  |  |  | 85132721103 | SUR_531_JS033_OPT
|  |  |  | 85137707103 | SUR_531_JS037_OPT
|  |  |  | 85137708103 | SUR_531_JS039_OPT
|  |  |  | 85137709103 | SUR_531_JS040_OPT
|  |  |  | 85137710103 | SUR_531_JS045_OPT
|  |  |  | 85137711103 | SUR_531_JS101_OPT
|  |  |  | 85136722103 | SUR_533_MC015_RSH_OPT
|  |  |  | 85136723103 | SUR_533_MC016_RSH_OPT
|  |  |  | 85136724103 | SUR_533_MC072_RSH_OPT
|  |  |  | 85136725103 | SUR_533_MC092_RSH_OPT
|  |  |  | 85136726103 | SUR_533_MC315_RSH_OPT
|  |  |  | 85116711103 | SUR_533_MC322_RSH_OPT
|  |  |  | 87409711103 | SUR_534_A33-O061_RSH_OPT
|  |  |  | 87365700103 | SUR_534_MC036_RSH_OPT
|  |  |  | 87365701103 | SUR_534_MC065_RSH_OPT
|  |  |  | 87365699103 | SUR_534_MC076_RSH_OPT
|  |  |  | 87393706103 | SUR_534_MC318_RSH_OPT
|  |  |  | 84981698103 | SUR_B772M_Opt
|  |  |  | 84981697103 | SUR_B985M_Opt
|  |  |  | 84981703103 | SUR_BM103_Opt
|  |  |  | 84981699103 | SUR_BM392_Opt
|  |  |  | 84981702103 | SUR_BM640_Opt
|  |  |  | 84981704103 | SUR_BM642_Opt
|  |  |  | 84981701103 | SUR_BM643_Opt
|  |  |  | 84981700103 | SUR_BM778_Opt
|  |  |  | 94102702103 | A38-B323_A38-B323_RSH_OPT_5G
|  |  |  | 90431715103 | AMBA_100_CS011_RSH_OPT
|  |  |  | 90834724103 | AMBA_100_CS011_RSH_OPT_5G
|  |  |  | 90431714103 | AMBA_100_CS188_RSH_OPT
|  |  |  | 90834714103 | AMBA_100_CS188_RSH_OPT_5G
|  |  |  | 90431713103 | AMBA_100_CS263_RSH_OPT
|  |  |  | 90834710103 | AMBA_100_CS263_RSH_OPT_5G
|  |  |  | 90431712103 | AMBA_100_CS296_RSH_OPT
|  |  |  | 90834707103 | AMBA_100_CS296_RSH_OPT_5G
|  |  |  | 93849714103 | AMBA_101_KS131_RSH_OPT_4G
|  |  |  | 90431764103 | AMBA_101_KS195_RSH_OPT
|  |  |  | 93849713103 | AMBA_101_KS280_RSH_OPT_4G
|  |  |  | 93868704103 | AMBA_104_BS060_RSH_OPT_4G
|  |  |  | 90607738103 | AMBA_104_BS107_RSH_OPT
|  |  |  | 93868705103 | AMBA_104_BS107_RSH_OPT_4G
|  |  |  | 93868702103 | AMBA_104_BS162_RSH_OPT_4G
|  |  |  | 93868701103 | AMBA_104_BS219_RSH_OPT_4G
|  |  |  | 90607737103 | AMBA_104_BS308_RSH_OPT
|  |  |  | 93868703103 | AMBA_104_BS390_RSH_OPT_4G
|  |  |  | 93868700103 | AMBA_104_KS221_RSH_OPT_4G
|  |  |  | 90431781103 | AMBA_110_KO215_RSH_OPT
|  |  |  | 90431758103 | AMBA_111_KO055_RSH_OPT
|  |  |  | 90431763103 | AMBA_111_KO207_RSH_OPT
|  |  |  | 90431761103 | AMBA_115_KN214_RSH_OPT
|  |  |  | 90431769103 | AMBA_116_KN269_RSH_OPT
|  |  |  | 90431762103 | AMBA_116_KO050_RSH_OPT
|  |  |  | 90431728103 | AMBA_118_CN262_RSH_OPT
|  |  |  | 90834738103 | AMBA_118_CN262_RSH_OPT_5G
|  |  |  | 90431727103 | AMBA_118_CN264_RSH_OPT
|  |  |  | 90834737103 | AMBA_118_CN264_RSH_OPT_5G
|  |  |  | 90431726103 | AMBA_118_CN301_RSH_OPT
|  |  |  | 90834733103 | AMBA_118_CN301_RSH_OPT_5G
|  |  |  | 90431725103 | AMBA_118_CN313_RSH_OPT
|  |  |  | 90834732103 | AMBA_118_CN313_RSH_OPT_5G
|  |  |  | 90607736103 | AMBA_125_KN114_RSH_OPT
|  |  |  | 90431759103 | AMBA_126_KN118_RSH_OPT
|  |  |  | 90431799103 | AMBA_127_KN087_RSH_OPT
|  |  |  | 90431804103 | AMBA_129_CN194_RSH_OPT
|  |  |  | 90431792103 | AMBA_129_CN210_RSH_OPT
|  |  |  | 90431732103 | AMBA_129_CN482_RSH_OPT
|  |  |  | 90834727103 | AMBA_129_CN482_RSH_OPT_5G
|  |  |  | 90431731103 | AMBA_129_CN483_RSH_OPT
|  |  |  | 90834726103 | AMBA_129_CN483_RSH_OPT_5G
|  |  |  | 90431790103 | AMBA_136_CN142_RSH_OPT
|  |  |  | 93827702103 | AMBA_137_CN445_RSH_OPT_4G
|  |  |  | 93827701103 | AMBA_137_CN446_RSH_OPT_4G
|  |  |  | 93849711103 | AMBA_137_CN446_RSH_OPT_5G
|  |  |  | 90431789103 | AMBA_137_CS073_RSH_OPT
|  |  |  | 93827700103 | AMBA_137_CS222_RSH_OPT_4G
|  |  |  | 93849710103 | AMBA_137_CS222_RSH_OPT_5G
|  |  |  | 93827699103 | AMBA_137_CS231_RSH_OPT_4G
|  |  |  | 90431788103 | AMBA_138_CN027_RSH_OPT_4G
|  |  |  | 90607735103 | AMBA_139_CN476_RSH_OPT
|  |  |  | 90431787103 | AMBA_140_CS276_RSH_OPT_5G
|  |  |  | 90431786103 | AMBA_144_CN252_RSH_OPT
|  |  |  | 90431730103 | AMBA_144_CN357_RSH_OPT
|  |  |  | 90834730103 | AMBA_144_CN357_RSH_OPT_5G
|  |  |  | 90431729103 | AMBA_144_CN467_RSH_OPT
|  |  |  | 90834728103 | AMBA_144_CN467_RSH_OPT_5G
|  |  |  | 90431803103 | AMBA_146_CN172_RSH_OPT
|  |  |  | 90431724103 | AMBA_146_CN234_RSH_OPT
|  |  |  | 90834739103 | AMBA_146_CN234_RSH_OPT_5G
|  |  |  | 90431785103 | AMBA_146_CN236_RSH_OPT
|  |  |  | 90431723103 | AMBA_146_CN300_RSH_OPT
|  |  |  | 90834734103 | AMBA_146_CN300_RSH_OPT_5G
|  |  |  | 90431722103 | AMBA_147_CN012_RSH_OPT
|  |  |  | 90834744103 | AMBA_147_CN012_RSH_OPT_5G
|  |  |  | 90431721103 | AMBA_147_CN296_RSH_OPT
|  |  |  | 90834736103 | AMBA_147_CN296_RSH_OPT_5G
|  |  |  | 90431720103 | AMBA_147_CN299_RSH_OPT
|  |  |  | 90834735103 | AMBA_147_CN299_RSH_OPT_5G
|  |  |  | 90431784103 | AMBA_147_CN810_RSH_OPT
|  |  |  | 90431802103 | AMBA_149_CN347_RSH_OPT_5G
|  |  |  | 90431719103 | AMBA_150_CN186_RSH_OPT
|  |  |  | 90834742103 | AMBA_150_CN186_RSH_OPT_5G
|  |  |  | 90431718103 | AMBA_150_CN227_RSH_OPT
|  |  |  | 90834740103 | AMBA_150_CN227_RSH_OPT_5G
|  |  |  | 90431717103 | AMBA_150_CN348_RSH_OPT
|  |  |  | 90834731103 | AMBA_150_CN348_RSH_OPT_5G
|  |  |  | 90431716103 | AMBA_150_CN378_RSH_OPT
|  |  |  | 90834729103 | AMBA_150_CN378_RSH_OPT_5G
|  |  |  | 90431783103 | AMBA_151_CN405_RSH_OPT_4G
|  |  |  | 89781728103 | AMBA_153_CN037_RSH_OPT
|  |  |  | 90607734103 | AMBA_153_CN202_RSH_OPT
|  |  |  | 90431806103 | AMBA_153_CN232_RSH_OPT
|  |  |  | 90607733103 | AMBA_153_CN233_RSH_OPT
|  |  |  | 90431808103 | AMBA_153_CN240_RSH_OPT
|  |  |  | 89781727103 | AMBA_153_CN324_RSH_OPT
|  |  |  | 89781729103 | AMBA_153_CN325_RSH_OPT
|  |  |  | 89781719103 | AMBA_153_CN425_RSH_OPT
|  |  |  | 89781721103 | AMBA_153_CN453_RSH_OPT
|  |  |  | 90607732103 | AMBA_154_CN206_RSH_OPT
|  |  |  | 90431807103 | AMBA_154_CN248_RSH_OPT
|  |  |  | 89781722103 | AMBA_154_CN294_RSH_OPT
|  |  |  | 89781726103 | AMBA_154_CN311_RSH_OPT
|  |  |  | 89781725103 | AMBA_154_CN409_RSH_OPT
|  |  |  | 89781724103 | AMBA_157_CN046_RSH_OPT
|  |  |  | 89781730103 | AMBA_157_CN250_RSH_OPT
|  |  |  | 90607731103 | AMBA_157_CN275_RSH_OPT
|  |  |  | 89781720103 | AMBA_157_CN293_RSH_OPT
|  |  |  | 89781723103 | AMBA_158_CN216_RSH_OPT
|  |  |  | 90607729103 | AMBA_158_CN372_RSH_OPT
|  |  |  | 90607730103 | AMBA_158_CN491_RSH_OPT
|  |  |  | 90431740103 | AMBA_164_CS001_RSH_OPT
|  |  |  | 90834725103 | AMBA_164_CS001_RSH_OPT_5G
|  |  |  | 90431798103 | AMBA_164_CS003_RSH_OPT
|  |  |  | 90431739103 | AMBA_164_CS167_RSH_OPT
|  |  |  | 90834717103 | AMBA_164_CS167_RSH_OPT_5G
|  |  |  | 90431738103 | AMBA_164_CS203_RSH_OPT
|  |  |  | 90834713103 | AMBA_164_CS203_RSH_OPT_5G
|  |  |  | 90431737103 | AMBA_164_CS221_RSH_OPT
|  |  |  | 90834711103 | AMBA_164_CS221_RSH_OPT_5G
|  |  |  | 90431746103 | AMBA_165_CM034_RSH_OPT
|  |  |  | 90834745103 | AMBA_165_CM034_RSH_OPT_5G
|  |  |  | 90431745103 | AMBA_165_CN034_RSH_OPT
|  |  |  | 90834743103 | AMBA_165_CN034_RSH_OPT_5G
|  |  |  | 90431744103 | AMBA_165_CN205_RSH_OPT
|  |  |  | 90834741103 | AMBA_165_CN205_RSH_OPT_5G
|  |  |  | 90431751103 | AMBA_167_CS331_RSH_OPT
|  |  |  | 90834704103 | AMBA_167_CS331_RSH_OPT_5G
|  |  |  | 90431750103 | AMBA_167_CS334_RSH_OPT
|  |  |  | 90834703103 | AMBA_167_CS334_RSH_OPT_5G
|  |  |  | 90431749103 | AMBA_167_CS337_RSH_OPT
|  |  |  | 90834702103 | AMBA_167_CS337_RSH_OPT_5G
|  |  |  | 90431748103 | AMBA_167_CS508_RSH_OPT
|  |  |  | 90834699103 | AMBA_167_CS508_RSH_OPT_5G
|  |  |  | 90431747103 | AMBA_167_CU045_RSH_OPT
|  |  |  | 90834698103 | AMBA_167_CU045_RSH_OPT_5G
|  |  |  | 90431809103 | AMBA_168_CM005_RSH_OPT
|  |  |  | 90607728103 | AMBA_168_CU076_RSH_OPT
|  |  |  | 89781718103 | AMBA_168_CU081_RSH_OPT
|  |  |  | 90834722103 | AMBA_170_CS097_RSH_OPT_5G
|  |  |  | 90834712103 | AMBA_170_CS210_RSH_OPT_5G
|  |  |  | 90607726103 | AMBA_171_CS002_RSH_OPT
|  |  |  | 90607725103 | AMBA_171_CS029_RSH_OPT
|  |  |  | 89781714103 | AMBA_171_CS127_RSH_OPT
|  |  |  | 89781717103 | AMBA_171_CS133_RSH_OPT
|  |  |  | 90431805103 | AMBA_171_CS136_RSH_OPT
|  |  |  | 90431755103 | AMBA_171_CS219_RSH_OPT
|  |  |  | 90431801103 | AMBA_171_CS272_RSH_OPT
|  |  |  | 90607727103 | AMBA_171_CS339_RSH_OPT
|  |  |  | 90431736103 | AMBA_172_CS160_RSH_OPT
|  |  |  | 90834718103 | AMBA_172_CS160_RSH_OPT_5G
|  |  |  | 90431735103 | AMBA_172_CS187_RSH_OPT
|  |  |  | 90834715103 | AMBA_172_CS187_RSH_OPT_5G
|  |  |  | 90431734103 | AMBA_172_CS294_RSH_OPT
|  |  |  | 90834708103 | AMBA_172_CS294_RSH_OPT_5G
|  |  |  | 90431733103 | AMBA_172_CS352_RSH_OPT
|  |  |  | 90834701103 | AMBA_172_CS352_RSH_OPT_5G
|  |  |  | 90431743103 | AMBA_173_CS168_RSH_OPT
|  |  |  | 90834716103 | AMBA_173_CS168_RSH_OPT_5G
|  |  |  | 90431742103 | AMBA_173_CS273_RSH_OPT
|  |  |  | 90834709103 | AMBA_173_CS273_RSH_OPT_5G
|  |  |  | 90431741103 | AMBA_173_CS306_RSH_OPT
|  |  |  | 90834706103 | AMBA_173_CS306_RSH_OPT_5G
|  |  |  | 90607721103 | AMBA_178_CS105_RSH_OPT
|  |  |  | 93827705103 | AMBA_178_CS105_RSH_OPT_4G
|  |  |  | 90431791103 | AMBA_178_CS170_RSH_OPT
|  |  |  | 90607722103 | AMBA_178_CS175_RSH_OPT
|  |  |  | 93827706103 | AMBA_178_CS175_RSH_OPT_4G
|  |  |  | 90607723103 | AMBA_178_CS190_RSH_OPT
|  |  |  | 93827704103 | AMBA_178_CS190_RSH_OPT_4G
|  |  |  | 90607724103 | AMBA_178_CS293_RSH_OPT
|  |  |  | 93827703103 | AMBA_178_CS293_RSH_OPT_4G
|  |  |  | 90431797103 | AMBA_178_CS347_RSH_OPT
|  |  |  | 93827707103 | AMBA_178_CS347_RSH_OPT_4G
|  |  |  | 90431752103 | AMBA_179_KS154_RSH_OPT
|  |  |  | 90431772103 | AMBA_179_KS174_RSH_OPT
|  |  |  | 90431767103 | AMBA_179_KS464_RSH_OPT
|  |  |  | 90431770103 | AMBA_181_BS144_RSH_OPT
|  |  |  | 90607720103 | AMBA_183_KS326_RSH_OPT
|  |  |  | 90607718103 | AMBA_187_KS188_RSH_OPT
|  |  |  | 90431754103 | AMBA_187_KS189_RSH_OPT
|  |  |  | 90607719103 | AMBA_187_KS293_RSH_OPT
|  |  |  | 90607717103 | AMBA_188_BS097_RSH_OPT
|  |  |  | 90607714103 | AMBA_190_BS096_RSH_OPT
|  |  |  | 90607715103 | AMBA_190_KS185_RSH_OPT
|  |  |  | 90431778103 | AMBA_190_KS203_RSH_OPT
|  |  |  | 90607716103 | AMBA_190_KS310_RSH_OPT
|  |  |  | 90607713103 | AMBA_194_BS102_RSH_OPT
|  |  |  | 90431777103 | AMBA_194_BS176_RSH_OPT
|  |  |  | 90431774103 | AMBA_194_BS372_RSH_OPT
|  |  |  | 90607710103 | AMBA_195_KS119_RSH_OPT
|  |  |  | 90607711103 | AMBA_195_KS302_RSH_OPT
|  |  |  | 90607708103 | AMBA_195_KS378_RSH_OPT
|  |  |  | 90607712103 | AMBA_195_KS436_RSH_OPT
|  |  |  | 90607709103 | AMBA_195_KS702_RSH_OPT
|  |  |  | 90607705103 | AMBA_196_KS111_RSH_OPT
|  |  |  | 90431796103 | AMBA_196_KS184_RSH_OPT
|  |  |  | 90607706103 | AMBA_196_KS325_RSH_OPT
|  |  |  | 90607707103 | AMBA_196_KS607_RSH_OPT
|  |  |  | 90431756103 | AMBA_198_BS081_RSH_OPT
|  |  |  | 90431810103 | AMBA_199_BS069_RSH_OPT
|  |  |  | 90431800103 | AMBA_199_BS093_RSH_OPT
|  |  |  | 89781716103 | AMBA_199_BS094_RSH_OPT
|  |  |  | 90607704103 | AMBA_199_BS098_RSH_OPT
|  |  |  | 90607703103 | AMBA_199_BS174_RSH_OPT
|  |  |  | 90607702103 | AMBA_199_BS194_RSH_OPT
|  |  |  | 90431780103 | AMBA_199_BS195_RSH_OPT
|  |  |  | 91246709103 | AMBA_200_LP029_RSH_OPT_5G
|  |  |  | 91246714103 | AMBA_203_LC007_RSH_OPT_5G
|  |  |  | 91246715103 | AMBA_203_LC059_RSH_OPT_5G
|  |  |  | 91247700103 | AMBA_204_LC044_RSH_OPT_5G
|  |  |  | 91246713103 | AMBA_205_LC001_RSH_OPT_5G
|  |  |  | 91247699103 | AMBA_207_LC040_RSH_OPT_5G
|  |  |  | 91243757103 | AMBA_211_LC008_RSH_OPT_5G
|  |  |  | 91243758103 | AMBA_211_LC029_RSH_OPT_5G
|  |  |  | 91243759103 | AMBA_211_LC035_RSH_OPT_5G
|  |  |  | 91243760103 | AMBA_211_LC054_RSH_OPT_5G
|  |  |  | 91243761103 | AMBA_211_LP086_RSH_OPT_5G
|  |  |  | 90607701103 | AMBA_213_BO950_RSH_OPT
|  |  |  | 90607700103 | AMBA_217_LP112_RSH_OPT
|  |  |  | 89781732103 | AMBA_219_BN156_RSH_OPT
|  |  |  | 89781733103 | AMBA_220_BN511_RSH_OPT
|  |  |  | 90607698103 | AMBA_227_KS192_RSH_OPT
|  |  |  | 90607699103 | AMBA_227_KS286_RSH_OPT
|  |  |  | 91246697103 | AMBA_228_KS461_RSH_OPT_5G
|  |  |  | 91246710103 | AMBA_239_LP015_RSH_OPT_5G
|  |  |  | 91246711103 | AMBA_239_LP111_RSH_OPT_5G
|  |  |  | 90606715103 | AMBA_256_BS043_RSH_OPT
|  |  |  | 93868731103 | AMBA_256_BS128_RSH_OPT_4G
|  |  |  | 90606716103 | AMBA_256_BS129_RSH_OPT
|  |  |  | 93868730103 | AMBA_256_BS129_RSH_OPT_4G
|  |  |  | 90607697103 | AMBA_256_BS130_RSH_OPT
|  |  |  | 93868732103 | AMBA_256_BS130_RSH_OPT_4G
|  |  |  | 93868726103 | AMBA_256_BS205_RSH_OPT_4G
|  |  |  | 93868729103 | AMBA_256_BS206_RSH_OPT_4G
|  |  |  | 93868728103 | AMBA_256_BS207_RSH_OPT_4G
|  |  |  | 93868727103 | AMBA_256_BS260_RSH_OPT_4G
|  |  |  | 89781731103 | AMBA_40_BN287_RSH_OPT
|  |  |  | 90606714103 | AMBA_41_BN458_RSH_OPT
|  |  |  | 91246698103 | AMBA_55_BN127_RSH_OPT_5G
|  |  |  | 93827708103 | AMBA_56_NPU351_RSH_OPT
|  |  |  | 90606713103 | AMBA_58_KO032_RSH_OPT
|  |  |  | 93849712103 | AMBA_64_KN045_RSH_OPT_4G
|  |  |  | 93849698103 | AMBA_64_KN045_RSH_OPT_5G
|  |  |  | 90606712103 | AMBA_78_KO197_RSH_OPT
|  |  |  | 93868719103 | AMBA_80_BS052_RSH_OPT_4G
|  |  |  | 93849700103 | AMBA_80_BS052_RSH_OPT_5G
|  |  |  | 93868716103 | AMBA_80_BS071_RSH_OPT_4G
|  |  |  | 90431773103 | AMBA_80_BS213_RSH_OPT
|  |  |  | 90606710103 | AMBA_80_BS253_RSH_OPT
|  |  |  | 93868718103 | AMBA_80_BS253_RSH_OPT_4G
|  |  |  | 90431760103 | AMBA_80_BS287_RSH_OPT
|  |  |  | 93868715103 | AMBA_80_BS293_RSH_OPT_4G
|  |  |  | 90606711103 | AMBA_80_BS294_RSH_OPT
|  |  |  | 93868717103 | AMBA_80_BS294_RSH_OPT_4G
|  |  |  | 93868714103 | AMBA_80_BS297_RSH_OPT_4G
|  |  |  | 90431795103 | AMBA_82_BS090_RSH_OPT
|  |  |  | 93868721103 | AMBA_82_BS116_RSH_OPT_4G
|  |  |  | 90606707103 | AMBA_82_BS117_RSH_OPT
|  |  |  | 93868725103 | AMBA_82_BS117_RSH_OPT_4G
|  |  |  | 90431794103 | AMBA_82_BS158_RSH_OPT
|  |  |  | 90431793103 | AMBA_82_BS159_RSH_OPT
|  |  |  | 93868724103 | AMBA_82_BS208_RSH_OPT_4G
|  |  |  | 90606708103 | AMBA_82_BS254_RSH_OPT
|  |  |  | 93868720103 | AMBA_82_BS254_RSH_OPT_4G
|  |  |  | 94101707103 | AMBA_82_BS257_RSH_OPT_4G
|  |  |  | 94101697103 | AMBA_82_BS257_RSH_OPT_5G
|  |  |  | 90606709103 | AMBA_82_BS289_RSH_OPT
|  |  |  | 93868723103 | AMBA_82_BS289_RSH_OPT_4G
|  |  |  | 93868722103 | AMBA_82_BS291_RSH_OPT_4G
|  |  |  | 93868712103 | AMBA_83_BS077_RSH_OPT_4G
|  |  |  | 90606706103 | AMBA_83_BS110_RSH_OPT
|  |  |  | 93868713103 | AMBA_83_BS110_RSH_OPT_4G
|  |  |  | 93868711103 | AMBA_83_BS235_RSH_OPT_4G
|  |  |  | 93868710103 | AMBA_83_BS239_RSH_OPT_4G
|  |  |  | 93868709103 | AMBA_83_BS249_RSH_OPT_4G
|  |  |  | 93868706103 | AMBA_83_BS251_RSH_OPT_4G
|  |  |  | 88561710103 | AMBA_83_BS304_RSH_OPT
|  |  |  | 93868708103 | AMBA_83_BS306_RSH_OPT_4G
|  |  |  | 93868707103 | AMBA_83_BS307_RSH_OPT_4G
|  |  |  | 93868743103 | AMBA_84_CS107_RSH_OPT_4G
|  |  |  | 93868742103 | AMBA_84_CS149_RSH_OPT_4G
|  |  |  | 93868741103 | AMBA_84_CS152_RSH_OPT_4G
|  |  |  | 93868740103 | AMBA_84_CS153_RSH_OPT_4G
|  |  |  | 93868739103 | AMBA_84_CS241_RSH_OPT_4G
|  |  |  | 93849704103 | AMBA_84_CS241_RSH_OPT_5G
|  |  |  | 95580697103 | AMBA_84_CS309_RSH_OPT
|  |  |  | 93868738103 | AMBA_84_CS311_RSH_OPT_4G
|  |  |  | 93849703103 | AMBA_84_CS311_RSH_OPT_5G
|  |  |  | 93868737103 | AMBA_84_CS312_RSH_OPT_4G
|  |  |  | 93868736103 | AMBA_84_CS313_RSH_OPT_4G
|  |  |  | 90431775103 | AMBA_86_KO037_RSH_OPT
|  |  |  | 90431771103 | AMBA_86_KO044_RSH_OPT
|  |  |  | 90431776103 | AMBA_86_KO193_RSH_OPT
|  |  |  | 90431768103 | AMBA_86_KS472_RSH_OPT
|  |  |  | 93827698103 | AMBA_88_CS147_RSH_OPT_4G
|  |  |  | 93849709103 | AMBA_88_CS147_RSH_OPT_5G
|  |  |  | 93868751103 | AMBA_88_CS148_RSH_OPT_4G
|  |  |  | 93849708103 | AMBA_88_CS148_RSH_OPT_5G
|  |  |  | 93868750103 | AMBA_88_CS230_RSH_OPT_4G
|  |  |  | 93868749103 | AMBA_88_CS287_RSH_OPT_4G
|  |  |  | 93868748103 | AMBA_89_CN449_RSH_OPT_4G
|  |  |  | 93868747103 | AMBA_89_CS154_RSH_OPT_4G
|  |  |  | 93868746103 | AMBA_89_CS158_RSH_OPT_4G
|  |  |  | 93849707103 | AMBA_89_CS158_RSH_OPT_5G
|  |  |  | 93868745103 | AMBA_89_CS200_RSH_OPT_4G
|  |  |  | 93849706103 | AMBA_89_CS200_RSH_OPT_5G
|  |  |  | 93868744103 | AMBA_89_CS286_RSH_OPT_4G
|  |  |  | 93849705103 | AMBA_89_CS286_RSH_OPT_5G
|  |  |  | 90606705103 | AMBA_90_KS116_RSH_OPT
|  |  |  | 90431765103 | AMBA_90_KS200_RSH_OPT
|  |  |  | 90431779103 | AMBA_90_KS300_RSH_OPT
|  |  |  | 90431757103 | AMBA_91_BS134_RSH_OPT
|  |  |  | 90431766103 | AMBA_91_KS334_RSH_OPT
|  |  |  | 90431753103 | AMBA_92_BS196_RSH_OPT
|  |  |  | 93849721103 | AMBA_93_KS159_RSH_OPT_4G
|  |  |  | 93849699103 | AMBA_93_KS159_RSH_OPT_5G
|  |  |  | 93868697103 | AMBA_93_KS202_RSH_OPT_4G
|  |  |  | 93849722103 | AMBA_93_KS343_RSH_OPT_4G
|  |  |  | 93868698103 | AMBA_93_KS425_RSH_OPT_4G
|  |  |  | 93868699103 | AMBA_94_BS234_RSH_OPT_4G
|  |  |  | 93849719103 | AMBA_95_KS127_RSH_OPT_4G
|  |  |  | 93849720103 | AMBA_95_KS134_RSH_OPT_4G
|  |  |  | 93849718103 | AMBA_95_KS149_RSH_OPT_4G
|  |  |  | 93849715103 | AMBA_95_KS204_RSH_OPT_4G
|  |  |  | 93849717103 | AMBA_95_KS276_RSH_OPT_4G
|  |  |  | 93849716103 | AMBA_95_KS428_RSH_OPT_4G
|  |  |  | 90431782103 | AMBA_97_CS033_RSH_OPT
|  |  |  | 93868734103 | AMBA_97_CS151_RSH_OPT_4G
|  |  |  | 93868733103 | AMBA_97_CS198_RSH_OPT_4G
|  |  |  | 93849701103 | AMBA_97_CS198_RSH_OPT_5G
|  |  |  | 93868735103 | AMBA_97_KS018_RSH_OPT_4G
|  |  |  | 93849702103 | AMBA_97_KS018_RSH_OPT_5G
|  |  |  | 90431711103 | AMBA_98_CS014_RSH_OPT
|  |  |  | 90834723103 | AMBA_98_CS014_RSH_OPT_5G
|  |  |  | 90431710103 | AMBA_98_CS120_RSH_OPT
|  |  |  | 90834721103 | AMBA_98_CS120_RSH_OPT_5G
|  |  |  | 90431709103 | AMBA_98_CS143_RSH_OPT
|  |  |  | 90834720103 | AMBA_98_CS143_RSH_OPT_5G
|  |  |  | 90431708103 | AMBA_98_CS146_RSH_OPT
|  |  |  | 90834719103 | AMBA_98_CS146_RSH_OPT_5G
|  |  |  | 90431707103 | AMBA_98_CS330_RSH_OPT
|  |  |  | 90834705103 | AMBA_98_CS330_RSH_OPT_5G
|  |  |  | 90431706103 | AMBA_98_CS355_RSH_OPT
|  |  |  | 90834700103 | AMBA_98_CS355_RSH_OPT_5G
|  |  |  | 98691700103 | AMBA_A42-A051_Mod_TA
|  |  |  | 98691699103 | AMBA_A42-B169_Mod_TA
|  |  |  | 98691698103 | AMBA_A42-B777_Mod_TA
|  |  |  | 98691697103 | AMBA_A42-B908_Mod_TA
|  |  |  | 93556717103 | AMBA_BC172_Swap_MVS
|  |  |  | 93685697103 | AMBA_BH062_Swap_MVS
|  |  |  | 93622723103 | AMBA_BN078_Swap_MVS
|  |  |  | 93618719103 | AMBA_BN100_Swap_MVS
|  |  |  | 93556719103 | AMBA_BN105_Swap_MVS
|  |  |  | 93621710103 | AMBA_BN142_Swap_MVS
|  |  |  | 93556724103 | AMBA_BN149_Swap_MVS
|  |  |  | 93618720103 | AMBA_BN152_Swap_MVS
|  |  |  | 93618721103 | AMBA_BN155_Swap_MVS
|  |  |  | 93556725103 | AMBA_BN156_Swap_MVS
|  |  |  | 93622697103 | AMBA_BN181_Swap_MVS
|  |  |  | 93621701103 | AMBA_BN208_Swap_MVS
|  |  |  | 93622724103 | AMBA_BN209_Swap_MVS
|  |  |  | 93556726103 | AMBA_BN215_Swap_MVS
|  |  |  | 93622698103 | AMBA_BN233_Swap_MVS
|  |  |  | 93622725103 | AMBA_BN287_Swap_MVS
|  |  |  | 93556727103 | AMBA_BN288_Swap_MVS
|  |  |  | 93621717103 | AMBA_BN289_Swap_MVS
|  |  |  | 93622699103 | AMBA_BN303_Swap_MVS
|  |  |  | 93621718103 | AMBA_BN306_Swap_MVS
|  |  |  | 93556728103 | AMBA_BN308_Swap_MVS
|  |  |  | 93622700103 | AMBA_BN316_Swap_MVS
|  |  |  | 93621711103 | AMBA_BN335_Swap_MVS
|  |  |  | 93556720103 | AMBA_BN340_Swap_MVS
|  |  |  | 93620707103 | AMBA_BN345_Swap_MVS
|  |  |  | 93623721103 | AMBA_BN397_Swap_MVS
|  |  |  | 93620708103 | AMBA_BN400_Swap_MVS
|  |  |  | 93620709103 | AMBA_BN404_Swap_MVS
|  |  |  | 93621719103 | AMBA_BN407_Swap_MVS
|  |  |  | 93623717103 | AMBA_BN408_Swap_MVS
|  |  |  | 93622701103 | AMBA_BN416_Swap_MVS
|  |  |  | 93623718103 | AMBA_BN430_Swap_MVS
|  |  |  | 93621720103 | AMBA_BN432_Swap_MVS
|  |  |  | 93621721103 | AMBA_BN446_Swap_MVS
|  |  |  | 93623722103 | AMBA_BN448_Swap_MVS
|  |  |  | 93622717103 | AMBA_BN454_Swap_MVS
|  |  |  | 93620710103 | AMBA_BN456_Swap_MVS
|  |  |  | 93556721103 | AMBA_BN458_Swap_MVS
|  |  |  | 93622718103 | AMBA_BN460_Swap_MVS
|  |  |  | 93556722103 | AMBA_BN461_Swap_MVS
|  |  |  | 93620711103 | AMBA_BN466_Swap_MVS
|  |  |  | 93622719103 | AMBA_BN468_Swap_MVS
|  |  |  | 93622720103 | AMBA_BN471_Swap_MVS
|  |  |  | 93620712103 | AMBA_BN473_Swap_MVS
|  |  |  | 93622721103 | AMBA_BN511_Swap_MVS
|  |  |  | 93621716103 | AMBA_BO031_Swap_MVS
|  |  |  | 93620713103 | AMBA_BO035_Swap_MVS
|  |  |  | 93620702103 | AMBA_BO045_Swap_MVS
|  |  |  | 93623697103 | AMBA_BO049_Swap_MVS
|  |  |  | 93618727103 | AMBA_BO121_Swap_MVS
|  |  |  | 93623698103 | AMBA_BO137_Swap_MVS
|  |  |  | 93623699103 | AMBA_BO148_Swap_MVS
|  |  |  | 93618728103 | AMBA_BO191_Swap_MVS
|  |  |  | 93620703103 | AMBA_BO219_Swap_MVS
|  |  |  | 93620704103 | AMBA_BO287_Swap_MVS
|  |  |  | 93620714103 | AMBA_BO318_Swap_MVS
|  |  |  | 93618697103 | AMBA_BO325_Swap_MVS
|  |  |  | 93618698103 | AMBA_BO345_Swap_MVS
|  |  |  | 93618729103 | AMBA_BO348_Swap_MVS
|  |  |  | 93620715103 | AMBA_BO349_Swap_MVS
|  |  |  | 93618730103 | AMBA_BO351_Swap_MVS
|  |  |  | 93620716103 | AMBA_BO352_Swap_MVS
|  |  |  | 93620705103 | AMBA_BO356_Swap_MVS
|  |  |  | 93618731103 | AMBA_BO360_Swap_MVS
|  |  |  | 93620706103 | AMBA_BO361_Swap_MVS
|  |  |  | 93623700103 | AMBA_BO364_Swap_MVS
|  |  |  | 93623701103 | AMBA_BO366_Swap_MVS
|  |  |  | 93618722103 | AMBA_BO368_Swap_MVS
|  |  |  | 93618699103 | AMBA_BO386_Swap_MVS
|  |  |  | 93618723103 | AMBA_BO387_Swap_MVS
|  |  |  | 93618700103 | AMBA_BO388_Swap_MVS
|  |  |  | 93618707103 | AMBA_BO427_Swap_MVS
|  |  |  | 93618724103 | AMBA_BO438_Swap_MVS
|  |  |  | 93618725103 | AMBA_BO441_Swap_MVS
|  |  |  | 93621702103 | AMBA_BO442_Swap_MVS
|  |  |  | 93618726103 | AMBA_BO443_Swap_MVS
|  |  |  | 93621703103 | AMBA_BO445_Swap_MVS
|  |  |  | 93622702103 | AMBA_BO451_Swap_MVS
|  |  |  | 93621704103 | AMBA_BO452_Swap_MVS
|  |  |  | 93622703103 | AMBA_BO453_Swap_MVS
|  |  |  | 93621705103 | AMBA_BO454_Swap_MVS
|  |  |  | 93622704103 | AMBA_BO455_Swap_MVS
|  |  |  | 93618701103 | AMBA_BO456_Swap_MVS
|  |  |  | 93622705103 | AMBA_BO457_Swap_MVS
|  |  |  | 93556718103 | AMBA_BO459_Swap_MVS
|  |  |  | 93618702103 | AMBA_BO460_Swap_MVS
|  |  |  | 93622706103 | AMBA_BO461_Swap_MVS
|  |  |  | 93618703103 | AMBA_BO462_Swap_MVS
|  |  |  | 93618708103 | AMBA_BO463_Swap_MVS
|  |  |  | 93618704103 | AMBA_BO464_Swap_MVS
|  |  |  | 93618709103 | AMBA_BO465_Swap_MVS
|  |  |  | 93618710103 | AMBA_BO468_Swap_MVS
|  |  |  | 93618705103 | AMBA_BO469_Swap_MVS
|  |  |  | 93618711103 | AMBA_BO473_Swap_MVS
|  |  |  | 93618712103 | AMBA_BO477_Swap_MVS
|  |  |  | 93618706103 | AMBA_BO478_Swap_MVS
|  |  |  | 93618713103 | AMBA_BO480_Swap_MVS
|  |  |  | 93618714103 | AMBA_BO482_Swap_MVS
|  |  |  | 93621706103 | AMBA_BO484_Swap_MVS
|  |  |  | 93618715103 | AMBA_BO490_Swap_MVS
|  |  |  | 93621712103 | AMBA_BO812_Swap_MVS
|  |  |  | 93620697103 | AMBA_BO813_Swap_MVS
|  |  |  | 93621713103 | AMBA_BO814_Swap_MVS
|  |  |  | 93620698103 | AMBA_BO815_Swap_MVS
|  |  |  | 93620699103 | AMBA_BO828_Swap_MVS
|  |  |  | 93618716103 | AMBA_BO829_Swap_MVS
|  |  |  | 93620700103 | AMBA_BO833_Swap_MVS
|  |  |  | 93620701103 | AMBA_BO835_Swap_MVS
|  |  |  | 93621697103 | AMBA_BO837_Swap_MVS
|  |  |  | 93621698103 | AMBA_BO839_Swap_MVS
|  |  |  | 93618717103 | AMBA_BO843_Swap_MVS
|  |  |  | 93556716103 | AMBA_BO867_Swap_MVS
|  |  |  | 93621714103 | AMBA_BO868_Swap_MVS
|  |  |  | 93621715103 | AMBA_BO872_Swap_MVS
|  |  |  | 93621707103 | AMBA_BO889_Swap_MVS
|  |  |  | 93621699103 | AMBA_BO910_Swap_MVS
|  |  |  | 93621700103 | AMBA_BO921_Swap_MVS
|  |  |  | 93623719103 | AMBA_BS043_Swap_MVS
|  |  |  | 93623723103 | AMBA_BS062_Swap_MVS
|  |  |  | 93622726103 | AMBA_BS090_Swap_MVS
|  |  |  | 93623720103 | AMBA_BS094_Swap_MVS
|  |  |  | 93623724103 | AMBA_BS097_Swap_MVS
|  |  |  | 93623725103 | AMBA_BS102_Swap_MVS
|  |  |  | 93623726103 | AMBA_BS113_Swap_MVS
|  |  |  | 93622722103 | AMBA_BS117_Swap_MVS
|  |  |  | 93618718103 | AMBA_BS128_Swap_MVS
|  |  |  | 93556723103 | AMBA_BS134_Swap_MVS
|  |  |  | 93621708103 | AMBA_BS227_Swap_MVS
|  |  |  | 93621709103 | AMBA_BS238_Swap_MVS
|  |  |  | 90598704103 | AMBA_BS352_Swap_MVS
|  |  |  | 93626697103 | AMBA_KN083_Swap_MVS
|  |  |  | 93623706103 | AMBA_KN085_Swap_MVS
|  |  |  | 93626698103 | AMBA_KN086_Swap_MVS
|  |  |  | 93622727103 | AMBA_KN087_Swap_MVS
|  |  |  | 93622728103 | AMBA_KN106_Swap_MVS
|  |  |  | 93626699103 | AMBA_KN126_Swap_MVS
|  |  |  | 93556735103 | AMBA_KN154_Swap_MVS
|  |  |  | 93622729103 | AMBA_KN175_Swap_MVS
|  |  |  | 93580704103 | AMBA_KN202_Swap_MVS
|  |  |  | 93618734103 | AMBA_KN222_Swap_MVS
|  |  |  | 93556736103 | AMBA_KN236_Swap_MVS
|  |  |  | 93626700103 | AMBA_KN237_Swap_MVS
|  |  |  | 93556737103 | AMBA_KN239_Swap_MVS
|  |  |  | 93626701103 | AMBA_KN240_Swap_MVS
|  |  |  | 93622730103 | AMBA_KN247_Swap_MVS
|  |  |  | 93622710103 | AMBA_KN253_Swap_MVS
|  |  |  | 93622731103 | AMBA_KN254_Swap_MVS
|  |  |  | 93556729103 | AMBA_KN260_Swap_MVS
|  |  |  | 93622711103 | AMBA_KN262_Swap_MVS
|  |  |  | 93617728103 | AMBA_KN273_Swap_MVS
|  |  |  | 93623711103 | AMBA_KN274_Swap_MVS
|  |  |  | 93618735103 | AMBA_KN285_Swap_MVS
|  |  |  | 93594701103 | AMBA_KN288_Swap_MVS
|  |  |  | 93618736103 | AMBA_KN291_Swap_MVS
|  |  |  | 93556738103 | AMBA_KN295_Swap_MVS
|  |  |  | 93618737103 | AMBA_KN296_Swap_MVS
|  |  |  | 93617737103 | AMBA_KN297_Swap_MVS
|  |  |  | 93617738103 | AMBA_KN300_Swap_MVS
|  |  |  | 93594702103 | AMBA_KN303_Swap_MVS
|  |  |  | 93594703103 | AMBA_KN306_Swap_MVS
|  |  |  | 93617739103 | AMBA_KN307_Swap_MVS
|  |  |  | 93617740103 | AMBA_KN309_Swap_MVS
|  |  |  | 93594704103 | AMBA_KN310_Swap_MVS
|  |  |  | 93617741103 | AMBA_KN311_Swap_MVS
|  |  |  | 93617729103 | AMBA_KN313_Swap_MVS
|  |  |  | 93556730103 | AMBA_KN314_Swap_MVS
|  |  |  | 93623702103 | AMBA_KN318_Swap_MVS
|  |  |  | 93625704103 | AMBA_KN321_Swap_MVS
|  |  |  | 93556731103 | AMBA_KN329_Swap_MVS
|  |  |  | 93625705103 | AMBA_KN330_Swap_MVS
|  |  |  | 93580705103 | AMBA_KN345_Swap_MVS
|  |  |  | 93625706103 | AMBA_KN346_Swap_MVS
|  |  |  | 93556739103 | AMBA_KN351_Swap_MVS
|  |  |  | 93594706103 | AMBA_KN352_Swap_MVS
|  |  |  | 93594707103 | AMBA_KN356_Swap_MVS
|  |  |  | 93594705103 | AMBA_KN359_Swap_MVS
|  |  |  | 93625697103 | AMBA_KN369_Swap_MVS
|  |  |  | 93625698103 | AMBA_KN376_Swap_MVS
|  |  |  | 93594708103 | AMBA_KO037_Swap_MVS
|  |  |  | 93618738103 | AMBA_KO058_Swap_MVS
|  |  |  | 93617730103 | AMBA_KO180_Swap_MVS
|  |  |  | 93623703103 | AMBA_KO181_Swap_MVS
|  |  |  | 93617731103 | AMBA_KO183_Swap_MVS
|  |  |  | 93623712103 | AMBA_KO184_Swap_MVS
|  |  |  | 93623713103 | AMBA_KO188_Swap_MVS
|  |  |  | 93618739103 | AMBA_KO200_Swap_MVS
|  |  |  | 93618740103 | AMBA_KO212_Swap_MVS
|  |  |  | 93618741103 | AMBA_KO214_Swap_MVS
|  |  |  | 93622712103 | AMBA_KO234_Swap_MVS
|  |  |  | 93623704103 | AMBA_KO243_Swap_MVS
|  |  |  | 93623705103 | AMBA_KO256_Swap_MVS
|  |  |  | 93623714103 | AMBA_KO901_Swap_MVS
|  |  |  | 93618732103 | AMBA_KO904_Swap_MVS
|  |  |  | 93622713103 | AMBA_KO906_Swap_MVS
|  |  |  | 93622714103 | AMBA_KO908_Swap_MVS
|  |  |  | 93622707103 | AMBA_KO909_Swap_MVS
|  |  |  | 93622715103 | AMBA_KO910_Swap_MVS
|  |  |  | 93622708103 | AMBA_KO911_Swap_MVS
|  |  |  | 93622716103 | AMBA_KO912_Swap_MVS
|  |  |  | 93623707103 | AMBA_KO914_Swap_MVS
|  |  |  | 93622709103 | AMBA_KO915_Swap_MVS
|  |  |  | 93623708103 | AMBA_KO918_Swap_MVS
|  |  |  | 93625699103 | AMBA_KS020_Swap_MVS
|  |  |  | 90598705103 | AMBA_KS063_Swap_MVS
|  |  |  | 93623709103 | AMBA_KS069_Swap_MVS
|  |  |  | 93623710103 | AMBA_KS082_Swap_MVS
|  |  |  | 93556740103 | AMBA_KS116_Swap_MVS
|  |  |  | 93618733103 | AMBA_KS118_Swap_MVS
|  |  |  | 93556732103 | AMBA_KS120_Swap_MVS
|  |  |  | 93625700103 | AMBA_KS172_Swap_MVS
|  |  |  | 90560702103 | AMBA_KS306_Swap_MVS
|  |  |  | 90598703103 | AMBA_KS364_Swap_MVS
|  |  |  | 90598702103 | AMBA_KS432_Swap_MVS
|  |  |  | 90569711103 | AMBA_KS642_Swap_MVS
|  |  |  | 93556741103 | AMBA_LC008_Swap_MVS
|  |  |  | 93580701103 | AMBA_LP027_Swap_MVS
|  |  |  | 93580702103 | AMBA_LP029_Swap_MVS
|  |  |  | 93556742103 | AMBA_LP031_Swap_MVS
|  |  |  | 93556733103 | AMBA_LP044_Swap_MVS
|  |  |  | 93594709103 | AMBA_LP048_Swap_MVS
|  |  |  | 93556743103 | AMBA_LP049_Swap_MVS
|  |  |  | 93580703103 | AMBA_LP061_Swap_MVS
|  |  |  | 93625701103 | AMBA_LP066_Swap_MVS
|  |  |  | 93625702103 | AMBA_LP072_Swap_MVS
|  |  |  | 93625703103 | AMBA_LP074_Swap_MVS
|  |  |  | 93556734103 | AMBA_LP100_Swap_MVS
|  |  |  | 94164697103 | AllRegion_ClusterOPT_March_TLF
|  |  |  | 94645697103 | BA_ARBA0541_FARM_Etapa1_MVS
|  |  |  | 93712697103 | BA_ARBA1454_FARM_Etapa1_MVS
|  |  |  | 90749697103 | BA_BB006_Swap_MVS
|  |  |  | 90749699103 | BA_BB140_Swap_MVS
|  |  |  | 90598697103 | BA_BB304_Swap_MVS
|  |  |  | 90598700103 | BA_BB360_Swap_MVS
|  |  |  | 94466697103 | BA_BB372_Swap
|  |  |  | 90598699103 | BA_BB389_Swap_MVS
|  |  |  | 90598698103 | BA_BB391_Swap_MVS
|  |  |  | 90598701103 | BA_BB475_Swap_MVS
|  |  |  | 90749698103 | BA_BB482_Swap_MVS
|  |  |  | 93556746103 | BA_BH056_Swap_MVS
|  |  |  | 93556747103 | BA_BH057_Swap_MVS
|  |  |  | 93556748103 | BA_BH060_Swap_MVS
|  |  |  | 93626707103 | BA_BH068_Swap_MVS
|  |  |  | 93627699103 | BA_BH069_Swap_MVS
|  |  |  | 93626708103 | BA_BH072_Swap_MVS
|  |  |  | 93627700103 | BA_BH301_Swap_MVS
|  |  |  | 93627701103 | BA_BH302_Swap_MVS
|  |  |  | 93595703103 | BA_BH305_Swap_MVS
|  |  |  | 93626710103 | BA_BH721_Swap_MVS
|  |  |  | 93626711103 | BA_BH726_Swap_MVS
|  |  |  | 93627697103 | BA_BH739_Swap_MVS
|  |  |  | 90560701103 | BA_BM308_Swap_MVS
|  |  |  | 90560699103 | BA_BM318_Swap_MVS
|  |  |  | 90569709103 | BA_BM800_Swap_MVS
|  |  |  | 90569707103 | BA_BM801_Swap_MVS
|  |  |  | 90569710103 | BA_BM802_Swap_MVS
|  |  |  | 90687697103 | BM631_TEST
|  |  |  | 93617735103 | CABA_CM012_Swap_MVS
|  |  |  | 93617733103 | CABA_CN058_Swap_MVS
|  |  |  | 93580707103 | CABA_CN108_Swap_MVS
|  |  |  | 93623715103 | CABA_CN139_Swap_MVS
|  |  |  | 93594710103 | CABA_CN142_Swap_MVS
|  |  |  | 93626702103 | CABA_CN144_Swap_MVS
|  |  |  | 93556744103 | CABA_CN155_Swap_MVS
|  |  |  | 93626705103 | CABA_CN159_Swap_MVS
|  |  |  | 93626706103 | CABA_CN169_Swap_MVS
|  |  |  | 93626704103 | CABA_CN194_Swap_MVS
|  |  |  | 93580708103 | CABA_CS002_Swap_MVS
|  |  |  | 93626703103 | CABA_CS033_Swap_MVS
|  |  |  | 93556714103 | CABA_CS072_Swap_MVS
|  |  |  | 93580706103 | CABA_CS073_Swap_MVS
|  |  |  | 93623716103 | CABA_CS081_Swap_MVS
|  |  |  | 93617736103 | CABA_CS095_Swap_MVS
|  |  |  | 93580709103 | CABA_CS097_Swap_MVS
|  |  |  | 93617732103 | CABA_CS099_Swap_MVS
|  |  |  | 93617734103 | CABA_CU006_Swap_MVS
|  |  |  | 93556715103 | CABA_CU014_Swap_MVS
|  |  |  | 93580710103 | CABA_CU045_Swap_MVS
|  |  |  | 91265698103 | CB_XN008_Swap_MVS
|  |  |  | 91269706103 | CB_XS023_Swap_MVS
|  |  |  | 91269705103 | CB_XS024_Swap_MVS
|  |  |  | 91266735103 | CT_UE008_Swap_MVS
|  |  |  | 91266734103 | CT_UE017_Swap_MVS
|  |  |  | 91267735103 | CT_UE023_Swap_MVS
|  |  |  | 91267724103 | CT_UE025_Swap_MVS
|  |  |  | 91266733103 | CT_UE028_Swap_MVS
|  |  |  | 91267734103 | CT_UE051_Swap_MVS
|  |  |  | 91267738103 | CT_UE057_Swap_MVS
|  |  |  | 91267737103 | CT_UE058_Swap_MVS
|  |  |  | 91267733103 | CT_UE069_Swap_MVS
|  |  |  | 91267732103 | CT_UE086_Swap_MVS
|  |  |  | 91265736103 | CT_UE121_Swap_MVS
|  |  |  | 91267723103 | CT_UE125_Swap_MVS
|  |  |  | 91267731103 | CT_UE126_Swap_MVS
|  |  |  | 91267722103 | CT_UE130_Swap_MVS
|  |  |  | 91267736103 | CT_UE314_Swap_MVS
|  |  |  | 91215708103 | JY_YS009_Swap_MVS
|  |  |  | 90892697103 | LP_ARPA0040_FARM_Etapa1_MVS
|  |  |  | 89277697103 | LP_DC002_Swap_MVS
|  |  |  | 90569708103 | LP_DC022_Swap_MVS
|  |  |  | 91265726103 | LP_DC023_Swap_MVS
|  |  |  | 91265723103 | LP_DE003_Swap_MVS
|  |  |  | 91265724103 | LP_DE015_Swap_MVS
|  |  |  | 91265722103 | LP_DN006_Swap_MVS
|  |  |  | 91265721103 | LP_DN041_Swap_MVS
|  |  |  | 91265725103 | LP_DS001_Swap_MVS
|  |  |  | 91265729103 | LP_DS033_Swap_MVS
|  |  |  | 91265728103 | LP_DS047_Swap_MVS
|  |  |  | 91265727103 | LP_DW017_Swap_MVS
|  |  |  | 89775701103 | MEDI_65_XW009_OPT
|  |  |  | 89775700103 | MEDI_65_XW083_OPT
|  |  |  | 89775699103 | MEDI_65_XW095_OPT
|  |  |  | 89775698103 | MEDI_65_XW097_OPT
|  |  |  | 89775697103 | MEDI_65_XWM07_OPT
|  |  |  | 91265731103 | MEDI_MC107_SWAP_MVS
|  |  |  | 91269713103 | MEDI_MC307_SWAP_MVS
|  |  |  | 94528700103 | MEDI_OS002_Swap_MVS
|  |  |  | 94528699103 | MEDI_XC074_Swap_MVS
|  |  |  | 94528698103 | MEDI_XN092_Swap_MVS
|  |  |  | 94528701103 | MEDI_XW075_Swap_MVS
|  |  |  | 94528697103 | MEDI_XW305_Swap_MVS
|  |  |  | 91266720103 | MZ_MC004_Swap_MVS
|  |  |  | 90560704103 | MZ_MC035_Swap_MVS
|  |  |  | 91266719103 | MZ_MC041_Swap_MVS
|  |  |  | 91265732103 | MZ_MC063_Swap_MVS
|  |  |  | 90598706103 | MZ_MC064_Swap_MVS
|  |  |  | 91266718103 | MZ_MC076_Swap_MVS
|  |  |  | 91266717103 | MZ_MC077_Swap_MVS
|  |  |  | 90560706103 | MZ_MC080_Swap_MVS
|  |  |  | 91269715103 | MZ_MC126_Swap_MVS
|  |  |  | 91269714103 | MZ_MC305_Swap_MVS
|  |  |  | 88645698103 | MZ_MC397_Swap_MVS
|  |  |  | 90560705103 | MZ_MC401_Swap_MVS
|  |  |  | 90560700103 | MZ_MN008_Swap_MVS
|  |  |  | 91265730103 | MZ_MN078_Swap_MVS
|  |  |  | 91269711103 | MZ_MN083_Swap_MVS
|  |  |  | 91269710103 | MZ_MN084_Swap_MVS
|  |  |  | 91269709103 | MZ_MN088_Swap_MVS
|  |  |  | 88645697103 | MZ_MN379_Swap_MVS
|  |  |  | 91269708103 | MZ_MS006_Swap_MVS
|  |  |  | 91269707103 | MZ_MS028_Swap_MVS
|  |  |  | 90560698103 | MZ_MS032_Swap_MVS
|  |  |  | 90560703103 | NQ_QE004_Swap_MVS
|  |  |  | 91266732103 | NQ_QE378_Swap_MVS
|  |  |  | 91266731103 | NQ_QN036_Swap_MVS
|  |  |  | 91265733103 | NQ_QW013_Swap_MVS
|  |  |  | 91215718103 | RN_RE004_Swap_MVS
|  |  |  | 91269736103 | RN_RE009_Swap_MVS
|  |  |  | 91269735103 | RN_RE011_Swap_MVS
|  |  |  | 91269734103 | RN_RE022_Swap_MVS
|  |  |  | 91269733103 | RN_RE063_Swap_MVS
|  |  |  | 91269732103 | RN_RN002_Swap_MVS
|  |  |  | 91269731103 | RN_RN013_Swap_MVS
|  |  |  | 91267739103 | RN_RN016_Swap_MVS
|  |  |  | 91269730103 | RN_RN028_Swap_MVS
|  |  |  | 91269729103 | RN_RN030_Swap_MVS
|  |  |  | 91269728103 | RN_RN035_Swap_MVS
|  |  |  | 91269727103 | RN_RN037_Swap_MVS
|  |  |  | 91267725103 | RN_RN053_Swap_MVS
|  |  |  | 91269726103 | RN_RN072_Swap_MVS
|  |  |  | 91269725103 | RN_RN301_Swap_MVS
|  |  |  | 91269724103 | RN_RN302_Swap_MVS
|  |  |  | 91269723103 | RN_RN303_Swap_MVS
|  |  |  | 91269722103 | RN_RN304_Swap_MVS
|  |  |  | 91267741103 | RN_RN305_Swap_MVS
|  |  |  | 91267740103 | RN_RN344_Swap_MVS
|  |  |  | 91266730103 | RN_RS003_Swap_MVS
|  |  |  | 91266729103 | RN_RS014_Swap_MVS
|  |  |  | 91215721103 | RN_RS046_Swap_MVS
|  |  |  | 91215720103 | RN_RS056_Swap_MVS
|  |  |  | 91267726103 | RN_RS070_Swap_MVS
|  |  |  | 91215719103 | RN_RS126_Swap_MVS
|  |  |  | 91265703103 | SA_AN015_Swap_MVS
|  |  |  | 91267730103 | SC_VC003_Swap_MVS
|  |  |  | 91265735103 | SC_VE002_Swap_MVS
|  |  |  | 91267729103 | SC_VE014_Swap_MVS
|  |  |  | 91265734103 | SC_VE022_Swap_MVS
|  |  |  | 91267728103 | SC_VN010_Swap_MVS
|  |  |  | 91267727103 | SC_VW030_Swap_MVS
|  |  |  | 91265719103 | SJ_JC003_Swap_MVS
|  |  |  | 91265718103 | SJ_JC004_Swap_MVS
|  |  |  | 91265717103 | SJ_JC008_Swap_MVS
|  |  |  | 91269721103 | SJ_JC024_Swap_MVS
|  |  |  | 90253700103 | SJ_JC025_Swap_MVS
|  |  |  | 90253699103 | SJ_JC026_Swap_MVS
|  |  |  | 89567698103 | SJ_JC029_Swap_MVS
|  |  |  | 91269720103 | SJ_JC054_Swap_MVS
|  |  |  | 91269719103 | SJ_JC101_Swap_MVS
|  |  |  | 91269718103 | SJ_JC302_Swap_MVS
|  |  |  | 90253698103 | SJ_JC322_Swap_MVS
|  |  |  | 90253697103 | SJ_JC326_Swap_MVS
|  |  |  | 91269717103 | SJ_JC336_Swap_MVS
|  |  |  | 91266721103 | SJ_JS011_Swap_MVS
|  |  |  | 89567697103 | SJ_JS307_Swap_MVS
|  |  |  | 89157697103 | SL_FC001_Swap_MVS
|  |  |  | 89153704103 | SL_FC003_Swap_MVS
|  |  |  | 89157707103 | SL_FC004_Swap_MVS
|  |  |  | 89153703103 | SL_FC006_Swap_MVS
|  |  |  | 89153702103 | SL_FC007_Swap_MVS
|  |  |  | 89153701103 | SL_FC022_Swap_MVS
|  |  |  | 89153700103 | SL_FC032_Swap_MVS
|  |  |  | 89159701103 | SL_FC036_Swap_MVS
|  |  |  | 89156701103 | SL_FC037_Swap_MVS
|  |  |  | 89156700103 | SL_FC302_Swap_MVS
|  |  |  | 89156699103 | SL_FC333_Swap_MVS
|  |  |  | 89158699103 | SL_FE012_Swap_MVS
|  |  |  | 89158698103 | SL_FE014_Swap_MVS
|  |  |  | 89159700103 | SL_FE017_Swap_MVS
|  |  |  | 89156698103 | SL_FE019_Swap_MVS
|  |  |  | 89159697103 | SL_FE020_Swap_MVS
|  |  |  | 89158697103 | SL_FE021_Swap_MVS
|  |  |  | 89156697103 | SL_FE041_Swap_MVS
|  |  |  | 89157706103 | SL_FE047_Swap_MVS
|  |  |  | 89157705103 | SL_FE048_Swap_MVS
|  |  |  | 89157698103 | SL_FE055_Swap_MVS
|  |  |  | 89155697103 | SL_FE056_Swap_MVS
|  |  |  | 89155701103 | SL_FE343_Swap_MVS
|  |  |  | 89157703103 | SL_FEM22_Swap_MVS
|  |  |  | 89157702103 | SL_FEM44_Swap_MVS
|  |  |  | 89158701103 | SL_FN001_Swap_MVS
|  |  |  | 89155698103 | SL_FN002_Swap_MVS
|  |  |  | 89158700103 | SL_FN004_Swap_MVS
|  |  |  | 91265720103 | SL_FN007_Swap_MVS
|  |  |  | 89157704103 | SL_FN010_Swap_MVS
|  |  |  | 89159698103 | SL_FN019_Swap_MVS
|  |  |  | 89157700103 | SL_FN026_Swap_MVS
|  |  |  | 89155700103 | SL_FN032_Swap_MVS
|  |  |  | 89155699103 | SL_FN036_Swap_MVS
|  |  |  | 89157699103 | SL_FN129_Swap_MVS
|  |  |  | 89157701103 | SL_FO013_Swap_MVS
|  |  |  | 89159699103 | SL_FO112_Swap_MVS
|  |  |  | 90956698103 | SOUTH_A38-B315_5G
|  |  |  | 90956700103 | SOUTH_A38-B322_5G
|  |  |  | 90431697103 | SUR_123_QE005_RSH_OPT
|  |  |  | 98690699103 | SUR_130_QC006_RSH_OPT_4G
|  |  |  | 98690698103 | SUR_130_QC006_RSH_OPT_5G
|  |  |  | 98690708103 | SUR_130_QC012_RSH_OPT_4G
|  |  |  | 98690707103 | SUR_130_QC013_RSH_OPT_4G
|  |  |  | 98690706103 | SUR_130_QC023_RSH_OPT_4G
|  |  |  | 98690702103 | SUR_130_QC023_RSH_OPT_5G
|  |  |  | 98690705103 | SUR_130_QC037_RSH_OPT_4G
|  |  |  | 98690701103 | SUR_130_QC037_RSH_OPT_5G
|  |  |  | 90606703103 | SUR_130_QC044_RSH_OPT
|  |  |  | 98690704103 | SUR_130_QC053_RSH_OPT_4G
|  |  |  | 98690700103 | SUR_130_QC053_RSH_OPT_5G
|  |  |  | 90606704103 | SUR_130_QC054_RSH_OPT
|  |  |  | 98690703103 | SUR_130_QC076_RSH_OPT_4G
|  |  |  | 94091708103 | SUR_131_A30-Q003_RSH_OPT_4G
|  |  |  | 94102704103 | SUR_131_A30-Q003_RSH_OPT_5G
|  |  |  | 94091707103 | SUR_131_A30-Q048_RSH_OPT_4G
|  |  |  | 94091706103 | SUR_131_A30-Q076_RSH_OPT_4G
|  |  |  | 94151697103 | SUR_131_QC074_RSH_OPT_5G
|  |  |  | 94151698103 | SUR_131_QC105_RSH_OPT_5G
|  |  |  | 94091700103 | SUR_134_A30-Q007_RSH_OPT_4G
|  |  |  | 94091701103 | SUR_134_A30-Q029_RSH_OPT_4G
|  |  |  | 94101708103 | SUR_134_QE009_RSH_OPT_4G
|  |  |  | 94101709103 | SUR_134_QE037_RSH_OPT_4G
|  |  |  | 94101710103 | SUR_134_QE051_RSH_OPT_4G
|  |  |  | 94151699103 | SUR_134_QE083_RSH_OPT_4G
|  |  |  | 90608770103 | SUR_179_BM004_RSH_OPT
|  |  |  | 90608755103 | SUR_179_BM116_RSH_OPT
|  |  |  | 90608769103 | SUR_179_BM506_RSH_OPT
|  |  |  | 90608768103 | SUR_179_BM584_RSH_OPT
|  |  |  | 90608767103 | SUR_179_BM749_RSH_OPT
|  |  |  | 90608773103 | SUR_179_BM750_RSH_OPT
|  |  |  | 90608766103 | SUR_179_BM751_RSH_OPT
|  |  |  | 90608765103 | SUR_179_BM752_RSH_OPT
|  |  |  | 90608764103 | SUR_179_BM805_RSH_OPT
|  |  |  | 90608763103 | SUR_179_BM806_RSH_OPT
|  |  |  | 90608772103 | SUR_179_BM808_RSH_OPT
|  |  |  | 90608771103 | SUR_179_BM809_RSH_OPT
|  |  |  | 89129705103 | SUR_181 _BM538_OPT
|  |  |  | 89111707103 | SUR_181_BM540_OPT
|  |  |  | 89111706103 | SUR_181_BM541_OPT
|  |  |  | 89111705103 | SUR_181_BM543_OPT
|  |  |  | 89111704103 | SUR_181_BM544_OPT
|  |  |  | 89111703103 | SUR_181_BM545_OPT
|  |  |  | 89111702103 | SUR_181_BM546_OPT
|  |  |  | 89111701103 | SUR_181_BM547_OPT
|  |  |  | 89111700103 | SUR_181_BM548_OPT
|  |  |  | 91246712103 | SUR_184_BM484_RSH_OPT_5G
|  |  |  | 93827709103 | SUR_184_BM611_RSH_OPT_5G
|  |  |  | 91246699103 | SUR_185_BM008_RSH_OPT_5G
|  |  |  | 91246700103 | SUR_186_BM312_RSH_OPT_5G
|  |  |  | 90431704103 | SUR_188_BM057_RSH_OPT
|  |  |  | 90431705103 | SUR_188_BM303_RSH_OPT
|  |  |  | 90431703103 | SUR_188_BM357_RSH_OPT
|  |  |  | 90606700103 | SUR_188_BM550_RSH_OPT
|  |  |  | 90606701103 | SUR_188_BM725_RSH_OPT
|  |  |  | 90608754103 | SUR_199_BM129_RSH_OPT
|  |  |  | 90608753103 | SUR_199_BM316_RSH_OPT
|  |  |  | 90608756103 | SUR_199_BM329_RSH_OPT
|  |  |  | 90608760103 | SUR_199_BM391_RSH_OPT
|  |  |  | 90608759103 | SUR_199_BM638_RSH_OPT
|  |  |  | 90608752103 | SUR_199_BM640_RSH_OPT
|  |  |  | 90608758103 | SUR_199_BM642_RSH_OPT
|  |  |  | 90608751103 | SUR_199_BM643_RSH_OPT
|  |  |  | 90608750103 | SUR_199_BM778_RSH_OPT
|  |  |  | 91247697103 | SUR_200_BM010_RSH_OPT_5G
|  |  |  | 91247698103 | SUR_201_BM096_RSH_OPT_5G
|  |  |  | 89131697103 | SUR_202 _BH045_OPT
|  |  |  | 93728700103 | SUR_204_BM083_OPT_4G
|  |  |  | 93728698103 | SUR_204_BM083_OPT_Adec
|  |  |  | 93728699103 | SUR_204_BM094_OPT_4G
|  |  |  | 93728697103 | SUR_204_BM094_OPT_Adec
|  |  |  | 90608762103 | SUR_204_BM375_RSH_OPT
|  |  |  | 91246704103 | SUR_205_BM025_RSH_OPT_5G
|  |  |  | 91246706103 | SUR_205_BM104_RSH_OPT_5G
|  |  |  | 91246705103 | SUR_206_BM040_RSH_OPT_5G
|  |  |  | 91246707103 | SUR_206_BM631_RSH_OPT_5G
|  |  |  | 91246708103 | SUR_207_BM625_RSH_OPT_5G
|  |  |  | 90608761103 | SUR_208_BM106_RSH_OPT
|  |  |  | 94091697103 | SUR_247_A37-B060_RSH_OPT_4G
|  |  |  | 94101702103 | SUR_247_BT042_RSH_OPT_4G
|  |  |  | 94101701103 | SUR_247_BT043_RSH_OPT_4G
|  |  |  | 94091699103 | SUR_283_A42-B393_RSH_OPT_4G
|  |  |  | 94091698103 | SUR_283_A42-B394_RSH_OPT_4G
|  |  |  | 94101705103 | SUR_283_BH001_RSH_OPT_4G
|  |  |  | 94101704103 | SUR_283_BH043_RSH_OPT_4G
|  |  |  | 94101706103 | SUR_283_BH062_RSH_OPT_4G
|  |  |  | 94101703103 | SUR_283_BH073_RSH_OPT_4G
|  |  |  | 90185702103 | SUR_329_BM033_OPT
|  |  |  | 90608757103 | SUR_329_BM141_RSH_OPT
|  |  |  | 90608749103 | SUR_329_BM393_RSH_OPT
|  |  |  | 90608748103 | SUR_329_BM501_RSH_OPT
|  |  |  | 90608747103 | SUR_329_BM767_RSH_OPT
|  |  |  | 90608746103 | SUR_329_BM768_RSH_OPT
|  |  |  | 88561709103 | SUR_334_BM018_RSH_OPT
|  |  |  | 94091705103 | SUR_3_A38-B051_RSH_OPT_4G
|  |  |  | 94102703103 | SUR_3_A38-B051_RSH_OPT_5G
|  |  |  | 94091704103 | SUR_3_A38-B055_RSH_OPT_4G
|  |  |  | 94091703103 | SUR_3_A38-B318_RSH_OPT_4G
|  |  |  | 94091702103 | SUR_3_A38-B323_RSH_OPT_4G
|  |  |  | 94102697103 | SUR_3_BB064_RSH_OPT_4G
|  |  |  | 94101699103 | SUR_3_BB064_RSH_OPT_5G
|  |  |  | 94101711103 | SUR_3_BB173_RSH_OPT_4G
|  |  |  | 94101698103 | SUR_3_BB173_RSH_OPT_5G
|  |  |  | 94102701103 | SUR_3_BB307_RSH_OPT_4G
|  |  |  | 94101700103 | SUR_3_BB307_RSH_OPT_5G
|  |  |  | 94102700103 | SUR_3_BB351_RSH_OPT_4G
|  |  |  | 94102699103 | SUR_3_BB391_RSH_OPT_4G
|  |  |  | 94102698103 | SUR_3_BB482_RSH_OPT_4G
|  |  |  | 90185701103 | SUR_501_JS502_OPT
|  |  |  | 88561697103 | SUR_502_JC005_RSH_OPT
|  |  |  | 90431700103 | SUR_502_JC053_RSH_OPT
|  |  |  | 90606699103 | SUR_502_JC101_RSH_OPT
|  |  |  | 90431701103 | SUR_502_JC341_RSH_OPT
|  |  |  | 90608745103 | SUR_514_MO002_RSH_OPT
|  |  |  | 90608744103 | SUR_514_MS011_RSH_OPT
|  |  |  | 90608743103 | SUR_514_MS019_RSH_OPT
|  |  |  | 90608742103 | SUR_514_MS023_RSH_OPT
|  |  |  | 90608741103 | SUR_514_MS028_RSH_OPT
|  |  |  | 90608740103 | SUR_514_MS030_RSH_OPT
|  |  |  | 90608739103 | SUR_514_MS032_RSH_OPT
|  |  |  | 90608738103 | SUR_514_MS035_RSH_OPT
|  |  |  | 90608737103 | SUR_514_MS038_RSH_OPT
|  |  |  | 90608736103 | SUR_514_MS041_RSH_OPT
|  |  |  | 90608735103 | SUR_514_MS042_RSH_OPT
|  |  |  | 90608734103 | SUR_514_MS044_RSH_OPT
|  |  |  | 90608733103 | SUR_514_MS062_RSH_OPT
|  |  |  | 90608732103 | SUR_514_MS063_RSH_OPT
|  |  |  | 90608731103 | SUR_514_MS122_RSH_OPT
|  |  |  | 90608730103 | SUR_515_MS001_RSH_OPT
|  |  |  | 90608729103 | SUR_515_MS005_RSH_OPT
|  |  |  | 90608728103 | SUR_515_MS006_RSH_OPT
|  |  |  | 90608727103 | SUR_515_MS009_RSH_OPT
|  |  |  | 90608726103 | SUR_515_MS017_RSH_OPT
|  |  |  | 90608725103 | SUR_515_MS054_RSH_OPT
|  |  |  | 90608724103 | SUR_515_MS059_RSH_OPT
|  |  |  | 90608723103 | SUR_515_MS061_RSH_OPT
|  |  |  | 90608722103 | SUR_515_MS066_RSH_OPT
|  |  |  | 90608721103 | SUR_515_MS067_RSH_OPT
|  |  |  | 90185700103 | SUR_515_MS075_OPT
|  |  |  | 90185699103 | SUR_515_MS503_OPT
|  |  |  | 90608720103 | SUR_515_MSM24_RSH_OPT
|  |  |  | 88561706103 | SUR_518_MC006_RSH_OPT
|  |  |  | 88561705103 | SUR_518_MC010_RSH_OPT
|  |  |  | 88561704103 | SUR_518_MC068_RSH_OPT
|  |  |  | 90431702103 | SUR_518_MC073_RSH_OPT
|  |  |  | 90431698103 | SUR_519_MC305_RSH_OPT
|  |  |  | 88561703103 | SUR_520_MC017_RSH_OPT
|  |  |  | 88561702103 | SUR_520_MC033_RSH_OPT
|  |  |  | 88561701103 | SUR_520_MC051_RSH_OPT
|  |  |  | 90185698103 | SUR_521_MC326_OPT
|  |  |  | 90606698103 | SUR_521_MC326_RSH_OPT
|  |  |  | 88561698103 | SUR_522_MC039_RSH_OPT
|  |  |  | 88561700103 | SUR_522_MC107_RSH_OPT
|  |  |  | 90606697103 | SUR_522_MC307_RSH_OPT
|  |  |  | 88561699103 | SUR_522_MC348_RSH_OPT
|  |  |  | 90608699103 | SUR_523_MC035_RSH_OPT
|  |  |  | 90608698103 | SUR_523_MC041_RSH_OPT
|  |  |  | 90608719103 | SUR_523_MC080_RSH_OPT
|  |  |  | 90608697103 | SUR_523_MC091_RSH_OPT
|  |  |  | 90608700103 | SUR_523_MC093_RSH_OPT
|  |  |  | 90608718103 | SUR_523_MC094_RSH_OPT
|  |  |  | 90608717103 | SUR_523_MC300_RSH_OPT
|  |  |  | 90608716103 | SUR_523_MC401_RSH_OPT
|  |  |  | 90608715103 | SUR_523_MC403_RSH_OPT
|  |  |  | 90608714103 | SUR_523_MC409_RSH_OPT
|  |  |  | 90185697103 | SUR_524_MN510_OPT
|  |  |  | 90431699103 | SUR_529_MS014_RSH_OPT
|  |  |  | 89781715103 | SUR_529_MS022_RSH_OPT
|  |  |  | 88561708103 | SUR_530_MC316_RSH_OPT
|  |  |  | 88561707103 | SUR_530_MC319_RSH_OPT
|  |  |  | 90608713103 | SUR_531_JS002_RSH_OPT
|  |  |  | 90608712103 | SUR_531_JS012_RSH_OPT
|  |  |  | 90608711103 | SUR_531_JS015_RSH_OPT
|  |  |  | 90608710103 | SUR_531_JS017_RSH_OPT
|  |  |  | 90608709103 | SUR_531_JS026_RSH_OPT
|  |  |  | 90608708103 | SUR_531_JS027_RSH_OPT
|  |  |  | 90608707103 | SUR_531_JS028_RSH_OPT
|  |  |  | 90608706103 | SUR_531_JS033_RSH_OPT
|  |  |  | 90608705103 | SUR_531_JS037_RSH_OPT
|  |  |  | 90608704103 | SUR_531_JS039_RSH_OPT
|  |  |  | 90608703103 | SUR_531_JS040_RSH_OPT
|  |  |  | 90608702103 | SUR_531_JS045_RSH_OPT
|  |  |  | 90608701103 | SUR_531_JS101_RSH_OPT
|  |  |  | 91246701103 | SUR_533_MC016_RSH_OPT_5G
|  |  |  | 91246702103 | SUR_533_MC092_RSH_OPT_5G
|  |  |  | 91246703103 | SUR_533_MC315_RSH_OPT_5G
|  |  |  | 89779698103 | SUR_534_M0016_RSH_OPT
|  |  |  | 94527699103 | South_A33-O006_Mod_TA
|  |  |  | 94527698103 | South_A33-O010_Mod_TA
|  |  |  | 94527697103 | South_A33-O045_Mod_TA
|  |  |  | 94526701103 | South_A33-O059_Mod_TA
|  |  |  | 94526700103 | South_A33-O064_Mod_TA
|  |  |  | 94525702103 | South_A33-O073_Mod_TA
|  |  |  | 94527701103 | South_A33-O088_Mod_TA
|  |  |  | 94526699103 | South_A33-O091_Mod_TA
|  |  |  | 94526698103 | South_A33-O112_Mod_TA
|  |  |  | 94526697103 | South_A33-O143_Mod_TA
|  |  |  | 94525701103 | South_A33-O218_Mod_TA
|  |  |  | 94525704103 | South_A33-O245_Mod_TA
|  |  |  | 94527700103 | South_A33-O381_Mod_TA
|  |  |  | 94525700103 | South_A33-O389_Mod_TA
|  |  |  | 94525697103 | South_A33-O574_Mod_TA
|  |  |  | 94525699103 | South_A33-O737_Mod_TA
|  |  |  | 94525703103 | South_A35-D036_Mod_TA
|  |  |  | 94606698103 | South_A37-B060_Mod_TA
|  |  |  | 94606697103 | South_A37-B131_Mod_TA
|  |  |  | 94528702103 | South_MC373_Swap_MVS
|  |  |  | 94687697103 | Storage_March
|  |  |  | 91266725103 | TF_IC001_Swap_MVS
|  |  |  | 91266724103 | TF_IC002_Swap_MVS
|  |  |  | 91266736103 | TF_IC005_Swap_MVS
|  |  |  | 91266728103 | TF_IC008_Swap_MVS
|  |  |  | 91266727103 | TF_IC015_Swap_MVS
|  |  |  | 91266723103 | TF_IC017_Swap_MVS
|  |  |  | 91266722103 | TF_IC021_Swap_MVS
|  |  |  | 91266726103 | TF_IC024_Swap_MVS
|  |  |  | 91266737103 | TF_IN001_Swap_MVS
|  |  |  | 91267709103 | TU_TC040_Swap_MVS
|  |  |  | 91266704103 | TU_TE006_Swap_MVS
|  |  |  | 91265707103 | TU_TE007_Swap_MVS
|  |  |  | 91266702103 | TU_TE013_Swap_MVS
|  |  |  | 91267702103 | TU_TN001_Swap_MVS
|  |  |  | 91269701103 | TU_TN010_Swap_MVS
|  |  |  | 91266707103 | TU_TN130_Swap_MVS
|  |  |  | 91265708103 | TU_TS012_Swap_MVS
|  |  |  | 91268699103 | TU_TS052_Swap_MVS
|  |  |  | 93280743103 | AMBA_102_KS173_RSH_OPT_5G
|  |  |  | 93280742103 | AMBA_102_KS237_RSH_OPT_5G
|  |  |  | 93332700103 | AMBA_102_KS348_RSH_OPT_5G
|  |  |  | 93332699103 | AMBA_102_KS349_RSH_OPT_5G
|  |  |  | 93332698103 | AMBA_102_KS375_RSH_OPT_5G
|  |  |  | 93332697103 | AMBA_102_KS608_RSH_OPT_5G
|  |  |  | 93332704103 | AMBA_103_BS374_RSH_OPT_5G
|  |  |  | 93280741103 | AMBA_104_BS107_RSH_OPT_5G
|  |  |  | 93280740103 | AMBA_106_BN105_RSH_OPT_5G
|  |  |  | 93280739103 | AMBA_106_BN243_RSH_OPT_5G
|  |  |  | 93280738103 | AMBA_106_BN266_RSH_OPT_5G
|  |  |  | 91375701103 | AMBA_108_KN322_RSH_OPT
|  |  |  | 93280736103 | AMBA_110_KO059_RSH_OPT_5G
|  |  |  | 93280735103 | AMBA_110_KO066_RSH_OPT_5G
|  |  |  | 93280737103 | AMBA_110_KO215_RSH_OPT_5G
|  |  |  | 93280734103 | AMBA_115_KN214_RSH_OPT_5G
|  |  |  | 93280733103 | AMBA_116_KN269_RSH_OPT_5G
|  |  |  | 93280732103 | AMBA_116_KO050_RSH_OPT_5G
|  |  |  | 93095766103 | AMBA_117_CN188_RSH_OPT_4G
|  |  |  | 93095764103 | AMBA_117_CN267_RSH_OPT_4G
|  |  |  | 93095765103 | AMBA_117_CN355_RSH_OPT_4G
|  |  |  | 93280731103 | AMBA_120_BN174_RSH_OPT_5G
|  |  |  | 93280730103 | AMBA_120_BN249_RSH_OPT_5G
|  |  |  | 93280729103 | AMBA_121_KN103_RSH_OPT_5G
|  |  |  | 93280728103 | AMBA_121_KN258_RSH_OPT_5G
|  |  |  | 93280727103 | AMBA_121_KN323_RSH_OPT_5G
|  |  |  | 93280726103 | AMBA_122_BN175_RSH_OPT_5G
|  |  |  | 93278703103 | AMBA_122_BN226_RSH_OPT_5G
|  |  |  | 93280725103 | AMBA_123_KN166_RSH_OPT_5G
|  |  |  | 93280724103 | AMBA_123_KN202_RSH_OPT_5G
|  |  |  | 93280723103 | AMBA_123_KN203_RSH_OPT_5G
|  |  |  | 93280722103 | AMBA_123_KN364_RSH_OPT_5G
|  |  |  | 93280721103 | AMBA_126_KN118_RSH_OPT_5G
|  |  |  | 93280720103 | AMBA_127_KN087_RSH_OPT_5G
|  |  |  | 94131698103 | AMBA_129_CN194_RSH_OPT_5G
|  |  |  | 93280719103 | AMBA_130_KN209_RSH_OPT_5G
|  |  |  | 93280718103 | AMBA_131_CN016_RSH_OPT_5G
|  |  |  | 93280717103 | AMBA_131_KN363_RSH_OPT_5G
|  |  |  | 93280712103 | AMBA_132_KN079_RSH_OPT_5G
|  |  |  | 93280716103 | AMBA_132_KN080_RSH_OPT_5G
|  |  |  | 93280711103 | AMBA_132_KN134_RSH_OPT_5G
|  |  |  | 93280715103 | AMBA_132_KN163_RSH_OPT_5G
|  |  |  | 93280714103 | AMBA_132_KN206_RSH_OPT_5G
|  |  |  | 93280713103 | AMBA_132_KN303_RSH_OPT_5G
|  |  |  | 93280709103 | AMBA_133_KN082_RSH_OPT_5G
|  |  |  | 93280710103 | AMBA_133_KN259_RSH_OPT_5G
|  |  |  | 93280707103 | AMBA_134_KN109_RSH_OPT_5G
|  |  |  | 93280706103 | AMBA_134_KN154_RSH_OPT_5G
|  |  |  | 93278702103 | AMBA_134_KN155_RSH_OPT_5G
|  |  |  | 93280708103 | AMBA_134_KN215_RSH_OPT_5G
|  |  |  | 93095761103 | AMBA_135_CN063_RSH_OPT_4G
|  |  |  | 93095763103 | AMBA_135_CN314_RSH_OPT_4G
|  |  |  | 93095762103 | AMBA_135_CN318_RSH_OPT_4G
|  |  |  | 93095744103 | AMBA_136_CN025_RSH_OPT_4G
|  |  |  | 93095745103 | AMBA_136_CN142_RSH_OPT_4G
|  |  |  | 94131701103 | AMBA_136_CN142_RSH_OPT_5G
|  |  |  | 93095742103 | AMBA_136_CN214_RSH_OPT_4G
|  |  |  | 93095741103 | AMBA_136_CN317_RSH_OPT_4G
|  |  |  | 93095739103 | AMBA_136_CN448_RSH_OPT_4G
|  |  |  | 93095740103 | AMBA_136_CN454_RSH_OPT_4G
|  |  |  | 93095743103 | AMBA_136_CS102_RSH_OPT_4G
|  |  |  | 94273704103 | AMBA_136_CS102_RSH_OPT_5G
|  |  |  | 94131699103 | AMBA_137_CS073_RSH_OPT_5G
|  |  |  | 93095754103 | AMBA_138_CN027_RSH_OPT_5G
|  |  |  | 93095753103 | AMBA_138_CN228_RSH_OPT_4G
|  |  |  | 93095752103 | AMBA_138_CN280_RSH_OPT_4G
|  |  |  | 93095751103 | AMBA_138_CS277_RSH_OPT_4G
|  |  |  | 93095750103 | AMBA_138_CS806_RSH_OPT_4G
|  |  |  | 93095759103 | AMBA_139_CN231_RSH_OPT_4G
|  |  |  | 93095758103 | AMBA_139_CN281_RSH_OPT_4G
|  |  |  | 93095757103 | AMBA_139_CN292_RSH_OPT_4G
|  |  |  | 93095756103 | AMBA_139_CN352_RSH_OPT_4G
|  |  |  | 93095760103 | AMBA_139_CN476_RSH_OPT_4G
|  |  |  | 93095755103 | AMBA_139_CN478_RSH_OPT_4G
|  |  |  | 93095747103 | AMBA_140_CS046_RSH_OPT_4G
|  |  |  | 93095748103 | AMBA_140_CS098_RSH_OPT_4G
|  |  |  | 93095746103 | AMBA_140_CS162_RSH_OPT_4G
|  |  |  | 93095749103 | AMBA_140_CS276_RSH_OPT_4G
|  |  |  | 93278701103 | AMBA_141_CN212_RSH_OPT_5G
|  |  |  | 93278700103 | AMBA_141_CN259_RSH_OPT_5G
|  |  |  | 93280705103 | AMBA_141_CN306_RSH_OPT_5G
|  |  |  | 93280703103 | AMBA_141_CN444_RSH_OPT_5G
|  |  |  | 93280704103 | AMBA_141_CN819_RSH_OPT_5G
|  |  |  | 93280702103 | AMBA_142_CN159_RSH_OPT_5G
|  |  |  | 93280701103 | AMBA_142_CN193_RSH_OPT_5G
|  |  |  | 93280697103 | AMBA_142_CN253_RSH_OPT_5G
|  |  |  | 93280700103 | AMBA_142_CN254_RSH_OPT_5G
|  |  |  | 93280699103 | AMBA_142_CN312_RSH_OPT_5G
|  |  |  | 93280698103 | AMBA_142_CN830_RSH_OPT_5G
|  |  |  | 93279731103 | AMBA_143_CN307_RSH_OPT_5G
|  |  |  | 93279730103 | AMBA_143_KN077_RSH_OPT_5G
|  |  |  | 93279729103 | AMBA_143_KN120_RSH_OPT_5G
|  |  |  | 93279728103 | AMBA_143_KN191_RSH_OPT_5G
|  |  |  | 93279726103 | AMBA_145_CN169_RSH_OPT_5G
|  |  |  | 93279727103 | AMBA_145_CN274_RSH_OPT_5G
|  |  |  | 93279725103 | AMBA_145_CN493_RSH_OPT_5G
|  |  |  | 93095794103 | AMBA_149_CN185_RSH_OPT_4G
|  |  |  | 93095792103 | AMBA_149_CN225_RSH_OPT_4G
|  |  |  | 93095791103 | AMBA_149_CN226_RSH_OPT_4G
|  |  |  | 93095795103 | AMBA_149_CN347_RSH_OPT_4G
|  |  |  | 93095793103 | AMBA_149_CS090_RSH_OPT_4G
|  |  |  | 93095790103 | AMBA_149_CS140_RSH_OPT_4G
|  |  |  | 93095788103 | AMBA_149_CS268_RSH_OPT_4G
|  |  |  | 93095789103 | AMBA_149_CS269_RSH_OPT_4G
|  |  |  | 93095785103 | AMBA_151_CN199_RSH_OPT_4G
|  |  |  | 93095784103 | AMBA_151_CN297_RSH_OPT_4G
|  |  |  | 93095783103 | AMBA_151_CN298_RSH_OPT_4G
|  |  |  | 93095782103 | AMBA_151_CN393_RSH_OPT_4G
|  |  |  | 93095786103 | AMBA_151_CN404_RSH_OPT_4G
|  |  |  | 93095787103 | AMBA_151_CN405_RSH_OPT_5G
|  |  |  | 93095776103 | AMBA_152_CN394_RSH_OPT_4G
|  |  |  | 93095775103 | AMBA_152_CN396_RSH_OPT_4G
|  |  |  | 93095781103 | AMBA_152_CN823_RSH_OPT_4G
|  |  |  | 93095780103 | AMBA_152_CS131_RSH_OPT_4G
|  |  |  | 93095779103 | AMBA_152_CS250_RSH_OPT_4G
|  |  |  | 93095778103 | AMBA_152_CS251_RSH_OPT_4G
|  |  |  | 93095774103 | AMBA_152_CS256_RSH_OPT_4G
|  |  |  | 93095777103 | AMBA_152_CS324_RSH_OPT_4G
|  |  |  | 93279724103 | AMBA_153_CN037_RSH_OPT_5G
|  |  |  | 93279719103 | AMBA_153_CN202_RSH_OPT_5G
|  |  |  | 93279723103 | AMBA_153_CN232_RSH_OPT_5G
|  |  |  | 93279718103 | AMBA_153_CN233_RSH_OPT_5G
|  |  |  | 93279722103 | AMBA_153_CN240_RSH_OPT_5G
|  |  |  | 93278699103 | AMBA_153_CN324_RSH_OPT_5G
|  |  |  | 93279721103 | AMBA_153_CN325_RSH_OPT_5G
|  |  |  | 93279720103 | AMBA_153_CN425_RSH_OPT_5G
|  |  |  | 93279714103 | AMBA_154_CN206_RSH_OPT_5G
|  |  |  | 93279717103 | AMBA_154_CN248_RSH_OPT_5G
|  |  |  | 93279716103 | AMBA_154_CN294_RSH_OPT_5G
|  |  |  | 93279715103 | AMBA_154_CN311_RSH_OPT_5G
|  |  |  | 93279713103 | AMBA_155_CN108_RSH_OPT_5G
|  |  |  | 93279712103 | AMBA_155_CN144_RSH_OPT_5G
|  |  |  | 93279711103 | AMBA_155_CN428_RSH_OPT_5G
|  |  |  | 93279710103 | AMBA_156_CN321_RSH_OPT_5G
|  |  |  | 93279709103 | AMBA_156_CN343_RSH_OPT_5G
|  |  |  | 93279708103 | AMBA_156_CN344_RSH_OPT_5G
|  |  |  | 93279707103 | AMBA_157_CN046_RSH_OPT_5G
|  |  |  | 93279706103 | AMBA_157_CN250_RSH_OPT_5G
|  |  |  | 93279704103 | AMBA_157_CN275_RSH_OPT_5G
|  |  |  | 93279705103 | AMBA_157_CN293_RSH_OPT_5G
|  |  |  | 93279703103 | AMBA_158_CN216_RSH_OPT_5G
|  |  |  | 93279702103 | AMBA_158_CN372_RSH_OPT_5G
|  |  |  | 93278698103 | AMBA_158_CN491_RSH_OPT_5G
|  |  |  | 93279701103 | AMBA_159_CM001_RSH_OPT_5G
|  |  |  | 93279700103 | AMBA_159_CM026_RSH_OPT_5G
|  |  |  | 93279699103 | AMBA_159_CM029_RSH_OPT_5G
|  |  |  | 93279698103 | AMBA_159_CM036_RSH_OPT_5G
|  |  |  | 93279697103 | AMBA_159_CN291_RSH_OPT_5G
|  |  |  | 93278821103 | AMBA_160_CN247_RSH_OPT_5G
|  |  |  | 93278820103 | AMBA_161_CN167_RSH_OPT_5G
|  |  |  | 93278819103 | AMBA_161_CN244_RSH_OPT_5G
|  |  |  | 93278818103 | AMBA_162_CN155_RSH_OPT_5G
|  |  |  | 93278817103 | AMBA_162_CU003_RSH_OPT_5G
|  |  |  | 93278816103 | AMBA_162_CU049_RSH_OPT_5G
|  |  |  | 93278814103 | AMBA_163_CU007_RSH_OPT_5G
|  |  |  | 93278813103 | AMBA_163_CU048_RSH_OPT_5G
|  |  |  | 93278815103 | AMBA_163_CU067_RSH_OPT_5G
|  |  |  | 93278812103 | AMBA_164_CS003_RSH_OPT_5G
|  |  |  | 91375705103 | AMBA_166_CS026_RSH_OPT_5G
|  |  |  | 93278811103 | AMBA_166_CS289_RSH_OPT_5G
|  |  |  | 93278810103 | AMBA_166_CU005_RSH_OPT_5G
|  |  |  | 93278809103 | AMBA_166_CU068_RSH_OPT_5G
|  |  |  | 93095738103 | AMBA_167_CS331_RSH_OPT_4G
|  |  |  | 93095737103 | AMBA_167_CS334_RSH_OPT_4G
|  |  |  | 93095736103 | AMBA_167_CS337_RSH_OPT_4G
|  |  |  | 93278808103 | AMBA_168_CM005_RSH_OPT_5G
|  |  |  | 93278807103 | AMBA_168_CU081_RSH_OPT_5G
|  |  |  | 93278697103 | AMBA_168_KN127_RSH_OPT_5G
|  |  |  | 93277706103 | AMBA_170_CM033_RSH_OPT_5G
|  |  |  | 93277705103 | AMBA_171_CS002_RSH_OPT_5G
|  |  |  | 93278801103 | AMBA_171_CS029_RSH_OPT_5G
|  |  |  | 93278806103 | AMBA_171_CS127_RSH_OPT_5G
|  |  |  | 93278805103 | AMBA_171_CS133_RSH_OPT_5G
|  |  |  | 93278804103 | AMBA_171_CS136_RSH_OPT_5G
|  |  |  | 93278803103 | AMBA_171_CS219_RSH_OPT_5G
|  |  |  | 93278802103 | AMBA_171_CS272_RSH_OPT_5G
|  |  |  | 93102720103 | AMBA_178_CS105_RSH_OPT_5G
|  |  |  | 93278800103 | AMBA_178_CS170_RSH_OPT_5G
|  |  |  | 93102719103 | AMBA_178_CS175_RSH_OPT_5G
|  |  |  | 93102718103 | AMBA_178_CS190_RSH_OPT_5G
|  |  |  | 93095797103 | AMBA_178_CS224_RSH_OPT_4G
|  |  |  | 93102717103 | AMBA_178_CS293_RSH_OPT_5G
|  |  |  | 93278799103 | AMBA_178_CS347_RSH_OPT_5G
|  |  |  | 93095796103 | AMBA_178_KS618_RSH_OPT_4G
|  |  |  | 93301699103 | AMBA_179_KS464_RSH_OPT_5G
|  |  |  | 93332709103 | AMBA_180_BS067_RSH_OPT_5G
|  |  |  | 93301700103 | AMBA_180_KS120_RSH_OPT_5G
|  |  |  | 93278798103 | AMBA_181_BS144_RSH_OPT_5G
|  |  |  | 93278797103 | AMBA_183_KS326_RSH_OPT_5G
|  |  |  | 93278796103 | AMBA_187_KS189_RSH_OPT_5G
|  |  |  | 91375700103 | AMBA_187_KS198_RSH_OPT
|  |  |  | 93278795103 | AMBA_188_BS097_RSH_OPT_5G
|  |  |  | 93278794103 | AMBA_190_KS203_RSH_OPT_5G
|  |  |  | 93278793103 | AMBA_194_BS102_RSH_OPT_5G
|  |  |  | 93278792103 | AMBA_194_BS176_RSH_OPT_5G
|  |  |  | 93278791103 | AMBA_194_BS372_RSH_OPT_5G
|  |  |  | 93278789103 | AMBA_196_KS111_RSH_OPT_5G
|  |  |  | 93278790103 | AMBA_196_KS184_RSH_OPT_5G
|  |  |  | 93278788103 | AMBA_196_KS325_RSH_OPT_5G
|  |  |  | 93277704103 | AMBA_196_KS607_RSH_OPT_5G
|  |  |  | 93278787103 | AMBA_198_BS081_RSH_OPT_5G
|  |  |  | 93278786103 | AMBA_199_BS069_RSH_OPT_5G
|  |  |  | 93278785103 | AMBA_199_BS093_RSH_OPT_5G
|  |  |  | 93278784103 | AMBA_199_BS094_RSH_OPT_5G
|  |  |  | 93278782103 | AMBA_199_BS194_RSH_OPT_5G
|  |  |  | 93278783103 | AMBA_199_BS195_RSH_OPT_5G
|  |  |  | 93278781103 | AMBA_200_LP048_RSH_OPT_5G
|  |  |  | 93331698103 | AMBA_202_LP061_RSH_OPT_5G
|  |  |  | 93331701103 | AMBA_203_LC058_RSH_OPT_5G
|  |  |  | 93278780103 | AMBA_204_LC014_RSH_OPT_5G
|  |  |  | 93278779103 | AMBA_205_LC046_RSH_OPT_5G
|  |  |  | 93278778103 | AMBA_207_LC021_RSH_OPT_5G
|  |  |  | 93278777103 | AMBA_207_LC031_RSH_OPT_5G
|  |  |  | 93278776103 | AMBA_207_LC033_RSH_OPT_5G
|  |  |  | 93278775103 | AMBA_207_LC034_RSH_OPT_5G
|  |  |  | 93331705103 | AMBA_207_LC038_RSH_OPT_5G
|  |  |  | 93331704103 | AMBA_207_LC039_RSH_OPT_5G
|  |  |  | 93331703103 | AMBA_207_LC052_RSH_OPT_5G
|  |  |  | 93331700103 | AMBA_209_LP031_RSH_OPT_5G
|  |  |  | 93278774103 | AMBA_209_LP127_RSH_OPT_5G
|  |  |  | 93331706103 | AMBA_211_LC026_RSH_OPT_5G
|  |  |  | 93331702103 | AMBA_211_LC053_RSH_OPT_5G
|  |  |  | 93278773103 | AMBA_211_LC055_RSH_OPT_5G
|  |  |  | 93331699103 | AMBA_215_LP045_RSH_OPT_5G
|  |  |  | 93278772103 | AMBA_220_BN511_RSH_OPT_5G
|  |  |  | 93278771103 | AMBA_227_KS192_RSH_OPT_5G
|  |  |  | 91375699103 | AMBA_227_KS231_RSH_OPT
|  |  |  | 93278770103 | AMBA_227_KS286_RSH_OPT_5G
|  |  |  | 91375698103 | AMBA_227_KS482_RSH_OPT
|  |  |  | 93278769103 | AMBA_228_KS282_RSH_OPT_5G
|  |  |  | 93332708103 | AMBA_229_BS080_RSH_OPT_5G
|  |  |  | 93332707103 | AMBA_229_BS114_RSH_OPT_5G
|  |  |  | 93332706103 | AMBA_229_BS230_RSH_OPT_5G
|  |  |  | 93332705103 | AMBA_229_BS233_RSH_OPT_5G
|  |  |  | 93331697103 | AMBA_239_LP109_RSH_OPT_5G
|  |  |  | 93332710103 | AMBA_24_BN078_RSH_OPT_5G
|  |  |  | 93278768103 | AMBA_24_BN149_RSH_OPT_5G
|  |  |  | 93277703103 | AMBA_24_BN276_RSH_OPT_5G
|  |  |  | 93278767103 | AMBA_253_BN095_RSH_OPT_5G
|  |  |  | 93301701103 | AMBA_254_KN104_RSH_OPT_5G
|  |  |  | 91375703103 | AMBA_31_BO162_RSH_OPT
|  |  |  | 91375702103 | AMBA_36_BO363_RSH_OPT
|  |  |  | 93278765103 | AMBA_56_BN147_RSH_OPT_5G
|  |  |  | 93278764103 | AMBA_56_BN484_RSH_OPT_5G
|  |  |  | 93278766103 | AMBA_56_BN489_RSH_OPT_5G
|  |  |  | 93278763103 | AMBA_58_KO032_RSH_OPT_5G
|  |  |  | 93278762103 | AMBA_63_BN092_RSH_OPT_5G
|  |  |  | 93278761103 | AMBA_63_BN118_RSH_OPT_5G
|  |  |  | 93278760103 | AMBA_63_BN148_RSH_OPT_5G
|  |  |  | 93278759103 | AMBA_64_BN263_RSH_OPT_5G
|  |  |  | 93278758103 | AMBA_67_BN231_RSH_OPT_5G
|  |  |  | 93278757103 | AMBA_78_KO197_RSH_OPT_5G
|  |  |  | 93278756103 | AMBA_80_BS287_RSH_OPT_5G
|  |  |  | 93278755103 | AMBA_82_BS090_RSH_OPT_5G
|  |  |  | 93278752103 | AMBA_82_BS117_RSH_OPT_5G
|  |  |  | 93278754103 | AMBA_82_BS158_RSH_OPT_5G
|  |  |  | 93278753103 | AMBA_82_BS159_RSH_OPT_5G
|  |  |  | 93278750103 | AMBA_83_BS110_RSH_OPT_5G
|  |  |  | 93278751103 | AMBA_83_BS304_RSH_OPT_5G
|  |  |  | 93278749103 | AMBA_86_KO037_RSH_OPT_5G
|  |  |  | 93278748103 | AMBA_86_KO193_RSH_OPT_5G
|  |  |  | 93277702103 | AMBA_86_KS472_RSH_OPT_5G
|  |  |  | 93277700103 | AMBA_90_KS116_RSH_OPT_5G
|  |  |  | 93277701103 | AMBA_90_KS300_RSH_OPT_5G
|  |  |  | 94131700103 | AMBA_91_BS134_RSH_OPT_5G
|  |  |  | 93278747103 | AMBA_92_BS196_RSH_OPT_5G
|  |  |  | 94131702103 | AMBA_97_CS033_RSH_OPT_5G
|  |  |  | 93095773103 | AMBA_99_CS119_RSH_OPT_4G
|  |  |  | 93095772103 | AMBA_99_CS141_RSH_OPT_4G
|  |  |  | 93095771103 | AMBA_99_CS144_RSH_OPT_4G
|  |  |  | 93095770103 | AMBA_99_CS163_RSH_OPT_4G
|  |  |  | 93095769103 | AMBA_99_CS279_RSH_OPT_4G
|  |  |  | 93095768103 | AMBA_99_CS280_RSH_OPT_4G
|  |  |  | 93095767103 | AMBA_99_CS302_RSH_OPT_4G
|  |  |  | 92190698103 | AMBA_BC031_Swap_MVS
|  |  |  | 92190697103 | AMBA_BC075_Swap_MVS
|  |  |  | 92146713103 | AMBA_BC079_Swap_MVS
|  |  |  | 92146716103 | AMBA_BC116_Swap_MVS
|  |  |  | 92146712103 | AMBA_BC754_Swap_MVS
|  |  |  | 92029698103 | AMBA_BH039_Swap_MVS
|  |  |  | 92108705103 | AMBA_BH041_Swap_MVS
|  |  |  | 92108704103 | AMBA_BH042_Swap_MVS
|  |  |  | 92029699103 | AMBA_BH046_Swap_MVS
|  |  |  | 92029700103 | AMBA_BH051_Swap_MVS
|  |  |  | 92029701103 | AMBA_BH071_Swap_MVS
|  |  |  | 92028702103 | AMBA_BH144_Swap_MVS
|  |  |  | 92169719103 | AMBA_BH311_Swap_MVS
|  |  |  | 91993714103 | AMBA_BN006_Swap_MVS
|  |  |  | 92002699103 | AMBA_BN024_Swap_MVS
|  |  |  | 92002700103 | AMBA_BN026_Swap_MVS
|  |  |  | 92001702103 | AMBA_BN079_Swap_MVS
|  |  |  | 92002706103 | AMBA_BN091_Swap_MVS
|  |  |  | 92004713103 | AMBA_BN099_Swap_MVS
|  |  |  | 92004714103 | AMBA_BN108_Swap_MVS
|  |  |  | 92004715103 | AMBA_BN115_Swap_MVS
|  |  |  | 92001697103 | AMBA_BN118_Swap_MVS
|  |  |  | 92004716103 | AMBA_BN123_Swap_MVS
|  |  |  | 92002701103 | AMBA_BN147_Swap_MVS
|  |  |  | 91993715103 | AMBA_BN148_Swap_MVS
|  |  |  | 91993725103 | AMBA_BN166_Swap_MVS
|  |  |  | 91993726103 | AMBA_BN167_Swap_MVS
|  |  |  | 91993727103 | AMBA_BN170_Swap_MVS
|  |  |  | 91993728103 | AMBA_BN182_Swap_MVS
|  |  |  | 92001703103 | AMBA_BN188_Swap_MVS
|  |  |  | 92001704103 | AMBA_BN192_Swap_MVS
|  |  |  | 92003697103 | AMBA_BN210_Swap_MVS
|  |  |  | 91993716103 | AMBA_BN214_Swap_MVS
|  |  |  | 92001707103 | AMBA_BN226_Swap_MVS
|  |  |  | 92001708103 | AMBA_BN231_Swap_MVS
|  |  |  | 92001698103 | AMBA_BN249_Swap_MVS
|  |  |  | 92001705103 | AMBA_BN250_Swap_MVS
|  |  |  | 95916698103 | AMBA_BN268_Swap_MVS
|  |  |  | 92001699103 | AMBA_BN332_Swap_MVS
|  |  |  | 92003698103 | AMBA_BN402_Swap_MVS
|  |  |  | 91993717103 | AMBA_BN403_Swap_MVS
|  |  |  | 95916697103 | AMBA_BN431_Swap_MVS
|  |  |  | 91993718103 | AMBA_BN484_Swap_MVS
|  |  |  | 92003699103 | AMBA_BN489_Swap_MVS
|  |  |  | 91993719103 | AMBA_BN880_Swap_MVS
|  |  |  | 92001706103 | AMBA_BO030_Swap_MVS
|  |  |  | 92001709103 | AMBA_BO097_Swap_MVS
|  |  |  | 92146714103 | AMBA_BO099_Swap_MVS
|  |  |  | 91993729103 | AMBA_BO102_Swap_MVS
|  |  |  | 92001700103 | AMBA_BO106_Swap_MVS
|  |  |  | 92004697103 | AMBA_BO107_Swap_MVS
|  |  |  | 92001701103 | AMBA_BO110_Swap_MVS
|  |  |  | 91993705103 | AMBA_BO113_Swap_MVS
|  |  |  | 91993730103 | AMBA_BO114_Swap_MVS
|  |  |  | 92190700103 | AMBA_BO120_Swap_MVS
|  |  |  | 91993731103 | AMBA_BO128_Swap_MVS
|  |  |  | 92003700103 | AMBA_BO140_Swap_MVS
|  |  |  | 91993732103 | AMBA_BO147_Swap_MVS
|  |  |  | 92004698103 | AMBA_BO183_Swap_MVS
|  |  |  | 91993733103 | AMBA_BO190_Swap_MVS
|  |  |  | 91993734103 | AMBA_BO202_Swap_MVS
|  |  |  | 92001710103 | AMBA_BO204_Swap_MVS
|  |  |  | 92190699103 | AMBA_BO225_Swap_MVS
|  |  |  | 92004699103 | AMBA_BO249_Swap_MVS
|  |  |  | 92006697103 | AMBA_BO268_Swap_MVS
|  |  |  | 92003701103 | AMBA_BO296_Swap_MVS
|  |  |  | 92005706103 | AMBA_BO324_Swap_MVS
|  |  |  | 92001717103 | AMBA_BO373_Swap_MVS
|  |  |  | 92001711103 | AMBA_BO378_Swap_MVS
|  |  |  | 92005697103 | AMBA_BO435_Swap_MVS
|  |  |  | 91993706103 | AMBA_BO471_Swap_MVS
|  |  |  | 92005698103 | AMBA_BO803_Swap_MVS
|  |  |  | 92005707103 | AMBA_BO806_Swap_MVS
|  |  |  | 92004700103 | AMBA_BO827_Swap_MVS
|  |  |  | 92004701103 | AMBA_BS006_Swap_MVS
|  |  |  | 91993707103 | AMBA_BS009_Swap_MVS
|  |  |  | 91993710103 | AMBA_BS050_Swap_MVS
|  |  |  | 92001718103 | AMBA_BS059_Swap_MVS
|  |  |  | 91993708103 | AMBA_BS061_Swap_MVS
|  |  |  | 91993709103 | AMBA_BS063_Swap_MVS
|  |  |  | 92001719103 | AMBA_BS065_Swap_MVS
|  |  |  | 92002702103 | AMBA_BS077_Swap_MVS
|  |  |  | 92001720103 | AMBA_BS087_Swap_MVS
|  |  |  | 92006698103 | AMBA_BS088_Swap_MVS
|  |  |  | 92001721103 | AMBA_BS105_Swap_MVS
|  |  |  | 92005699103 | AMBA_BS107_Swap_MVS
|  |  |  | 92001722103 | AMBA_BS124_Swap_MVS
|  |  |  | 92005700103 | AMBA_BS125_Swap_MVS
|  |  |  | 92002697103 | AMBA_BS140_Swap_MVS
|  |  |  | 92001723103 | AMBA_BS210_Swap_MVS
|  |  |  | 92002698103 | AMBA_BS211_Swap_MVS
|  |  |  | 92146715103 | AMBA_BS216_Swap_MVS
|  |  |  | 91993711103 | AMBA_BS241_Swap_MVS
|  |  |  | 91993712103 | AMBA_BS246_Swap_MVS
|  |  |  | 91993713103 | AMBA_BS248_Swap_MVS
|  |  |  | 92002703103 | AMBA_BS257_Swap_MVS
|  |  |  | 92002704103 | AMBA_BS263_Swap_MVS
|  |  |  | 92006699103 | AMBA_BS298_Swap_MVS
|  |  |  | 92002705103 | AMBA_BS302_Swap_MVS
|  |  |  | 92136702103 | AMBA_BS308_Swap_MVS
|  |  |  | 92001724103 | AMBA_BS314_Swap_MVS
|  |  |  | 92005701103 | AMBA_BS367_Swap_MVS
|  |  |  | 91991702103 | AMBA_CN025_Swap_MVS
|  |  |  | 92028700103 | AMBA_CN185_Swap_MVS
|  |  |  | 92136701103 | AMBA_CN186_Swap_MVS
|  |  |  | 92028701103 | AMBA_CN188_Swap_MVS
|  |  |  | 91991698103 | AMBA_CS001_Swap_MVS
|  |  |  | 92144697103 | AMBA_CS014_Swap_MVS
|  |  |  | 92028699103 | AMBA_CS026_Swap_MVS
|  |  |  | 92169716103 | AMBA_CS090_Swap_MVS
|  |  |  | 92108706103 | AMBA_CS098_Swap_MVS
|  |  |  | 92169718103 | AMBA_CS102_Swap_MVS
|  |  |  | 92169717103 | AMBA_CS107_Swap_MVS
|  |  |  | 91991699103 | AMBA_CS119_Swap_MVS
|  |  |  | 92029697103 | AMBA_CS143_Swap_MVS
|  |  |  | 91991700103 | AMBA_CS175_Swap_MVS
|  |  |  | 91991701103 | AMBA_CS352_Swap_MVS
|  |  |  | 91993721103 | AMBA_KN049_Swap_MVS
|  |  |  | 92004705103 | AMBA_KN060_Swap_MVS
|  |  |  | 92712697103 | AMBA_KN251_Swap_MVS
|  |  |  | 91989700103 | AMBA_KN255_Swap_MVS
|  |  |  | 91989713103 | AMBA_KN350_Swap_MVS
|  |  |  | 92004706103 | AMBA_KO004_Swap_MVS
|  |  |  | 91993722103 | AMBA_KO008_Swap_MVS
|  |  |  | 92006700103 | AMBA_KO010_Swap_MVS
|  |  |  | 91989701103 | AMBA_KO023_Swap_MVS
|  |  |  | 91989702103 | AMBA_KO041_Swap_MVS
|  |  |  | 91989714103 | AMBA_KO042_Swap_MVS
|  |  |  | 91993723103 | AMBA_KO238_Swap_MVS
|  |  |  | 91993724103 | AMBA_KO240_Swap_MVS
|  |  |  | 92001725103 | AMBA_KS008_Swap_MVS
|  |  |  | 92001726103 | AMBA_KS009_Swap_MVS
|  |  |  | 92005708103 | AMBA_KS018_Swap_MVS
|  |  |  | 92001727103 | AMBA_KS023_Swap_MVS
|  |  |  | 92001728103 | AMBA_KS037_Swap_MVS
|  |  |  | 92001712103 | AMBA_KS065_Swap_MVS
|  |  |  | 92005709103 | AMBA_KS067_Swap_MVS
|  |  |  | 92001713103 | AMBA_KS090_Swap_MVS
|  |  |  | 92001729103 | AMBA_KS105_Swap_MVS
|  |  |  | 91989704103 | AMBA_KS107_Swap_MVS
|  |  |  | 92006701103 | AMBA_KS108_Swap_MVS
|  |  |  | 92004702103 | AMBA_KS111_Swap_MVS
|  |  |  | 92001730103 | AMBA_KS134_Swap_MVS
|  |  |  | 92001731103 | AMBA_KS142_Swap_MVS
|  |  |  | 91989703103 | AMBA_KS143_Swap_MVS
|  |  |  | 91989715103 | AMBA_KS147_Swap_MVS
|  |  |  | 92005702103 | AMBA_KS151_Swap_MVS
|  |  |  | 92005710103 | AMBA_KS201_Swap_MVS
|  |  |  | 92004703103 | AMBA_KS202_Swap_MVS
|  |  |  | 91989705103 | AMBA_KS342_Swap_MVS
|  |  |  | 92005704103 | AMBA_KS374_Swap_MVS
|  |  |  | 92136700103 | AMBA_KS378_Swap_MVS
|  |  |  | 92005711103 | AMBA_KS401_Swap_MVS
|  |  |  | 92005705103 | AMBA_KS425_Swap_MVS
|  |  |  | 91989706103 | AMBA_KS446_Swap_MVS
|  |  |  | 91989707103 | AMBA_KS494_Swap_MVS
|  |  |  | 92004707103 | AMBA_KS622_Swap_MVS
|  |  |  | 91989716103 | AMBA_KS623_Swap_MVS
|  |  |  | 92004708103 | AMBA_KS624_Swap_MVS
|  |  |  | 92004709103 | AMBA_KS626_Swap_MVS
|  |  |  | 91989717103 | AMBA_KS627_Swap_MVS
|  |  |  | 92004710103 | AMBA_KS628_Swap_MVS
|  |  |  | 91989718103 | AMBA_KS629_Swap_MVS
|  |  |  | 92004711103 | AMBA_KS630_Swap_MVS
|  |  |  | 92004712103 | AMBA_KS631_Swap_MVS
|  |  |  | 91993720103 | AMBA_KS632_Swap_MVS
|  |  |  | 91989708103 | AMBA_KS633_Swap_MVS
|  |  |  | 92001714103 | AMBA_KS634_Swap_MVS
|  |  |  | 91989709103 | AMBA_KS635_Swap_MVS
|  |  |  | 91989710103 | AMBA_KS637_Swap_MVS
|  |  |  | 91989711103 | AMBA_KS639_Swap_MVS
|  |  |  | 92001715103 | AMBA_KS644_Swap_MVS
|  |  |  | 92001716103 | AMBA_KS701_Swap_MVS
|  |  |  | 92136698103 | AMBA_KS702_Swap_MVS
|  |  |  | 91989712103 | AMBA_KS707_Swap_MVS
|  |  |  | 91989699103 | AMBA_KS711_Swap_MVS
|  |  |  | 92004704103 | AMBA_KS908_Swap_MVS
|  |  |  | 92672697103 | AMBA_LP037_Swap_MVS
|  |  |  | 93461704103 | AllRegion_ClusterOPT_Feb_TLF
|  |  |  | 91673697103 | AllRegion_ClusterOPT_Jan
|  |  |  | 95711719103 | AllRegion_ClusterOPT_TLF_V2
|  |  |  | 92678697103 | BA_ARBA6402_FARM_Etapa1_MVS
|  |  |  | 91738714103 | BA_BB092_Swap_MVS
|  |  |  | 91738713103 | BA_BB310_Swap_MVS
|  |  |  | 92223698103 | MEDI_A33-O003_Mod_TA
|  |  |  | 92223697103 | MEDI_A33-O005_Mod_TA
|  |  |  | 92221706103 | MEDI_A33-O013_Mod_TA
|  |  |  | 92126699103 | MEDI_A33-O054_Mod_TA
|  |  |  | 92126698103 | MEDI_A33-O058_Mod_TA
|  |  |  | 92221705103 | MEDI_A33-O061_Mod_TA
|  |  |  | 92221704103 | MEDI_A33-O063_Mod_TA
|  |  |  | 92221703103 | MEDI_A33-O065_Mod_TA
|  |  |  | 92221702103 | MEDI_A33-O066_Mod_TA
|  |  |  | 92126697103 | MEDI_A33-O067_Mod_TA
|  |  |  | 92220706103 | MEDI_A33-O068_Mod_TA
|  |  |  | 92220705103 | MEDI_A33-O069_Mod_TA
|  |  |  | 92125701103 | MEDI_A33-O071_Mod_TA
|  |  |  | 92125700103 | MEDI_A33-O075_Mod_TA
|  |  |  | 92220704103 | MEDI_A33-O079_Mod_TA
|  |  |  | 92220703103 | MEDI_A33-O084_Mod_TA
|  |  |  | 92126700103 | MEDI_A33-O085_Mod_TA
|  |  |  | 92123701103 | MEDI_A33-O118_Mod_TA
|  |  |  | 92220702103 | MEDI_A33-O120_Mod_TA
|  |  |  | 92222701103 | MEDI_A33-O131_Mod_TA
|  |  |  | 92123700103 | MEDI_A33-O133_Mod_TA
|  |  |  | 92125699103 | MEDI_A33-O149_Mod_TA
|  |  |  | 92222700103 | MEDI_A33-O153_Mod_TA
|  |  |  | 92222699103 | MEDI_A33-O157_Mod_TA
|  |  |  | 92222698103 | MEDI_A33-O158_Mod_TA
|  |  |  | 92222697103 | MEDI_A33-O162_Mod_TA
|  |  |  | 92221701103 | MEDI_A33-O165_Mod_TA
|  |  |  | 92125698103 | MEDI_A33-O177_Mod_TA
|  |  |  | 92221700103 | MEDI_A33-O194_Mod_TA
|  |  |  | 92125697103 | MEDI_A33-O195_Mod_TA
|  |  |  | 92221699103 | MEDI_A33-O246_Mod_TA
|  |  |  | 92221698103 | MEDI_A33-O249_Mod_TA
|  |  |  | 92221697103 | MEDI_A33-O316_Mod_TA
|  |  |  | 92220701103 | MEDI_A33-O319_Mod_TA
|  |  |  | 92220700103 | MEDI_A33-O320_Mod_TA
|  |  |  | 92220699103 | MEDI_A33-O359_Mod_TA
|  |  |  | 92220698103 | MEDI_A33-O369_Mod_TA
|  |  |  | 92220697103 | MEDI_A33-O380_Mod_TA
|  |  |  | 92219701103 | MEDI_A33-O382_Mod_TA
|  |  |  | 92219700103 | MEDI_A33-O383_Mod_TA
|  |  |  | 92045708103 | MEDI_A33-O384_Mod_TA
|  |  |  | 92219699103 | MEDI_A33-O386_Mod_TA
|  |  |  | 92045707103 | MEDI_A33-O419_Mod_TA
|  |  |  | 92045706103 | MEDI_A33-O655_Mod_TA
|  |  |  | 96261697103 | MEDI_A33-O734_Mod_TA
|  |  |  | 92123699103 | MEDI_A35-D001_Mod_TA
|  |  |  | 92123698103 | MEDI_A35-D002_Mod_TA
|  |  |  | 92219698103 | MEDI_A35-D011_Mod_TA
|  |  |  | 92123697103 | MEDI_A35-D037_Mod_TA
|  |  |  | 92122701103 | MEDI_A35-D038_Mod_TA
|  |  |  | 92122700103 | MEDI_A35-D039_Mod_TA
|  |  |  | 92045705103 | MEDI_A35-D041_Mod_TA
|  |  |  | 92045704103 | MEDI_A35-D042_Mod_TA
|  |  |  | 92111761103 | MEDI_A35-D043_Mod_TA
|  |  |  | 92111760103 | MEDI_A35-D044_Mod_TA
|  |  |  | 92122699103 | MEDI_A35-D056_Mod_TA
|  |  |  | 92122698103 | MEDI_A35-D073_Mod_TA
|  |  |  | 92122697103 | MEDI_A35-D074_Mod_TA
|  |  |  | 92219697103 | MEDI_A35-D126_Mod_TA
|  |  |  | 92111758103 | MEDI_A37-F039_Mod_TA
|  |  |  | 92111757103 | MEDI_A37-F040_Mod_TA
|  |  |  | 98719702103 | MEDI_MC345_SWAP_MVS
|  |  |  | 92711697103 | MZA_ARME0060_FARM_Etapa1_MVS
|  |  |  | 94371698103 | MZ_ARME0006_FARM_Dismantle_MVS
|  |  |  | 96195697103 | MZ_ARME0009_FARM_Dismantle_MVS
|  |  |  | 96193697103 | MZ_ARME0014_FARM_Dismantle_MVS
|  |  |  | 96195699103 | MZ_ARME0061_FARM_Dismantle_MVS
|  |  |  | 96193699103 | MZ_ARME0062_FARM_Dismantle_MVS
|  |  |  | 96195698103 | MZ_ARME0099_FARM_Dismantle_MVS
|  |  |  | 94370699103 | MZ_ARME0115_FARM_Dismantle_MVS
|  |  |  | 94370700103 | MZ_ARME0702_FARM_Dismantle_MVS
|  |  |  | 94370701103 | MZ_ARME0817_FARM_Dismantle_MVS
|  |  |  | 94371701103 | MZ_ARME0838_FARM_Dismantle_MVS
|  |  |  | 94370697103 | MZ_ARME0840_FARM_Dismantle_MVS
|  |  |  | 94371700103 | MZ_ARME0841_FARM_Dismantle_MVS
|  |  |  | 96193698103 | MZ_ARME0842_FARM_Dismantle_MVS
|  |  |  | 96193700103 | MZ_ARME0843_FARM_Dismantle_MVS
|  |  |  | 94370698103 | MZ_ARME0849_FARM_Dismantle_MVS
|  |  |  | 94371699103 | MZ_ARME0864_FARM_Dismantle_MVS
|  |  |  | 94371697103 | MZ_ARME1042_FARM_Dismantle_MVS
|  |  |  | 92711698103 | NQ_ARNQ0017_FARM_Etapa2_MVS
|  |  |  | 91215730103 | NQ_QC048_Swap_MVS
|  |  |  | 91215729103 | NQ_QC053_Swap_MVS
|  |  |  | 91215728103 | NQ_QC349_Swap_MVS
|  |  |  | 91215727103 | NQ_QE029_Swap_MVS
|  |  |  | 99074698103 | NQ_QS003_SSV_MVS
|  |  |  | 91215726103 | NQ_QS003_Swap_MVS
|  |  |  | 91215725103 | RN_RS027_Swap_MVS
|  |  |  | 99074697103 | RN_RS033_SSV_MVS
|  |  |  | 91215724103 | RN_RS033_Swap_MVS
|  |  |  | 91215723103 | RN_RS035_Swap_MVS
|  |  |  | 91215722103 | RN_RS036_Swap_MVS
|  |  |  | 94197703103 | SUR_123_QE005_RSH_OPT_5G
|  |  |  | 93099734103 | SUR_128_QE004_RSH_OPT_4G
|  |  |  | 94273698103 | SUR_128_QE004_RSH_OPT_5G
|  |  |  | 93099732103 | SUR_128_QE029_RSH_OPT_4G
|  |  |  | 93099733103 | SUR_128_QE053_RSH_OPT_4G
|  |  |  | 94197701103 | SUR_130_QC044_RSH_OPT_5G
|  |  |  | 94197702103 | SUR_130_QC054_RSH_OPT_5G
|  |  |  | 93099730103 | SUR_131_QC001_RSH_OPT_4G
|  |  |  | 93099729103 | SUR_131_QC003_RSH_OPT_4G
|  |  |  | 93099728103 | SUR_131_QC058_RSH_OPT_4G
|  |  |  | 93099727103 | SUR_131_QC074_RSH_OPT_4G
|  |  |  | 93099731103 | SUR_131_QC105_RSH_OPT_4G
|  |  |  | 93099725103 | SUR_131_QC149_RSH_OPT_4G
|  |  |  | 93099726103 | SUR_131_QC346_RSH_OPT_4G
|  |  |  | 96307709103 | SUR_132_A30-Q092_RSH_OPT_4G
|  |  |  | 96307707103 | SUR_132_A30-Q255_RSH_OPT_4G
|  |  |  | 96307706103 | SUR_132_A30-Q257_RSH_OPT_4G
|  |  |  | 96307705103 | SUR_132_A30-Q258_RSH_OPT_4G
|  |  |  | 96307704103 | SUR_132_A30-Q265_RSH_OPT_4G
|  |  |  | 96307703103 | SUR_132_A30-Q266_RSH_OPT_4G
|  |  |  | 96307702103 | SUR_132_A30-Q267_RSH_OPT_4G
|  |  |  | 96307701103 | SUR_132_A30-Q268_RSH_OPT_4G
|  |  |  | 93099724103 | SUR_132_QC002_RSH_OPT_4G
|  |  |  | 93099723103 | SUR_132_QC005_RSH_OPT_4G
|  |  |  | 93099722103 | SUR_132_QC021_RSH_OPT_4G
|  |  |  | 93099721103 | SUR_132_QC024_RSH_OPT_4G
|  |  |  | 93099717103 | SUR_132_QC045_RSH_OPT_4G
|  |  |  | 93099716103 | SUR_132_QC048_RSH_OPT_4G
|  |  |  | 96307710103 | SUR_132_QC050_RSH_OPT
|  |  |  | 93099720103 | SUR_132_QC050_RSH_OPT_4G
|  |  |  | 94197700103 | SUR_132_QC050_RSH_OPT_5G
|  |  |  | 93099715103 | SUR_132_QC051_RSH_OPT_4G
|  |  |  | 93099719103 | SUR_132_QC059_RSH_OPT_4G
|  |  |  | 93099718103 | SUR_132_QC348_RSH_OPT_4G
|  |  |  | 93099714103 | SUR_133_QC007_RSH_OPT_4G
|  |  |  | 93099713103 | SUR_133_QC014_RSH_OPT_4G
|  |  |  | 93099707103 | SUR_133_QC052_RSH_OPT_4G
|  |  |  | 93099712103 | SUR_133_QC055_RSH_OPT_4G
|  |  |  | 93099711103 | SUR_133_QC056_RSH_OPT_4G
|  |  |  | 93099710103 | SUR_133_QC099_RSH_OPT_4G
|  |  |  | 93099709103 | SUR_133_QC354_RSH_OPT_4G
|  |  |  | 94197704103 | SUR_133_QC354_RSH_OPT_5G
|  |  |  | 93099708103 | SUR_133_QCM39_RSH_OPT_4G
|  |  |  | 91341697103 | SUR_179_BM116_OPT
|  |  |  | 91327708103 | SUR_179_BM116_RSH_OPT_5G
|  |  |  | 93332724103 | SUR_184_BM031_RSH_OPT_5G
|  |  |  | 94275698103 | SUR_184_BM102_RSH_OPT_5G
|  |  |  | 93332723103 | SUR_185_BM078_RSH_OPT_5G
|  |  |  | 93332721103 | SUR_185_BM306_RSH_OPT_5G
|  |  |  | 93332718103 | SUR_185_BM379_RSH_OPT_5G
|  |  |  | 91375704103 | SUR_186_BM305_RSH_OPT_5G
|  |  |  | 93278746103 | SUR_187_BM035_RSH_OPT_5G
|  |  |  | 91340697103 | SUR_187_BM051_RSH_OPT_5G
|  |  |  | 93278745103 | SUR_187_BM301_RSH_OPT_5G
|  |  |  | 91327703103 | SUR_188_BM057_RSH_OPT_5G
|  |  |  | 91327705103 | SUR_188_BM303_RSH_OPT_5G
|  |  |  | 91327706103 | SUR_188_BM357_RSH_OPT_5G
|  |  |  | 93278744103 | SUR_189_BM063_RSH_OPT_5G
|  |  |  | 94275697103 | SUR_189_BM086_RSH_OPT_5G
|  |  |  | 93278743103 | SUR_189_BM304_RSH_OPT_5G
|  |  |  | 93278742103 | SUR_189_BM522_RSH_OPT_5G
|  |  |  | 91327709103 | SUR_190_BM050_RSH_OPT_5G
|  |  |  | 93278741103 | SUR_190_BM090_RSH_OPT_5G
|  |  |  | 93278740103 | SUR_190_BM310_RSH_OPT_5G
|  |  |  | 93278739103 | SUR_191_BM002_RSH_OPT_5G
|  |  |  | 93332703103 | SUR_199_BM129_RSH_OPT_5G
|  |  |  | 93332702103 | SUR_199_BM316_RSH_OPT_5G
|  |  |  | 93278738103 | SUR_199_BM329_RSH_OPT_5G
|  |  |  | 93332701103 | SUR_199_BM640_RSH_OPT_5G
|  |  |  | 93095735103 | SUR_1_BB188_RSH_OPT_4G
|  |  |  | 93095734103 | SUR_1_BB308_RSH_OPT_4G
|  |  |  | 93095733103 | SUR_1_BB310_RSH_OPT_4G
|  |  |  | 93332722103 | SUR_200_BM091_RSH_OPT_5G
|  |  |  | 93332713103 | SUR_201_BM838_RSH_OPT_5G
|  |  |  | 93332712103 | SUR_201_BM839_RSH_OPT_5G
|  |  |  | 93332720103 | SUR_205_BM335_RSH_OPT_5G
|  |  |  | 93332716103 | SUR_205_BM390_RSH_OPT_5G
|  |  |  | 93332715103 | SUR_205_BM781_RSH_OPT_5G
|  |  |  | 93332719103 | SUR_206_BM343_RSH_OPT_5G
|  |  |  | 95676697103 | SUR_223_A41-B176_OPT
|  |  |  | 93095732103 | SUR_2_BB003_RSH_OPT_4G
|  |  |  | 93099751103 | SUR_2_BB004_RSH_OPT_4G
|  |  |  | 94273703103 | SUR_2_BB004_RSH_OPT_5G
|  |  |  | 93099750103 | SUR_2_BB011_RSH_OPT_4G
|  |  |  | 93099749103 | SUR_2_BB076_RSH_OPT_4G
|  |  |  | 94273702103 | SUR_2_BB076_RSH_OPT_5G
|  |  |  | 93099748103 | SUR_2_BB081_RSH_OPT_4G
|  |  |  | 94273701103 | SUR_2_BB081_RSH_OPT_5G
|  |  |  | 93099747103 | SUR_2_BB185_RSH_OPT_4G
|  |  |  | 93099746103 | SUR_2_BB378_RSH_OPT_4G
|  |  |  | 94273700103 | SUR_2_BB378_RSH_OPT_5G
|  |  |  | 96307700103 | SUR_309_A43-B004_RSH_OPT
|  |  |  | 96307699103 | SUR_309_A43-B011_RSH_OPT
|  |  |  | 96307708103 | SUR_309_A43-B237_RSH_OPT
|  |  |  | 96307698103 | SUR_309_A43-B604_RSH_OPT
|  |  |  | 96307697103 | SUR_309_A43-B811_RSH_OPT
|  |  |  | 93278737103 | SUR_329_BM141_RSH_OPT_5G
|  |  |  | 93332717103 | SUR_330_BM380_RSH_OPT_5G
|  |  |  | 93332714103 | SUR_330_BM811_RSH_OPT_5G
|  |  |  | 93278736103 | SUR_330_BM831_RSH_OPT_5G
|  |  |  | 93332711103 | SUR_330_BM840_RSH_OPT_5G
|  |  |  | 91327704103 | SUR_334_BM018_RSH_OPT_5G
|  |  |  | 93099742103 | SUR_4_BB071_RSH_OPT_4G
|  |  |  | 93099741103 | SUR_4_BB075_RSH_OPT_4G
|  |  |  | 93099740103 | SUR_4_BB077_RSH_OPT_4G
|  |  |  | 94273699103 | SUR_4_BB077_RSH_OPT_5G
|  |  |  | 93099745103 | SUR_4_BB092_RSH_OPT_4G
|  |  |  | 93099739103 | SUR_4_BB109_RSH_OPT_4G
|  |  |  | 93099744103 | SUR_4_BB122_RSH_OPT_4G
|  |  |  | 93099738103 | SUR_4_BB304_RSH_OPT_4G
|  |  |  | 93099743103 | SUR_4_BB475_RSH_OPT_4G
|  |  |  | 93278735103 | SUR_502_JC005_RSH_OPT_5G
|  |  |  | 93301702103 | SUR_502_JC053_RSH_OPT_5G
|  |  |  | 93278733103 | SUR_502_JC101_RSH_OPT_5G
|  |  |  | 93278734103 | SUR_502_JC341_RSH_OPT_5G
|  |  |  | 93278732103 | SUR_518_MC006_RSH_OPT_5G
|  |  |  | 93278729103 | SUR_518_MC010_RSH_OPT_5G
|  |  |  | 93278731103 | SUR_518_MC068_RSH_OPT_5G
|  |  |  | 93278730103 | SUR_518_MC073_RSH_OPT_5G
|  |  |  | 94158707103 | SUR_519_A33-O006_RSH_OPT_5G
|  |  |  | 93277699103 | SUR_519_MC024_RSH_OPT_5G
|  |  |  | 93278728103 | SUR_519_MC028_RSH_OPT_5G
|  |  |  | 93278727103 | SUR_519_MC037_RSH_OPT_5G
|  |  |  | 93301698103 | SUR_519_MC054_RSH_OPT_5G
|  |  |  | 93278724103 | SUR_519_MC126_RSH_OPT_5G
|  |  |  | 93278726103 | SUR_519_MC301_RSH_OPT_5G
|  |  |  | 93278725103 | SUR_519_MC303_RSH_OPT_5G
|  |  |  | 93278723103 | SUR_520_MC017_RSH_OPT_5G
|  |  |  | 93278722103 | SUR_520_MC033_RSH_OPT_5G
|  |  |  | 93278721103 | SUR_520_MC051_RSH_OPT_5G
|  |  |  | 93278720103 | SUR_521_MC002_RSH_OPT_5G
|  |  |  | 93278719103 | SUR_521_MC005_RSH_OPT_5G
|  |  |  | 93278718103 | SUR_521_MC025_RSH_OPT_5G
|  |  |  | 93278717103 | SUR_521_MC066_RSH_OPT_5G
|  |  |  | 93278716103 | SUR_521_MC098_RSH_OPT_5G
|  |  |  | 93278715103 | SUR_521_MC147_RSH_OPT_5G
|  |  |  | 91336697103 | SUR_521_MC171_RSH_OPT_5G
|  |  |  | 93278714103 | SUR_521_MC333_RSH_OPT_5G
|  |  |  | 93278713103 | SUR_521_MC350_RSH_OPT_5G
|  |  |  | 93278712103 | SUR_522_MC039_RSH_OPT_5G
|  |  |  | 93278710103 | SUR_522_MC107_RSH_OPT_5G
|  |  |  | 93278709103 | SUR_522_MC307_RSH_OPT_5G
|  |  |  | 93278711103 | SUR_522_MC348_RSH_OPT_5G
|  |  |  | 91327702103 | SUR_523_MC093_RSH_OPT_5G
|  |  |  | 91327707103 | SUR_524_MC405_RSH_OPT_5G
|  |  |  | 91375697103 | SUR_526_MN007_RSH_OPT
|  |  |  | 93277698103 | SUR_529_MS010_RSH_OPT_5G
|  |  |  | 93278708103 | SUR_529_MS020_RSH_OPT_5G
|  |  |  | 93277697103 | SUR_529_MS025_RSH_OPT_5G
|  |  |  | 93278707103 | SUR_529_MS033_RSH_OPT_5G
|  |  |  | 93278706103 | SUR_530_MC316_RSH_OPT_5G
|  |  |  | 93278705103 | SUR_530_MC319_RSH_OPT_5G
|  |  |  | 93278704103 | SUR_534_MC036_RSH_OPT_5G
|  |  |  | 91338697103 | SUR_534_MC076_RSH_OPT_5G
|  |  |  | 93099737103 | SUR_5_BB058_RSH_OPT_4G
|  |  |  | 93099736103 | SUR_5_BB360_RSH_OPT_4G
|  |  |  | 93099735103 | SUR_5_BB389_RSH_OPT_4G
|  |  |  | 92208708103 | South_A24-V007_Mod_TA
|  |  |  | 92208707103 | South_A24-V012_Mod_TA
|  |  |  | 92217701103 | South_A26-U035_Mod_TA
|  |  |  | 92217700103 | South_A26-Z019_Mod_TA
|  |  |  | 92217699103 | South_A27-U002_Mod_TA
|  |  |  | 92217698103 | South_A27-U008_Mod_TA
|  |  |  | 92217697103 | South_A27-U026_Mod_TA
|  |  |  | 92210716103 | South_A27-U089_Mod_TA
|  |  |  | 92210715103 | South_A28-Q078_Mod_TA
|  |  |  | 92126701103 | South_A28-Q160_Mod_TA
|  |  |  | 92129699103 | South_A28-R051_Mod_TA
|  |  |  | 92124703103 | South_A30-Q001_Mod_TA
|  |  |  | 92210714103 | South_A30-Q003_Mod_TA
|  |  |  | 92124702103 | South_A30-Q041_Mod_TA
|  |  |  | 92209697103 | South_A30-Q048_Mod_TA
|  |  |  | 92105703103 | South_A30-Q076_Mod_TA
|  |  |  | 92105702103 | South_A30-Q092_Mod_TA
|  |  |  | 92120708103 | South_A30-Q099_Mod_TA
|  |  |  | 92208701103 | South_A30-R040_Mod_TA
|  |  |  | 92208700103 | South_A30-R109_Mod_TA
|  |  |  | 92111759103 | South_A38-A110_Mod_TA
|  |  |  | 92175697103 | South_A38-B051_Mod_TA
|  |  |  | 92175698103 | South_A38-B315_Mod_TA
|  |  |  | 92105706103 | South_A38-B320_Mod_TA
|  |  |  | 92175699103 | South_A38-B321_Mod_TA
|  |  |  | 92175700103 | South_A38-B322_Mod_TA
|  |  |  | 92120709103 | South_A38-B323_Mod_TA
|  |  |  | 92124701103 | South_A38-B326_Mod_TA
|  |  |  | 92210713103 | South_A39-B047_Mod_TA
|  |  |  | 92210712103 | South_A40-B299_Mod_TA
|  |  |  | 92210711103 | South_A40-B300_Mod_TA
|  |  |  | 92210710103 | South_A41-A005_Mod_TA
|  |  |  | 92210709103 | South_A41-A006_Mod_TA
|  |  |  | 92210708103 | South_A41-A037_Mod_TA
|  |  |  | 92124698103 | South_A41-A467_Mod_TA
|  |  |  | 92124697103 | South_A41-A595_Mod_TA
|  |  |  | 92099702103 | South_A41-A649_Mod_TA
|  |  |  | 92124699103 | South_A41-A652_Mod_TA
|  |  |  | 92124700103 | South_A41-A653_Mod_TA
|  |  |  | 92129700103 | South_A41-B015_Mod_TA
|  |  |  | 92099698103 | South_A41-B018_Mod_TA
|  |  |  | 92210707103 | South_A41-B022_Mod_TA
|  |  |  | 92060822103 | South_A41-B023_Mod_TA
|  |  |  | 92105705103 | South_A41-B025_Mod_TA
|  |  |  | 92060825103 | South_A41-B028_Mod_TA
|  |  |  | 92216701103 | South_A41-B033_Mod_TA
|  |  |  | 92216700103 | South_A41-B041_Mod_TA
|  |  |  | 92060826103 | South_A41-B266_Mod_TA
|  |  |  | 92060824103 | South_A41-B268_Mod_TA
|  |  |  | 92129697103 | South_A41-B269_Mod_TA
|  |  |  | 92129698103 | South_A41-B270_Mod_TA
|  |  |  | 92128698103 | South_A41-B272_Mod_TA
|  |  |  | 92216699103 | South_A41-B274_Mod_TA
|  |  |  | 92129701103 | South_A41-B275_Mod_TA
|  |  |  | 92127698103 | South_A41-B276_Mod_TA
|  |  |  | 92128700103 | South_A41-B277_Mod_TA
|  |  |  | 92216698103 | South_A41-B278_Mod_TA
|  |  |  | 92099700103 | South_A41-B282_Mod_TA
|  |  |  | 92128701103 | South_A41-B291_Mod_TA
|  |  |  | 92216697103 | South_A41-B292_Mod_TA
|  |  |  | 92105704103 | South_A41-B295_Mod_TA
|  |  |  | 92210706103 | South_A41-B298_Mod_TA
|  |  |  | 92210705103 | South_A41-B389_Mod_TA
|  |  |  | 92210704103 | South_A41-B411_Mod_TA
|  |  |  | 92210703103 | South_A41-B436_Mod_TA
|  |  |  | 92127697103 | South_A41-B438_Mod_TA
|  |  |  | 92210702103 | South_A41-B439_Mod_TA
|  |  |  | 92060823103 | South_A41-B445_Mod_TA
|  |  |  | 92208705103 | South_A41-B455_Mod_TA
|  |  |  | 92099699103 | South_A41-B464_Mod_TA
|  |  |  | 92208699103 | South_A41-B475_Mod_TA
|  |  |  | 92208698103 | South_A41-B518_Mod_TA
|  |  |  | 92208704103 | South_A41-B541_Mod_TA
|  |  |  | 92208703103 | South_A41-B571_Mod_TA
|  |  |  | 92208697103 | South_A41-B574_Mod_TA
|  |  |  | 92208702103 | South_A41-B577_Mod_TA
|  |  |  | 96377717103 | South_A41-B577_SSV_TA
|  |  |  | 92128697103 | South_A41-B591_Mod_TA
|  |  |  | 92209706103 | South_A41-B594_Mod_TA
|  |  |  | 92209705103 | South_A41-B595_Mod_TA
|  |  |  | 92209704103 | South_A41-B623_Mod_TA
|  |  |  | 92209703103 | South_A41-B644_Mod_TA
|  |  |  | 92209702103 | South_A41-B795_Mod_TA
|  |  |  | 92210701103 | South_A41-B814_Mod_TA
|  |  |  | 92210700103 | South_A41-B833_Mod_TA
|  |  |  | 92210699103 | South_A41-B834_Mod_TA
|  |  |  | 92421697103 | South_A41-B873_Mod_TA
|  |  |  | 92099701103 | South_A41-B876_Mod_TA
|  |  |  | 92210698103 | South_A41-B909_Mod_TA
|  |  |  | 92210697103 | South_A41-B910_Mod_TA
|  |  |  | 92209701103 | South_A41-B916_Mod_TA
|  |  |  | 92209700103 | South_A41-B935_Mod_TA
|  |  |  | 92209699103 | South_A41-B938_Mod_TA
|  |  |  | 92209698103 | South_A41-B958_Mod_TA
|  |  |  | 96377716103 | South_A41-B958_SSV_TA
|  |  |  | 92405700103 | South_A43-B237_Mod_TA
|  |  |  | 92218708103 | South_BA003_Swap_MVS
|  |  |  | 92215699103 | South_BA007_Swap_MVS
|  |  |  | 92215698103 | South_BA009_Swap_MVS
|  |  |  | 92215697103 | South_BA011_Swap_MVS
|  |  |  | 92218707103 | South_BA013_Swap_MVS
|  |  |  | 92218706103 | South_BA016_Swap_MVS
|  |  |  | 92218705103 | South_BA022_Swap_MVS
|  |  |  | 92218704103 | South_BA023_Swap_MVS
|  |  |  | 92218703103 | South_BA025_Swap_MVS
|  |  |  | 92218702103 | South_BA027_Swap_MVS
|  |  |  | 92218701103 | South_BA030_Swap_MVS
|  |  |  | 92218700103 | South_BA032_Swap_MVS
|  |  |  | 92218699103 | South_BA038_Swap_MVS
|  |  |  | 92218698103 | South_BA039_Swap_MVS
|  |  |  | 92218697103 | South_BA040_Swap_MVS
|  |  |  | 92212726103 | South_BA041_Swap_MVS
|  |  |  | 92212725103 | South_BA043_Swap_MVS
|  |  |  | 92212724103 | South_BA048_Swap_MVS
|  |  |  | 92212723103 | South_BA053_Swap_MVS
|  |  |  | 92212722103 | South_BA056_Swap_MVS
|  |  |  | 92215731103 | South_BA075_Swap_MVS
|  |  |  | 92215730103 | South_BA431_Swap_MVS
|  |  |  | 92212706103 | South_BA700_Swap_MVS
|  |  |  | 92212705103 | South_BB070_Swap_MVS
|  |  |  | 92212704103 | South_BB103_Swap_MVS
|  |  |  | 92215729103 | South_BB188_Swap_MVS
|  |  |  | 92215728103 | South_BB307_Swap_MVS
|  |  |  | 92212703103 | South_BB308_Swap_MVS
|  |  |  | 92215727103 | South_BC013_Swap_MVS
|  |  |  | 92215726103 | South_BC014_Swap_MVS
|  |  |  | 92215725103 | South_BC018_Swap_MVS
|  |  |  | 92215724103 | South_BC028_Swap_MVS
|  |  |  | 92215723103 | South_BC035_Swap_MVS
|  |  |  | 92215722103 | South_BC042_Swap_MVS
|  |  |  | 92215721103 | South_BC047_Swap_MVS
|  |  |  | 92215720103 | South_BC052_Swap_MVS
|  |  |  | 92215719103 | South_BC053_Swap_MVS
|  |  |  | 92215718103 | South_BC059_Swap_MVS
|  |  |  | 92215717103 | South_BC062_Swap_MVS
|  |  |  | 92215716103 | South_BC065_Swap_MVS
|  |  |  | 92215715103 | South_BC069_Swap_MVS
|  |  |  | 92215714103 | South_BC070_Swap_MVS
|  |  |  | 92215713103 | South_BC081_Swap_MVS
|  |  |  | 92215712103 | South_BC082_Swap_MVS
|  |  |  | 92212702103 | South_BC084_Swap_MVS
|  |  |  | 92214701103 | South_BC088_Swap_MVS
|  |  |  | 92215711103 | South_BC089_Swap_MVS
|  |  |  | 92215710103 | South_BC091_Swap_MVS
|  |  |  | 92214700103 | South_BC099_Swap_MVS
|  |  |  | 92215709103 | South_BC100_Swap_MVS
|  |  |  | 92215708103 | South_BC102_Swap_MVS
|  |  |  | 92215707103 | South_BC109_Swap_MVS
|  |  |  | 92215706103 | South_BC117_Swap_MVS
|  |  |  | 92215705103 | South_BC122_Swap_MVS
|  |  |  | 92215704103 | South_BC125_Swap_MVS
|  |  |  | 92215703103 | South_BC127_Swap_MVS
|  |  |  | 92215702103 | South_BC151_Swap_MVS
|  |  |  | 92214726103 | South_BC301_Swap_MVS
|  |  |  | 92214725103 | South_BC303_Swap_MVS
|  |  |  | 92214724103 | South_BC304_Swap_MVS
|  |  |  | 92214723103 | South_BC306_Swap_MVS
|  |  |  | 92214722103 | South_BC310_Swap_MVS
|  |  |  | 92212721103 | South_BC311_Swap_MVS
|  |  |  | 92212720103 | South_BC317_Swap_MVS
|  |  |  | 92212719103 | South_BC318_Swap_MVS
|  |  |  | 92214699103 | South_BC326_Swap_MVS
|  |  |  | 92214698103 | South_BC327_Swap_MVS
|  |  |  | 92214697103 | South_BC328_Swap_MVS
|  |  |  | 92212718103 | South_BC329_Swap_MVS
|  |  |  | 92212717103 | South_BC340_Swap_MVS
|  |  |  | 92212716103 | South_BC341_Swap_MVS
|  |  |  | 92212715103 | South_BC342_Swap_MVS
|  |  |  | 92212714103 | South_BC350_Swap_MVS
|  |  |  | 92212713103 | South_BC385_Swap_MVS
|  |  |  | 92212712103 | South_BC391_Swap_MVS
|  |  |  | 92213756103 | South_BC392_Swap_MVS
|  |  |  | 92213755103 | South_BC398_Swap_MVS
|  |  |  | 92213754103 | South_BC399_Swap_MVS
|  |  |  | 92213753103 | South_BC401_Swap_MVS
|  |  |  | 92213752103 | South_BC423_Swap_MVS
|  |  |  | 92213751103 | South_BC700_Swap_MVS
|  |  |  | 92213750103 | South_BC701_Swap_MVS
|  |  |  | 92213749103 | South_BC711_Swap_MVS
|  |  |  | 92213748103 | South_BC742_Swap_MVS
|  |  |  | 92213747103 | South_BC758_Swap_MVS
|  |  |  | 92213746103 | South_BH001_Swap_MVS
|  |  |  | 92213745103 | South_BH003_Swap_MVS
|  |  |  | 92213744103 | South_BH004_Swap_MVS
|  |  |  | 92213743103 | South_BH006_Swap_MVS
|  |  |  | 92213701103 | South_BH026_Swap_MVS
|  |  |  | 92213700103 | South_BH040_Swap_MVS
|  |  |  | 92213699103 | South_BH043_Swap_MVS
|  |  |  | 92213742103 | South_BH045_Swap_MVS
|  |  |  | 92213741103 | South_BH054_Swap_MVS
|  |  |  | 92213740103 | South_BH059_Swap_MVS
|  |  |  | 92028705103 | South_BH065_Swap_MVS
|  |  |  | 92213739103 | South_BH073_Swap_MVS
|  |  |  | 92213738103 | South_BH076_Swap_MVS
|  |  |  | 92213737103 | South_BH081_Swap_MVS
|  |  |  | 92213736103 | South_BH082_Swap_MVS
|  |  |  | 92213735103 | South_BH086_Swap_MVS
|  |  |  | 92213734103 | South_BH100_Swap_MVS
|  |  |  | 92213733103 | South_BH105_Swap_MVS
|  |  |  | 92213732103 | South_BH107_Swap_MVS
|  |  |  | 92213731103 | South_BH189_Swap_MVS
|  |  |  | 92213730103 | South_BH309_Swap_MVS
|  |  |  | 92213729103 | South_BH750_Swap_MVS
|  |  |  | 92213728103 | South_BH761_Swap_MVS
|  |  |  | 92213727103 | South_BL001_Swap_MVS
|  |  |  | 92213726103 | South_BL006_Swap_MVS
|  |  |  | 92213725103 | South_BL009_Swap_MVS
|  |  |  | 92213698103 | South_BL011_Swap_MVS
|  |  |  | 92213697103 | South_BL012_Swap_MVS
|  |  |  | 92212701103 | South_BL020_Swap_MVS
|  |  |  | 92213724103 | South_BL023_Swap_MVS
|  |  |  | 92213723103 | South_BL031_Swap_MVS
|  |  |  | 92213722103 | South_BL076_Swap_MVS
|  |  |  | 92213721103 | South_BL323_Swap_MVS
|  |  |  | 92213720103 | South_BM003_Swap_MVS
|  |  |  | 92213719103 | South_BM020_Swap_MVS
|  |  |  | 92213718103 | South_BM050_Swap_MVS
|  |  |  | 92213717103 | South_BM059_Swap_MVS
|  |  |  | 92213716103 | South_BM087_Swap_MVS
|  |  |  | 92213715103 | South_BM231_Swap_MVS
|  |  |  | 92213714103 | South_BM307_Swap_MVS
|  |  |  | 92213713103 | South_BM314_Swap_MVS
|  |  |  | 92213712103 | South_BM320_Swap_MVS
|  |  |  | 92213711103 | South_BM350_Swap_MVS
|  |  |  | 92213710103 | South_BM359_Swap_MVS
|  |  |  | 92213709103 | South_BM360_Swap_MVS
|  |  |  | 92213708103 | South_BM369_Swap_MVS
|  |  |  | 92213707103 | South_BM376_Swap_MVS
|  |  |  | 92214721103 | South_BM397_Swap_MVS
|  |  |  | 92212700103 | South_BM401_Swap_MVS
|  |  |  | 92212699103 | South_BM404_Swap_MVS
|  |  |  | 92212698103 | South_BM408_Swap_MVS
|  |  |  | 92214720103 | South_BM424_Swap_MVS
|  |  |  | 92214719103 | South_BM507_Swap_MVS
|  |  |  | 92214718103 | South_BM508_Swap_MVS
|  |  |  | 92214717103 | South_BM509_Swap_MVS
|  |  |  | 92214716103 | South_BM519_Swap_MVS
|  |  |  | 92214715103 | South_BM527_Swap_MVS
|  |  |  | 92214714103 | South_BM589_Swap_MVS
|  |  |  | 92214713103 | South_BM590_Swap_MVS
|  |  |  | 92214712103 | South_BM618_Swap_MVS
|  |  |  | 92214711103 | South_BM647_Swap_MVS
|  |  |  | 92214710103 | South_BM668_Swap_MVS
|  |  |  | 92214709103 | South_BM671_Swap_MVS
|  |  |  | 92214708103 | South_BM672_Swap_MVS
|  |  |  | 92214707103 | South_BM673_Swap_MVS
|  |  |  | 92211711103 | South_BM674_Swap_MVS
|  |  |  | 92211710103 | South_BM675_Swap_MVS
|  |  |  | 92211709103 | South_BM704_Swap_MVS
|  |  |  | 92211708103 | South_BM755_Swap_MVS
|  |  |  | 92212697103 | South_BM756_Swap_MVS
|  |  |  | 92211701103 | South_BM758_Swap_MVS
|  |  |  | 92211700103 | South_BM770_Swap_MVS
|  |  |  | 92211707103 | South_BM808_Swap_MVS
|  |  |  | 92028706103 | South_BN190_Swap_MVS
|  |  |  | 92027698103 | South_BN200_Swap_MVS
|  |  |  | 92027699103 | South_BN207_Swap_MVS
|  |  |  | 91991703103 | South_BN223_Swap_MVS
|  |  |  | 92028703103 | South_BN892_Swap_MVS
|  |  |  | 92028704103 | South_BN897_Swap_MVS
|  |  |  | 92027697103 | South_BO316_Swap_MVS
|  |  |  | 92212711103 | South_BT004_Swap_MVS
|  |  |  | 92212710103 | South_BT005_Swap_MVS
|  |  |  | 92212709103 | South_BT012_Swap_MVS
|  |  |  | 92212708103 | South_BT013_Swap_MVS
|  |  |  | 92212707103 | South_BT020_Swap_MVS
|  |  |  | 92213706103 | South_BT021_Swap_MVS
|  |  |  | 92213705103 | South_BT022_Swap_MVS
|  |  |  | 92213704103 | South_BT023_Swap_MVS
|  |  |  | 92213703103 | South_BT025_Swap_MVS
|  |  |  | 92213702103 | South_BT032_Swap_MVS
|  |  |  | 92211706103 | South_BT033_Swap_MVS
|  |  |  | 92211705103 | South_BT034_Swap_MVS
|  |  |  | 92211704103 | South_BT036_Swap_MVS
|  |  |  | 92211703103 | South_BT037_Swap_MVS
|  |  |  | 92211702103 | South_BT042_Swap_MVS
|  |  |  | 92214706103 | South_BT043_Swap_MVS
|  |  |  | 92214705103 | South_BT045_Swap_MVS
|  |  |  | 92211699103 | South_BT046_Swap_MVS
|  |  |  | 92211698103 | South_BT111_Swap_MVS
|  |  |  | 92211697103 | South_BT714_Swap_MVS
|  |  |  | 92027700103 | South_LP036_Swap_MVS
|  |  |  | 92027701103 | South_LP055_Swap_MVS
|  |  |  | 92028697103 | South_LP075_Swap_MVS
|  |  |  | 92028698103 | South_LP112_Swap_MVS
|  |  |  | 92214704103 | South_QC023_Swap_MVS
|  |  |  | 92214703103 | South_QC056_Swap_MVS
|  |  |  | 92214702103 | South_QC076_Swap_MVS
|  |  |  | 92215701103 | South_QC354_Swap_MVS
|  |  |  | 92418697103 | South_QW038_Swap_MVS
|  |  |  | 92215700103 | South_SS082_Swap_MVS
|  |  |  | 91215732103 | TF_IC022_Swap_MVS
|  |  |  | 91215731103 | TF_IC025_Swap_MVS
|  |  |  | 97457730103 | 2026W17-AMBA-Benefits-Team
|  |  |  | 97457729103 | 2026W17-AMBA-Celltrex-Team
|  |  |  | 97457728103 | 2026W17-AMBA-Constel-Team
|  |  |  | 97457727103 | 2026W17-AMBA-Cyac-Team
|  |  |  | 97457726103 | 2026W17-AMBA-Esmetic-Team
|  |  |  | 97457725103 | 2026W17-AMBA-L2g-Team
|  |  |  | 97457724103 | 2026W17-AMBA-Terabyte-Team
|  |  |  | 97457723103 | 2026W17-MEDI-Celltrex-Team
|  |  |  | 97457722103 | 2026W17-MEDI-Ersatel-Team
|  |  |  | 97997708103 | 2026W18-AMBA-Benefits-Team
|  |  |  | 97997707103 | 2026W18-AMBA-Celltrex-Team
|  |  |  | 98103703103 | 2026W18-AMBA-Cis-Team
|  |  |  | 97997706103 | 2026W18-AMBA-Constel-Team
|  |  |  | 97997705103 | 2026W18-AMBA-Cyac-Team
|  |  |  | 97997704103 | 2026W18-AMBA-Esmetic-Team
|  |  |  | 98103702103 | 2026W18-AMBA-Interoptics-Team
|  |  |  | 97997703103 | 2026W18-AMBA-L2g-Team
|  |  |  | 97997702103 | 2026W18-AMBA-Terabyte-Team
|  |  |  | 97997701103 | 2026W18-MEDI-Celltrex-Team
|  |  |  | 98103701103 | 2026W18-MEDI-Cyac-Team
|  |  |  | 97997700103 | 2026W18-MEDI-Ersatel-Team
|  |  |  | 98103700103 | 2026W18-MEDI-L2g-Team
|  |  |  | 98103697103 | 2026W18-South-Cis-Team
|  |  |  | 98103699103 | 2026W18-South-Cyac-Team
|  |  |  | 98103698103 | 2026W18-South-L2g-Team
|  |  |  | 99402701103 | 2026W20-AMBA-Constel-Team
|  |  |  | 99402700103 | 2026W20-AMBA-Terabyte-Team
|  |  |  | 99402699103 | 2026W20-MEDI-Cis-Team
|  |  |  | 99402698103 | 2026W20-MEDI-L2g-Team
|  |  |  | 99402697103 | 2026W20-South-Cis-Team
|  |  |  | 99548706103 | 2026W21-AMBA-Celltrex-Team
|  |  |  | 99548705103 | 2026W21-AMBA-Cis-Team
|  |  |  | 99548704103 | 2026W21-AMBA-Constel-Team
|  |  |  | 99548703103 | 2026W21-AMBA-Cyac-Team
|  |  |  | 99548701103 | 2026W21-AMBA-Esmetic-Team
|  |  |  | 99548702103 | 2026W21-AMBA-ICS-Team
|  |  |  | 99548700103 | 2026W21-AMBA-L2g-Team
|  |  |  | 99548699103 | 2026W21-AMBA-Terabyte-Team
|  |  |  | 99548698103 | 2026W21-AMBA-Tg2-Team
|  |  |  | 99547705103 | 2026W21-MEDI-Celltrex-Team
|  |  |  | 99547703103 | 2026W21-MEDI-Ersatel-Team
|  |  |  | 99547704103 | 2026W21-MEDI-L2g-Team
|  |  |  | 99548697103 | 2026W21-South-Cyac-Team
|  |  |  | 99547706103 | 2026W21-South-L2g-Team
|  |  |  | 99547702103 | 2026W22-AMBA-Cyac-Team
|  |  |  | 99547701103 | 2026W22-AMBA-L2g-Team
|  |  |  | 99547699103 | 2026W22-MEDI-Cyac-Team
|  |  |  | 99547697103 | 2026W22-MEDI-Ersatel-Team
|  |  |  | 99547698103 | 2026W22-MEDI-L2g-Team
|  |  |  | 99547700103 | 2026W22-South-Cis-Team
|  |  |  | 96493710103 | AMBA_101_KS195_RSH_OPT_5G
|  |  |  | 99449699103 | AMBA_107_KN249_OPT
|  |  |  | 99449698103 | AMBA_107_KN287_OPT
|  |  |  | 99449697103 | AMBA_107_KN318_OPT
|  |  |  | 99300835103 | AMBA_108_KN085_RSH_OPT_4G
|  |  |  | 99300834103 | AMBA_108_KN222_RSH_OPT_4G
|  |  |  | 99300712103 | AMBA_108_KN222_RSH_OPT_5G
|  |  |  | 99300833103 | AMBA_108_KN253_RSH_OPT_4G
|  |  |  | 99300832103 | AMBA_108_KN296_RSH_OPT_4G
|  |  |  | 99300831103 | AMBA_108_KN313_RSH_OPT_4G
|  |  |  | 99300836103 | AMBA_108_KN322_RSH_OPT_4G
|  |  |  | 96493708103 | AMBA_111_KO055_RSH_OPT_5G
|  |  |  | 96493709103 | AMBA_111_KO207_RSH_OPT_5G
|  |  |  | 99300830103 | AMBA_126_KN242_RSH_OPT_4G
|  |  |  | 99300829103 | AMBA_127_KN251_RSH_OPT_4G
|  |  |  | 96493707103 | AMBA_129_CN210_RSH_OPT_5G
|  |  |  | 96493706103 | AMBA_144_CN252_RSH_OPT_5G
|  |  |  | 96493705103 | AMBA_146_CN172_RSH_OPT_5G
|  |  |  | 96493704103 | AMBA_146_CN236_RSH_OPT_5G
|  |  |  | 96493703103 | AMBA_147_CN810_RSH_OPT_5G
|  |  |  | 96493702103 | AMBA_169_CU004_RSH_OPT_5G
|  |  |  | 97924758103 | AMBA_175_KS023_RSH_OPT_4G
|  |  |  | 97924757103 | AMBA_175_KS374_RSH_OPT_4G
|  |  |  | 99300826103 | AMBA_176_KS008_RSH_OPT_4G
|  |  |  | 99300828103 | AMBA_176_KS108_RSH_OPT_4G
|  |  |  | 99300827103 | AMBA_176_KS631_RSH_OPT_4G
|  |  |  | 99300711103 | AMBA_176_KS631_RSH_OPT_5G
|  |  |  | 99300825103 | AMBA_176_KS632_RSH_OPT_4G
|  |  |  | 99300710103 | AMBA_176_KS632_RSH_OPT_5G
|  |  |  | 99300824103 | AMBA_176_KS633_RSH_OPT_4G
|  |  |  | 99300823103 | AMBA_177_KS009_RSH_OPT_4G
|  |  |  | 99300822103 | AMBA_177_KS634_RSH_OPT_4G
|  |  |  | 99300709103 | AMBA_177_KS634_RSH_OPT_5G
|  |  |  | 99300821103 | AMBA_177_KS644_RSH_OPT_4G
|  |  |  | 99300820103 | AMBA_177_KS908_RSH_OPT_4G
|  |  |  | 99300708103 | AMBA_177_KS908_RSH_OPT_5G
|  |  |  | 96493701103 | AMBA_179_KS174_RSH_OPT_5G
|  |  |  | 99300819103 | AMBA_182_KS624_RSH_OPT_4G
|  |  |  | 99300817103 | AMBA_182_KS628_RSH_OPT_4G
|  |  |  | 99300818103 | AMBA_182_KS629_RSH_OPT_4G
|  |  |  | 99300815103 | AMBA_183_KS147_RSH_OPT_4G
|  |  |  | 99300814103 | AMBA_183_KS642_RSH_OPT_4G
|  |  |  | 99300816103 | AMBA_183_KS701_RSH_OPT_4G
|  |  |  | 99300707103 | AMBA_183_KS701_RSH_OPT_5G
|  |  |  | 99300813103 | AMBA_184_KS105_RSH_OPT_4G
|  |  |  | 99300706103 | AMBA_184_KS105_RSH_OPT_5G
|  |  |  | 99300812103 | AMBA_184_KS635_RSH_OPT_4G
|  |  |  | 99300810103 | AMBA_184_KS637_RSH_OPT_4G
|  |  |  | 99300811103 | AMBA_184_KS639_RSH_OPT_4G
|  |  |  | 99300808103 | AMBA_185_KS446_RSH_OPT_4G
|  |  |  | 99300809103 | AMBA_185_KS626_RSH_OPT_4G
|  |  |  | 99300807103 | AMBA_185_KS627_RSH_OPT_4G
|  |  |  | 99300806103 | AMBA_185_KS630_RSH_OPT_4G
|  |  |  | 97924755103 | AMBA_186_BS125_RSH_OPT_4G
|  |  |  | 97924756103 | AMBA_186_BS210_RSH_OPT_4G
|  |  |  | 96896753103 | AMBA_188_BS097_RSH_OPT_4G
|  |  |  | 99300805103 | AMBA_189_KS107_RSH_OPT_4G
|  |  |  | 99300804103 | AMBA_189_KS306_RSH_OPT_4G
|  |  |  | 99300803103 | AMBA_189_KS432_RSH_OPT_4G
|  |  |  | 99300802103 | AMBA_189_KS711_RSH_OPT_4G
|  |  |  | 99300801103 | AMBA_190_KS063_RSH_OPT_4G
|  |  |  | 99300800103 | AMBA_190_KS364_RSH_OPT_4G
|  |  |  | 97924753103 | AMBA_191_KS067_RSH_OPT_4G
|  |  |  | 97924754103 | AMBA_191_KS151_RSH_OPT_4G
|  |  |  | 97924752103 | AMBA_191_KS494_RSH_OPT_4G
|  |  |  | 97924751103 | AMBA_192_BS238_RSH_OPT_4G
|  |  |  | 97924750103 | AMBA_193_BS065_RSH_OPT_4G
|  |  |  | 97924748103 | AMBA_193_BS105_RSH_OPT_4G
|  |  |  | 97924749103 | AMBA_193_BS124_RSH_OPT_4G
|  |  |  | 97924747103 | AMBA_193_BS352_RSH_OPT_4G
|  |  |  | 96896747103 | AMBA_194_BS227_RSH_OPT_4G
|  |  |  | 96896749103 | AMBA_195_KS378_RSH_OPT_4G
|  |  |  | 96896697103 | AMBA_195_KS378_RSH_OPT_5G
|  |  |  | 96896750103 | AMBA_195_KS702_RSH_OPT_4G
|  |  |  | 96896698103 | AMBA_195_KS702_RSH_OPT_5G
|  |  |  | 96896748103 | AMBA_195_KS707_RSH_OPT_4G
|  |  |  | 97924746103 | AMBA_196_KS111_RSH_OPT_4G
|  |  |  | 97924745103 | AMBA_196_KS201_RSH_OPT_4G
|  |  |  | 97924700103 | AMBA_196_KS201_RSH_OPT_5G
|  |  |  | 97924743103 | AMBA_197_BS050_RSH_OPT_4G
|  |  |  | 97924741103 | AMBA_197_BS088_RSH_OPT_4G
|  |  |  | 97924744103 | AMBA_197_BS246_RSH_OPT_4G
|  |  |  | 97924699103 | AMBA_197_BS246_RSH_OPT_5G
|  |  |  | 97924742103 | AMBA_197_BS314_RSH_OPT_4G
|  |  |  | 99300799103 | AMBA_198_BS087_RSH_OPT_4G
|  |  |  | 99300705103 | AMBA_198_BS087_RSH_OPT_5G
|  |  |  | 99300798103 | AMBA_198_BS140_RSH_OPT_4G
|  |  |  | 99300797103 | AMBA_198_BS302_RSH_OPT_4G
|  |  |  | 99300704103 | AMBA_198_BS302_RSH_OPT_5G
|  |  |  | 96896754103 | AMBA_226_KS037_RSH_OPT_4G
|  |  |  | 97924740103 | AMBA_249_KS622_RSH_OPT_4G
|  |  |  | 97924739103 | AMBA_249_KS623_RSH_OPT_4G
|  |  |  | 96493700103 | AMBA_80_BS213_RSH_OPT_5G
|  |  |  | 96493699103 | AMBA_86_KO044_RSH_OPT_5G
|  |  |  | 96493698103 | AMBA_90_KS200_RSH_OPT_5G
|  |  |  | 96493697103 | AMBA_91_KS334_RSH_OPT_5G
|  |  |  | 97924738103 | AMBA_96_KS142_RSH_OPT_4G
|  |  |  | 96515697103 | AMBA_A38-B059_Mod_TA
|  |  |  | 97616697103 | AMBA_A38-B318_Mod_TA
|  |  |  | 99544700103 | AMBA_A41-A688_Mod_TA
|  |  |  | 99544699103 | AMBA_A41-B034_Mod_TA
|  |  |  | 99033698103 | AMBA_A41-B258_Mod_TA
|  |  |  | 99033697103 | AMBA_A41-B259_Mod_TA
|  |  |  | 99544697103 | AMBA_A41-B265_Mod_TA
|  |  |  | 99543698103 | AMBA_BB051_SWAP_MVS
|  |  |  | 99424697103 | AMBA_BB354_SWAP_MVS
|  |  |  | 99543697103 | AMBA_BC408_SWAP_MVS
|  |  |  | 98950701103 | AMBA_BH097_SWAP_MVS
|  |  |  | 99543699103 | AMBA_BM014_SWAP_MVS
|  |  |  | 98950704103 | AMBA_BM037_SWAP_MVS
|  |  |  | 99034697103 | AMBA_BM081_SWAP_MVS
|  |  |  | 99032701103 | AMBA_BM381_SWAP_MVS
|  |  |  | 99032700103 | AMBA_BM382_SWAP_MVS
|  |  |  | 99032699103 | AMBA_BM392_SWAP_MVS
|  |  |  | 99032698103 | AMBA_BM551_SWAP_MVS
|  |  |  | 99032697103 | AMBA_BM626_SWAP_MVS
|  |  |  | 98950703103 | AMBA_BM835_SWAP_MVS
|  |  |  | 98950702103 | AMBA_BM902_SWAP_MVS
|  |  |  | 99375699103 | AMBA_BN067_SWAP_MVS
|  |  |  | 97429698103 | AMBA_BN147_SSV_MVS
|  |  |  | 98643697103 | AMBA_BN226_SSV_MVS
|  |  |  | 99375701103 | AMBA_BO223_SWAP_MVS
|  |  |  | 99375700103 | AMBA_BO408_SWAP_MVS
|  |  |  | 97429697103 | AMBA_BS094_SSV_MVS
|  |  |  | 98643698103 | AMBA_BS246_SSV_MVS
|  |  |  | 99117697103 | AMBA_CN186_SSV_MVS
|  |  |  | 97027704103 | AMBA_CS014_SSV_MVS
|  |  |  | 97414698103 | AMBA_CS090_SSV_MVS
|  |  |  | 97429699103 | AMBA_KS008_SSV_MVS
|  |  |  | 97429700103 | AMBA_KS009_SSV_MVS
|  |  |  | 97414700103 | AMBA_KS018_SSV_MVS
|  |  |  | 97414699103 | AMBA_KS111_SSV_MVS
|  |  |  | 96656698103 | AllRegion_ClusterOPT_Apr_TLF
|  |  |  | 97327699103 | AllRegion_ClusterOPT_Apr_TLF_V2
|  |  |  | 98185697103 | AllRegion_ClusterOPT_May_TLF
|  |  |  | 99195697103 | AllRegion_ClusterOPT_May_TLF_V2
|  |  |  | 96573697103 | BA_ARBA0430_FARM_Etapa1_MVS
|  |  |  | 97997709103 | BA_ARBA0484_FARM_Etapa1_MVS
|  |  |  | 97254697103 | BA_ARBA0635_FARM_Etapa01_MVS
|  |  |  | 96918698103 | BA_ARBA1185_FARM_Etapa1_MVS
|  |  |  | 97414704103 | BA_BB011_SSV_MVS
|  |  |  | 97027705103 | BA_BB076_SSV_MVS
|  |  |  | 99117698103 | BA_BB077_SSV_MVS
|  |  |  | 98614698103 | BA_BB173_SSV_MVS
|  |  |  | 97414702103 | BA_BM308_SSV_MVS
|  |  |  | 97959707103 | LP_DC022_SSV_MVS
|  |  |  | 99300763103 | MEDI_143_TC030_RSH_OPT_4G
|  |  |  | 99300703103 | MEDI_143_TC030_RSH_OPT_5G
|  |  |  | 96941714103 | MEDI_149_TC042_OPT
|  |  |  | 96941715103 | MEDI_149_TN304_OPT
|  |  |  | 96896752103 | MEDI_175_AN015_RSH_OPT_4G
|  |  |  | 97924737103 | MEDI_48_XC622_RSH_OPT_4G
|  |  |  | 96896751103 | MEDI_8_XN008_RSH_OPT_4G
|  |  |  | 97836697103 | MEDI_MC091_SWAP_MVS
|  |  |  | 97218697103 | MZ_ARME0188_FARM_Dismantle_MVS
|  |  |  | 97218698103 | MZ_ARME0837_FARM_Dismantle_MVS
|  |  |  | 97429701103 | MZ_MC004_SSV_MVS
|  |  |  | 97429702103 | NQ_QC048_SSV_MVS
|  |  |  | 97414701103 | NQ_QC053_SSV_MVS
|  |  |  | 98560712103 | NQ_QC105_SSV_MVS
|  |  |  | 96981698103 | RN_ARRN0006_FARM_Etapa1_MVS
|  |  |  | 97565697103 | RN_ARRN0052_FARM_Etapa01_MVS
|  |  |  | 96981697103 | RN_ARRN0338_FARM_Etapa1_MVS
|  |  |  | 99236699103 | RN_RS014_SSV_MVS
|  |  |  | 99236698103 | RN_RS056_SSV_MVS
|  |  |  | 97414703103 | SL_FC032_SSV_MVS
|  |  |  | 99300762103 | SUR_101_A38-B120_RSH_OPT_4G
|  |  |  | 99300761103 | SUR_101_A38-B223_RSH_OPT_4G
|  |  |  | 99300796103 | SUR_101_BB101_RSH_OPT_4G
|  |  |  | 99300795103 | SUR_101_BB113_RSH_OPT_4G
|  |  |  | 99300794103 | SUR_101_BB336_RSH_OPT_4G
|  |  |  | 99300793103 | SUR_101_BB337_RSH_OPT_4G
|  |  |  | 99300792103 | SUR_101_BB338_RSH_OPT_4G
|  |  |  | 99300791103 | SUR_101_BB339_RSH_OPT_4G
|  |  |  | 99300790103 | SUR_101_BB340_RSH_OPT_4G
|  |  |  | 99300789103 | SUR_101_BB400_RSH_OPT_4G
|  |  |  | 99238697103 | SUR_128_A30-Q001_RSH_OPT_4G
|  |  |  | 99238698103 | SUR_128_A30-Q001_RSH_OPT_5G
|  |  |  | 97257751103 | SUR_128_A30-Q041_RSH_OPT_4G
|  |  |  | 99130697103 | SUR_130_A30-Q034_RSH_OPT_5G
|  |  |  | 99130698103 | SUR_130_A30-Q042_RSH_OPT_5G
|  |  |  | 99300760103 | SUR_131_QC011_RSH_OPT_4G
|  |  |  | 99300788103 | SUR_131_QC349_RSH_OPT_4G
|  |  |  | 99239697103 | SUR_132_A30-Q092_RSH_OPT_5G
|  |  |  | 99238699103 | SUR_133_A30-Q099_RSH_OPT_4G
|  |  |  | 99238700103 | SUR_133_A30-Q099_RSH_OPT_5G
|  |  |  | 97264702103 | SUR_133_A30-Q259_RSH_OPT_4G
|  |  |  | 97264701103 | SUR_133_A30-Q261_RSH_OPT_4G
|  |  |  | 97264700103 | SUR_133_A30-Q262_RSH_OPT_4G
|  |  |  | 99300756103 | SUR_153_A36-F001_RSH_OPT_4G
|  |  |  | 99300759103 | SUR_153_A36-F003_RSH_OPT_4G
|  |  |  | 99300754103 | SUR_153_A36-F046_RSH_OPT_4G
|  |  |  | 99300757103 | SUR_153_A36-F049_RSH_OPT_4G
|  |  |  | 99300755103 | SUR_153_A36-F061_RSH_OPT_4G
|  |  |  | 99300758103 | SUR_153_A36-F068_RSH_OPT_4G
|  |  |  | 99300753103 | SUR_153_A36-F071_RSH_OPT_4G
|  |  |  | 99300785103 | SUR_153_DC005_RSH_OPT_4G
|  |  |  | 99300784103 | SUR_153_DC006_RSH_OPT_4G
|  |  |  | 99300787103 | SUR_153_DC022_RSH_OPT_4G
|  |  |  | 99300702103 | SUR_153_DC022_RSH_OPT_5G
|  |  |  | 99300783103 | SUR_153_DC115_RSH_OPT_4G
|  |  |  | 99300786103 | SUR_153_DC310_RSH_OPT_4G
|  |  |  | 96941700103 | SUR_15_A25-Z017_RSH_OPT_4G
|  |  |  | 96941699103 | SUR_15_A25-Z020_RSH_OPT_4G
|  |  |  | 96941698103 | SUR_15_A25-Z039_RSH_OPT_4G
|  |  |  | 96941712103 | SUR_15_VC001_RSH_OPT_4G
|  |  |  | 96941711103 | SUR_15_VC014_RSH_OPT_4G
|  |  |  | 96941710103 | SUR_15_VC023_RSH_OPT_4G
|  |  |  | 96941709103 | SUR_15_VC029_RSH_OPT_4G
|  |  |  | 96941708103 | SUR_15_VC307_RSH_OPT_4G
|  |  |  | 96941707103 | SUR_15_VC314_RSH_OPT_4G
|  |  |  | 97924729103 | SUR_163_A37-F039_RSH_OPT_4G
|  |  |  | 97924731103 | SUR_163_A37-F040_RSH_OPT_4G
|  |  |  | 97924698103 | SUR_163_A37-F040_RSH_OPT_5G
|  |  |  | 97924730103 | SUR_163_A37-F042_RSH_OPT_4G
|  |  |  | 97924736103 | SUR_163_DE006_RSH_OPT_4G
|  |  |  | 97924735103 | SUR_163_DE009_RSH_OPT_4G
|  |  |  | 97924734103 | SUR_163_DE033_RSH_OPT_4G
|  |  |  | 97924732103 | SUR_163_DE067_RSH_OPT_4G
|  |  |  | 97924733103 | SUR_163_DE068_RSH_OPT_4G
|  |  |  | 97181699103 | SUR_181_A41-A652_OPT
|  |  |  | 96887708103 | SUR_181_A41-A652_OPT_4G
|  |  |  | 97181698103 | SUR_181_A41-A653_OPT
|  |  |  | 96887707103 | SUR_181_A41-A653_OPT_4G
|  |  |  | 96887711103 | SUR_181_BM600_OPT_4G
|  |  |  | 96887710103 | SUR_181_BM602_OPT_4G
|  |  |  | 96887709103 | SUR_181_BM603_OPT_4G
|  |  |  | 97180699103 | SUR_186_A41-A660_RSH_OPT
|  |  |  | 97181697103 | SUR_186_A41-A688_RSH_OPT
|  |  |  | 99300747103 | SUR_193_A41-A004_RSH_OPT_4G
|  |  |  | 99300723103 | SUR_193_A41-A562_RSH_OPT_4G
|  |  |  | 99300748103 | SUR_193_A41-B027_RSH_OPT_4G
|  |  |  | 99300743103 | SUR_193_A41-B029_RSH_OPT_4G
|  |  |  | 99300744103 | SUR_193_A41-B285_RSH_OPT_4G
|  |  |  | 99300745103 | SUR_193_A41-B470_RSH_OPT_4G
|  |  |  | 99300746103 | SUR_193_A41-B471_RSH_OPT_4G
|  |  |  | 99300742103 | SUR_193_A41-B498_RSH_OPT_4G
|  |  |  | 99300741103 | SUR_193_A41-B937_RSH_OPT_4G
|  |  |  | 99300749103 | SUR_193_BM066_RSH_OPT_4G
|  |  |  | 99300752103 | SUR_193_BM074_RSH_OPT_4G
|  |  |  | 99300782103 | SUR_193_BM307_RSH_OPT_4G
|  |  |  | 99300751103 | SUR_193_BM327_RSH_OPT_4G
|  |  |  | 99300750103 | SUR_193_BM366_RSH_OPT_4G
|  |  |  | 99300778103 | SUR_193_BM376_RSH_OPT_4G
|  |  |  | 99300781103 | SUR_193_BM397_RSH_OPT_4G
|  |  |  | 99300780103 | SUR_193_BM519_RSH_OPT_4G
|  |  |  | 99300779103 | SUR_193_BM590_RSH_OPT_4G
|  |  |  | 99300739103 | SUR_195_A39-B304_RSH_OPT_4G
|  |  |  | 99300740103 | SUR_195_A39-B456_RSH_OPT_4G
|  |  |  | 99300738103 | SUR_195_A39-B780_RSH_OPT_4G
|  |  |  | 99300737103 | SUR_195_A39-B862_RSH_OPT_4G
|  |  |  | 99300775103 | SUR_195_BL001_RSH_OPT_4G
|  |  |  | 99300777103 | SUR_195_BL023_RSH_OPT_4G
|  |  |  | 99300776103 | SUR_195_BL323_RSH_OPT_4G
|  |  |  | 97264705103 | SUR_1_A38-B052_RSH_OPT_4G
|  |  |  | 97264704103 | SUR_1_A38-B310_RSH_OPT_4G
|  |  |  | 97257752103 | SUR_1_A38-B320_RSH_OPT_4G
|  |  |  | 97264703103 | SUR_1_A38-B324_RSH_OPT_4G
|  |  |  | 97180698103 | SUR_200_A41-A780_RSH_OPT
|  |  |  | 97180697103 | SUR_201_A41-A116_RSH_OPT
|  |  |  | 96887703103 | SUR_202_A42-A039_OPT_4G
|  |  |  | 96887704103 | SUR_202_A42-B082_OPT_4G
|  |  |  | 96887706103 | SUR_202_BH045_OPT_4G
|  |  |  | 96887705103 | SUR_203_BH107_OPT_4G
|  |  |  | 96941697103 | SUR_22_A25-Z041_RSH_OPT_4G
|  |  |  | 96941705103 | SUR_22_VW001_RSH_OPT_4G
|  |  |  | 96941701103 | SUR_22_VW005_RSH_OPT_4G
|  |  |  | 96941704103 | SUR_22_VW006_RSH_OPT_4G
|  |  |  | 96941703103 | SUR_22_VW033_RSH_OPT_4G
|  |  |  | 96941702103 | SUR_22_VW046_RSH_OPT_4G
|  |  |  | 96941706103 | SUR_22_VW303_RSH_OPT_4G
|  |  |  | 99300774103 | SUR_239_BH006_RSH_OPT_4G
|  |  |  | 99300773103 | SUR_239_BH054_RSH_OPT_4G
|  |  |  | 99300772103 | SUR_247_A37-B131_RSH_OPT_4G
|  |  |  | 97264699103 | SUR_2_A38-B314_RSH_OPT_4G
|  |  |  | 97230698103 | SUR_2_A38-B314_RSH_OPT_5G
|  |  |  | 97257750103 | SUR_2_A38-B315_RSH_OPT_4G
|  |  |  | 97230699103 | SUR_2_A38-B315_RSH_OPT_5G
|  |  |  | 97257749103 | SUR_2_A38-B321_RSH_OPT_4G
|  |  |  | 97257748103 | SUR_2_A38-B322_RSH_OPT_4G
|  |  |  | 96896714103 | SUR_310_A43-A803_RSH_OPT_4G
|  |  |  | 96896713103 | SUR_310_A43-A804_RSH_OPT_4G
|  |  |  | 96896712103 | SUR_310_A43-A805_RSH_OPT_4G
|  |  |  | 96896711103 | SUR_310_A43-B067_RSH_OPT_4G
|  |  |  | 96896710103 | SUR_310_A43-B145_RSH_OPT_4G
|  |  |  | 96896709103 | SUR_310_A43-B151_RSH_OPT_4G
|  |  |  | 96896708103 | SUR_310_A43-B156_RSH_OPT_4G
|  |  |  | 96896707103 | SUR_310_A43-B647_RSH_OPT_4G
|  |  |  | 96896706103 | SUR_310_A43-B907_RSH_OPT_4G
|  |  |  | 97924723103 | SUR_328_A41-B103_RSH_OPT_4G
|  |  |  | 97924724103 | SUR_328_A41-B289_RSH_OPT_4G
|  |  |  | 97924725103 | SUR_328_A41-B467_RSH_OPT_4G
|  |  |  | 97924722103 | SUR_328_A41-B983_RSH_OPT_4G
|  |  |  | 97924728103 | SUR_328_BM059_RSH_OPT_4G
|  |  |  | 97924727103 | SUR_328_BM509_RSH_OPT_4G
|  |  |  | 97924726103 | SUR_328_BM770_RSH_OPT_4G
|  |  |  | 99300736103 | SUR_3_BB354_RSH_OPT_4G
|  |  |  | 99300735103 | SUR_3_BB355_RSH_OPT_4G
|  |  |  | 97264706103 | SUR_4_A38-A110_RSH_OPT_4G
|  |  |  | 97264698103 | SUR_4_A38-B319_RSH_OPT_4G
|  |  |  | 97264697103 | SUR_4_A38-B412_RSH_OPT_4G
|  |  |  | 97178698103 | SUR_501_A34-J026_RSH_OPT
|  |  |  | 97179702103 | SUR_501_A34-J104_RSH_OPT
|  |  |  | 97178697103 | SUR_501_A34-J132_RSH_OPT
|  |  |  | 96896702103 | SUR_505_A34-J034_RSH_OPT_4G
|  |  |  | 96896703103 | SUR_505_A34-J071_RSH_OPT_4G
|  |  |  | 96896701103 | SUR_505_A34-J210_RSH_OPT_4G
|  |  |  | 96896730103 | SUR_505_JC016_RSH_OPT_4G
|  |  |  | 96896723103 | SUR_505_JC023_RSH_OPT_4G
|  |  |  | 96896729103 | SUR_505_JC031_RSH_OPT_4G
|  |  |  | 96896722103 | SUR_505_JC036_RSH_OPT_4G
|  |  |  | 96896721103 | SUR_505_JC047_RSH_OPT_4G
|  |  |  | 96896728103 | SUR_505_JC048_RSH_OPT_4G
|  |  |  | 96896727103 | SUR_505_JC049_RSH_OPT_4G
|  |  |  | 96896726103 | SUR_505_JC052_RSH_OPT_4G
|  |  |  | 96896725103 | SUR_505_JC056_RSH_OPT_4G
|  |  |  | 96896724103 | SUR_505_JC338_RSH_OPT_4G
|  |  |  | 96941713103 | SUR_509_FN032_RSH_OPT_4G
|  |  |  | 96896705103 | SUR_514_A32-O231_RSH_OPT_4G
|  |  |  | 96896704103 | SUR_514_A32-O426_RSH_OPT_4G
|  |  |  | 96896746103 | SUR_514_MO002_RSH_OPT_4G
|  |  |  | 96896732103 | SUR_514_MO015_RSH_OPT_4G
|  |  |  | 96896733103 | SUR_514_MS002_RSH_OPT_4G
|  |  |  | 96896731103 | SUR_514_MS007_RSH_OPT_4G
|  |  |  | 96896745103 | SUR_514_MS011_RSH_OPT_4G
|  |  |  | 96896744103 | SUR_514_MS023_RSH_OPT_4G
|  |  |  | 96896743103 | SUR_514_MS028_RSH_OPT_4G
|  |  |  | 96896742103 | SUR_514_MS032_RSH_OPT_4G
|  |  |  | 96896741103 | SUR_514_MS035_RSH_OPT_4G
|  |  |  | 96896740103 | SUR_514_MS038_RSH_OPT_4G
|  |  |  | 96896739103 | SUR_514_MS041_RSH_OPT_4G
|  |  |  | 96896738103 | SUR_514_MS042_RSH_OPT_4G
|  |  |  | 96896737103 | SUR_514_MS044_RSH_OPT_4G
|  |  |  | 96896736103 | SUR_514_MS062_RSH_OPT_4G
|  |  |  | 96896735103 | SUR_514_MS063_RSH_OPT_4G
|  |  |  | 96896734103 | SUR_514_MS122_RSH_OPT_4G
|  |  |  | 97255699103 | SUR_519_A33-O006_RSH_OPT_4G
|  |  |  | 99673703103 | SUR_523_A33-O075_OPT_4G
|  |  |  | 99673702103 | SUR_523_A33-O076_OPT_4G
|  |  |  | 99673701103 | SUR_523_A33-O134_OPT_4G
|  |  |  | 99673700103 | SUR_523_A33-O149_OPT_4G
|  |  |  | 99673699103 | SUR_523_A33-O244_OPT_4G
|  |  |  | 99673698103 | SUR_523_A33-O734_OPT_4G
|  |  |  | 99673697103 | SUR_523_MC397_OPT_4G
|  |  |  | 97177711103 | SUR_524_A33-O009_RSH_OPT
|  |  |  | 97177710103 | SUR_524_A33-O017_RSH_OPT
|  |  |  | 97177709103 | SUR_524_A33-O040_RSH_OPT
|  |  |  | 97179701103 | SUR_524_A33-O041_RSH_OPT
|  |  |  | 97177708103 | SUR_524_A33-O042_RSH_OPT
|  |  |  | 97177707103 | SUR_524_A33-O044_RSH_OPT
|  |  |  | 97177706103 | SUR_524_A33-O046_RSH_OPT
|  |  |  | 97177705103 | SUR_524_A33-O098_RSH_OPT
|  |  |  | 97177704103 | SUR_524_A33-O237_RSH_OPT
|  |  |  | 97177703103 | SUR_524_A33-O238_RSH_OPT
|  |  |  | 97177702103 | SUR_524_A33-O391_RSH_OPT
|  |  |  | 97179700103 | SUR_531_A34-J070_OPT
|  |  |  | 96887702103 | SUR_531_A34-J070_OPT_4G
|  |  |  | 97179699103 | SUR_531_A34-J096_OPT
|  |  |  | 96887699103 | SUR_531_A34-J096_OPT_4G
|  |  |  | 97179698103 | SUR_531_A34-J128_OPT
|  |  |  | 96887701103 | SUR_531_A34-J128_OPT_4G
|  |  |  | 96887700103 | SUR_531_JN013_OPT_4G
|  |  |  | 96887698103 | SUR_531_JS046_OPT_4G
|  |  |  | 96896699103 | SUR_532_A34-J057_RSH_OPT_4G
|  |  |  | 96896700103 | SUR_532_A34-J085_RSH_OPT_4G
|  |  |  | 96896720103 | SUR_532_JC010_RSH_OPT_4G
|  |  |  | 96896717103 | SUR_532_JC018_RSH_OPT_4G
|  |  |  | 96896719103 | SUR_532_JC075_RSH_OPT_4G
|  |  |  | 96896716103 | SUR_532_JC303_RSH_OPT_4G
|  |  |  | 96896715103 | SUR_532_JC320_RSH_OPT_4G
|  |  |  | 96896718103 | SUR_532_JC340_RSH_OPT_4G
|  |  |  | 97177701103 | SUR_533_A33-O054_RSH_OPT
|  |  |  | 97177700103 | SUR_533_A33-O067_RSH_OPT
|  |  |  | 97179697103 | SUR_533_A33-O070_RSH_OPT
|  |  |  | 97177699103 | SUR_533_A33-O071_RSH_OPT
|  |  |  | 97177698103 | SUR_533_A33-O102_RSH_OPT
|  |  |  | 97177697103 | SUR_533_A33-O419_RSH_OPT
|  |  |  | 97255697103 | SUR_5_A38-A792_RSH_OPT_4G
|  |  |  | 97255698103 | SUR_5_A38-B058_RSH_OPT_4G
|  |  |  | 99300728103 | SUR_63_A28-R015_RSH_OPT_4G
|  |  |  | 99300727103 | SUR_63_A28-R017_RSH_OPT_4G
|  |  |  | 99300765103 | SUR_63_A28-R051_RSH_OPT_4G
|  |  |  | 99300697103 | SUR_63_A28-R051_RSH_OPT_5G
|  |  |  | 99300726103 | SUR_63_A28-R057_RSH_OPT_4G
|  |  |  | 99300725103 | SUR_63_A28-R068_RSH_OPT_4G
|  |  |  | 99300719103 | SUR_63_A28-R076_RSH_OPT_4G
|  |  |  | 99300722103 | SUR_63_A28-R137_RSH_OPT_4G
|  |  |  | 99300715103 | SUR_63_A28-R138_RSH_OPT_4G
|  |  |  | 99300718103 | SUR_63_A28-R139_RSH_OPT_4G
|  |  |  | 99300714103 | SUR_63_A28-R140_RSH_OPT_4G
|  |  |  | 99300717103 | SUR_63_A28-R141_RSH_OPT_4G
|  |  |  | 99300713103 | SUR_63_A28-R144_RSH_OPT_4G
|  |  |  | 99300716103 | SUR_63_A28-R160_RSH_OPT_4G
|  |  |  | 99300721103 | SUR_63_A28-R163_RSH_OPT_4G
|  |  |  | 99300720103 | SUR_63_A28-R167_RSH_OPT_4G
|  |  |  | 99300766103 | SUR_63_RS003_RSH_OPT_4G
|  |  |  | 99300732103 | SUR_63_RS004_RSH_OPT_4G
|  |  |  | 99300731103 | SUR_63_RS005_RSH_OPT_4G
|  |  |  | 99300771103 | SUR_63_RS014_RSH_OPT_4G
|  |  |  | 99300701103 | SUR_63_RS014_RSH_OPT_5G
|  |  |  | 99300770103 | SUR_63_RS033_RSH_OPT_4G
|  |  |  | 99300700103 | SUR_63_RS033_RSH_OPT_5G
|  |  |  | 99300734103 | SUR_63_RS037_RSH_OPT_4G
|  |  |  | 99300730103 | SUR_63_RS040_RSH_OPT_4G
|  |  |  | 99300769103 | SUR_63_RS046_RSH_OPT_4G
|  |  |  | 99300733103 | SUR_63_RS048_RSH_OPT_4G
|  |  |  | 99300768103 | SUR_63_RS056_RSH_OPT_4G
|  |  |  | 99300699103 | SUR_63_RS056_RSH_OPT_5G
|  |  |  | 99300767103 | SUR_63_RS126_RSH_OPT_4G
|  |  |  | 99300698103 | SUR_63_RS126_RSH_OPT_5G
|  |  |  | 99300729103 | SUR_63_RS314_RSH_OPT_4G
|  |  |  | 97924720103 | SUR_64_RS008_RSH_OPT_4G
|  |  |  | 97924721103 | SUR_64_RS308_RSH_OPT_4G
|  |  |  | 97924719103 | SUR_65_RS089_RSH_OPT_4G
|  |  |  | 97924718103 | SUR_65_RS090_RSH_OPT_4G
|  |  |  | 97924717103 | SUR_65_RS091_RSH_OPT_4G
|  |  |  | 97924715103 | SUR_74_QS003_RSH_OPT_4G
|  |  |  | 97924697103 | SUR_74_QS003_RSH_OPT_5G
|  |  |  | 97924716103 | SUR_74_QS004_RSH_OPT_4G
|  |  |  | 97924714103 | SUR_74_QS007_RSH_OPT_4G
|  |  |  | 97924713103 | SUR_74_QS026_RSH_OPT_4G
|  |  |  | 97924712103 | SUR_74_QS027_RSH_OPT_4G
|  |  |  | 97924711103 | SUR_74_QS028_RSH_OPT_4G
|  |  |  | 97924710103 | SUR_74_QS029_RSH_OPT_4G
|  |  |  | 97924709103 | SUR_74_QS030_RSH_OPT_4G
|  |  |  | 97924708103 | SUR_74_QS031_RSH_OPT_4G
|  |  |  | 97924707103 | SUR_74_QS032_RSH_OPT_4G
|  |  |  | 97924706103 | SUR_74_QS304_RSH_OPT_4G
|  |  |  | 99300724103 | SUR_79_QS001_RSH_OPT_4G
|  |  |  | 99300764103 | SUR_79_QS013_RSH_OPT_4G
|  |  |  | 97924705103 | SUR_85_QW001_RSH_OPT_4G
|  |  |  | 97924704103 | SUR_85_QW002_RSH_OPT_4G
|  |  |  | 98184699103 | SUR_85_QW017_RSH_OPT_4G
|  |  |  | 97924701103 | SUR_91_RE019_RSH_OPT_4G
|  |  |  | 97924703103 | SUR_91_RE020_RSH_OPT_4G
|  |  |  | 97924702103 | SUR_91_RE021_RSH_OPT_4G
|  |  |  | 99544698103 | South_A24-V040_Mod_TA
|  |  |  | 98576697103 | South_A26-Z006_Mod_TA
|  |  |  | 97959705103 | South_A30-Q001_SSV_TA
|  |  |  | 97959700103 | South_A30-Q003_SSV_TA
|  |  |  | 97959704103 | South_A30-Q099_SSV_TA
|  |  |  | 98221697103 | South_A30-R041_Mod_TA
|  |  |  | 99033699103 | South_A34-J031_Mod_TA
|  |  |  | 98651697103 | South_A37-B060_SSV_TA
|  |  |  | 99236697103 | South_A37-B131_SSV_TA
|  |  |  | 97959701103 | South_A38-B315_SSV_TA
|  |  |  | 97959702103 | South_A38-B321_SSV_TA
|  |  |  | 97959703103 | South_A38-B322_SSV_TA
|  |  |  | 97959706103 | South_A38-B323_SSV_TA
|  |  |  | 96377723103 | South_A39-B047_SSV_TA
|  |  |  | 96377722103 | South_A40-B299_SSV_TA
|  |  |  | 96377721103 | South_A40-B300_SSV_TA
|  |  |  | 96377742103 | South_A41-A467_SSV_TA
|  |  |  | 96377741103 | South_A41-A595_SSV_TA
|  |  |  | 96377740103 | South_A41-A649_SSV_TA
|  |  |  | 96377743103 | South_A41-A652_SSV_TA
|  |  |  | 96377744103 | South_A41-A653_SSV_TA
|  |  |  | 96377729103 | South_A41-B015_SSV_TA
|  |  |  | 96377736103 | South_A41-B018_SSV_TA
|  |  |  | 96377747103 | South_A41-B023_SSV_TA
|  |  |  | 96377725103 | South_A41-B025_SSV_TA
|  |  |  | 96377750103 | South_A41-B028_SSV_TA
|  |  |  | 96377733103 | South_A41-B034_SSV_TA
|  |  |  | 96377726103 | South_A41-B266_SSV_TA
|  |  |  | 96377749103 | South_A41-B268_SSV_TA
|  |  |  | 96377727103 | South_A41-B269_SSV_TA
|  |  |  | 96377728103 | South_A41-B270_SSV_TA
|  |  |  | 96377732103 | South_A41-B272_SSV_TA
|  |  |  | 96377730103 | South_A41-B275_SSV_TA
|  |  |  | 96377746103 | South_A41-B276_SSV_TA
|  |  |  | 96377734103 | South_A41-B277_SSV_TA
|  |  |  | 96377738103 | South_A41-B282_SSV_TA
|  |  |  | 96377735103 | South_A41-B291_SSV_TA
|  |  |  | 96377720103 | South_A41-B292_SSV_TA
|  |  |  | 96377724103 | South_A41-B295_SSV_TA
|  |  |  | 96377719103 | South_A41-B298_SSV_TA
|  |  |  | 96377718103 | South_A41-B389_SSV_TA
|  |  |  | 96377745103 | South_A41-B438_SSV_TA
|  |  |  | 96377748103 | South_A41-B445_SSV_TA
|  |  |  | 96377737103 | South_A41-B464_SSV_TA
|  |  |  | 96377731103 | South_A41-B591_SSV_TA
|  |  |  | 96377739103 | South_A41-B876_SSV_TA
|  |  |  | 97959699103 | South_BB307_SSV_MVS
|  |  |  | 97052697103 | South_QC051_Swap_MVS
|  |  |  | 98220697103 | South_RC066_SWAP_MVS
|  |  |  | 98220698103 | South_RS020_SWAP_MVS
|  |  |  | 99543700103 | South_RS029_SWAP_MVS
|  |  |  | 98950700103 | South_UE002_SWAP_MVS
|  |  |  | 98577697103 | South_VC025_SWAP_MVS

## Site Rollout Plan
Customer Site ID | DU ID | DU ID Único | Site coefficient | TSSR | [5 empty] | TSSR Approval(TSSR Approved by Customer)(Civil Work) |  |  |  | ML |  |  |  | ML Configuaration in ISDP | Configuration Created | Farm Remark | Farm Batch | Row Farm | Subrack Farm | Room Farm | Rack Farm | Status BBU FARM
|  |  |  | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks
KS020 | AMBA_102_KS020_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS172 | AMBA_102_KS172_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS173 | AMBA_102_KS173_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS237 | AMBA_102_KS237_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS243 | AMBA_102_KS243_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS277 | AMBA_102_KS277_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS348 | AMBA_102_KS348_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS349 | AMBA_102_KS349_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS375 | AMBA_102_KS375_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS608 | AMBA_102_KS608_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS062 | AMBA_103_BS062_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS078 | AMBA_103_BS078_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS109 | AMBA_103_BS109_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS199 | AMBA_103_BS199_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS201 | AMBA_103_BS201_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS204 | AMBA_103_BS204_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS298 | AMBA_103_BS298_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS374 | AMBA_103_BS374_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS470 | AMBA_103_KS470_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN021 | AMBA_106_BN021_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN102 | AMBA_106_BN102_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN105 | AMBA_106_BN105_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN243 | AMBA_106_BN243_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN266 | AMBA_106_BN266_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN306 | AMBA_106_BN306_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO059 | AMBA_110_KO059_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO066 | AMBA_110_KO066_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN289 | AMBA_119_BN289_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN430 | AMBA_119_BN430_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN083 | AMBA_119_KN083_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN228 | AMBA_119_KN228_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN174 | AMBA_120_BN174_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN249 | AMBA_120_BN249_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN407 | AMBA_120_BN407_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN103 | AMBA_121_KN103_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN258 | AMBA_121_KN258_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN260 | AMBA_121_KN260_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN306 | AMBA_121_KN306_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN310 | AMBA_121_KN310_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN323 | AMBA_121_KN323_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN330 | AMBA_121_KN330_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN175 | AMBA_122_BN175_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN221 | AMBA_122_BN221_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN226 | AMBA_122_BN226_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN397 | AMBA_122_BN397_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN166 | AMBA_123_KN166_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN202 | AMBA_123_KN202_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN203 | AMBA_123_KN203_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN225 | AMBA_123_KN225_RSH_OPT |  | 1.53 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN297 | AMBA_123_KN297_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN300 | AMBA_123_KN300_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN354 | AMBA_123_KN354_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN364 | AMBA_123_KN364_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN106 | AMBA_124_KN106_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN126 | AMBA_124_KN126_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN295 | AMBA_124_KN295_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN356 | AMBA_124_KN356_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN175 | AMBA_130_KN175_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN209 | AMBA_130_KN209_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN329 | AMBA_130_KN329_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN351 | AMBA_130_KN351_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN352 | AMBA_130_KN352_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN016 | AMBA_131_CN016_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN239 | AMBA_131_KN239_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN290 | AMBA_131_KN290_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN314 | AMBA_131_KN314_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN363 | AMBA_131_KN363_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN079 | AMBA_132_KN079_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN080 | AMBA_132_KN080_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN081 | AMBA_132_KN081_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN134 | AMBA_132_KN134_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN163 | AMBA_132_KN163_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN206 | AMBA_132_KN206_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN223 | AMBA_132_KN223_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN303 | AMBA_132_KN303_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN369 | AMBA_132_KN369_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN376 | AMBA_132_KN376_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN082 | AMBA_133_KN082_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN099 | AMBA_133_KN099_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN127 | AMBA_133_KN127_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN254 | AMBA_133_KN254_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN255 | AMBA_133_KN255_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN259 | AMBA_133_KN259_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN350 | AMBA_133_KN350_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN359 | AMBA_133_KN359_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU211 | AMBA_133_NPU211_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU259 | AMBA_133_NPU259_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU325 | AMBA_133_NPU325_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU346 | AMBA_133_NPU346_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU508 | AMBA_133_NPU508_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU513 | AMBA_133_NPU513_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU514 | AMBA_133_NPU514_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN109 | AMBA_134_KN109_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN154 | AMBA_134_KN154_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN155 | AMBA_134_KN155_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN207 | AMBA_134_KN207_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN215 | AMBA_134_KN215_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN240 | AMBA_134_KN240_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN247 | AMBA_134_KN247_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN311 | AMBA_134_KN311_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN212 | AMBA_141_CN212_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN259 | AMBA_141_CN259_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN306 | AMBA_141_CN306_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN444 | AMBA_141_CN444_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN819 | AMBA_141_CN819_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN159 | AMBA_142_CN159_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN193 | AMBA_142_CN193_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN253 | AMBA_142_CN253_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN254 | AMBA_142_CN254_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN312 | AMBA_142_CN312_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN830 | AMBA_142_CN830_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN307 | AMBA_143_CN307_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN077 | AMBA_143_KN077_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN120 | AMBA_143_KN120_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN122 | AMBA_143_KN122_RSH_OPT |  | 1.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN191 | AMBA_143_KN191_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN236 | AMBA_143_KN236_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN237 | AMBA_143_KN237_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN309 | AMBA_143_KN309_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN169 | AMBA_145_CN169_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN274 | AMBA_145_CN274_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN493 | AMBA_145_CN493_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN310 | AMBA_148_CN310_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN360 | AMBA_148_CN360_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN108 | AMBA_155_CN108_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN144 | AMBA_155_CN144_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN428 | AMBA_155_CN428_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN272 | AMBA_156_CN272_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN321 | AMBA_156_CN321_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN343 | AMBA_156_CN343_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN344 | AMBA_156_CN344_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM001 | AMBA_159_CM001_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM026 | AMBA_159_CM026_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM029 | AMBA_159_CM029_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM036 | AMBA_159_CM036_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN291 | AMBA_159_CN291_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN247 | AMBA_160_CN247_RSH_OPT |  | 2.53 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN374 | AMBA_160_CN374_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN167 | AMBA_161_CN167_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN244 | AMBA_161_CN244_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN155 | AMBA_162_CN155_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU003 | AMBA_162_CU003_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU049 | AMBA_162_CU049_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU007 | AMBA_163_CU007_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU048 | AMBA_163_CU048_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU067 | AMBA_163_CU067_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS026 | AMBA_166_CS026_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS289 | AMBA_166_CS289_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS291 | AMBA_166_CS291_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU005 | AMBA_166_CU005_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU068 | AMBA_166_CU068_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU004 | AMBA_169_CU004_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM033 | AMBA_170_CM033_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS004 | AMBA_170_CS004_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS097 | AMBA_170_CS097_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS210 | AMBA_170_CS210_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS067 | AMBA_180_BS067_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS148 | AMBA_180_BS148_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS164 | AMBA_180_BS164_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS120 | AMBA_180_KS120_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS143 | AMBA_180_KS143_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS289 | AMBA_180_KS289_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS291 | AMBA_180_KS291_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS292 | AMBA_180_KS292_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS351 | AMBA_180_KS351_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS390 | AMBA_180_KS390_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP028 | AMBA_200_LP028_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP029 | AMBA_200_LP029_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP047 | AMBA_200_LP047_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP048 | AMBA_200_LP048_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP049 | AMBA_200_LP049_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP050 | AMBA_200_LP050_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP057 | AMBA_200_LP057_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP059 | AMBA_200_LP059_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP097 | AMBA_200_LP097_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP099 | AMBA_200_LP099_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP100 | AMBA_200_LP100_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP110 | AMBA_200_LP110_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP131 | AMBA_200_LP131_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP052 | AMBA_201_LP052_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP075 | AMBA_201_LP075_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP076 | AMBA_201_LP076_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP077 | AMBA_201_LP077_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP101 | AMBA_201_LP101_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP117 | AMBA_201_LP117_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP130 | AMBA_201_LP130_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP132 | AMBA_201_LP132_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP054 | AMBA_202_LP054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP056 | AMBA_202_LP056_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP058 | AMBA_202_LP058_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP060 | AMBA_202_LP060_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP061 | AMBA_202_LP061_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP062 | AMBA_202_LP062_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP105 | AMBA_202_LP105_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP129 | AMBA_202_LP129_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP157 | AMBA_202_LP157_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC007 | AMBA_203_LC007_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC016 | AMBA_203_LC016_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC020 | AMBA_203_LC020_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC045 | AMBA_203_LC045_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC047 | AMBA_203_LC047_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC058 | AMBA_203_LC058_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC059 | AMBA_203_LC059_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC014 | AMBA_204_LC014_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC023 | AMBA_204_LC023_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC025 | AMBA_204_LC025_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC041 | AMBA_204_LC041_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC043 | AMBA_204_LC043_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC044 | AMBA_204_LC044_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP136 | AMBA_204_LP136_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC001 | AMBA_205_LC001_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC036 | AMBA_205_LC036_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC037 | AMBA_205_LC037_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC046 | AMBA_205_LC046_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP022 | AMBA_206_LP022_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP034 | AMBA_206_LP034_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP038 | AMBA_206_LP038_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP074 | AMBA_206_LP074_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP078 | AMBA_206_LP078_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP079 | AMBA_206_LP079_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP080 | AMBA_206_LP080_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP115 | AMBA_206_LP115_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP116 | AMBA_206_LP116_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC021 | AMBA_207_LC021_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC022 | AMBA_207_LC022_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC024 | AMBA_207_LC024_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC027 | AMBA_207_LC027_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC031 | AMBA_207_LC031_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC033 | AMBA_207_LC033_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC034 | AMBA_207_LC034_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC038 | AMBA_207_LC038_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC039 | AMBA_207_LC039_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC040 | AMBA_207_LC040_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC052 | AMBA_207_LC052_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC064 | AMBA_207_LC064_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP030 | AMBA_209_LP030_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP031 | AMBA_209_LP031_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP066 | AMBA_209_LP066_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP073 | AMBA_209_LP073_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP090 | AMBA_209_LP090_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP091 | AMBA_209_LP091_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP093 | AMBA_209_LP093_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP122 | AMBA_209_LP122_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP126 | AMBA_209_LP126_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP127 | AMBA_209_LP127_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP135 | AMBA_209_LP135_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP036 | AMBA_210_LP036_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP087 | AMBA_210_LP087_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC008 | AMBA_211_LC008_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC013 | AMBA_211_LC013_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC026 | AMBA_211_LC026_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC029 | AMBA_211_LC029_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC030 | AMBA_211_LC030_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC032 | AMBA_211_LC032_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC035 | AMBA_211_LC035_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC053 | AMBA_211_LC053_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC054 | AMBA_211_LC054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC055 | AMBA_211_LC055_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC063 | AMBA_211_LC063_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP010 | AMBA_211_LP010_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP039 | AMBA_211_LP039_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP040 | AMBA_211_LP040_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP086 | AMBA_211_LP086_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP024 | AMBA_212_LP024_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP027 | AMBA_212_LP027_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP037 | AMBA_212_LP037_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP044 | AMBA_212_LP044_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP072 | AMBA_212_LP072_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP081 | AMBA_212_LP081_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP082 | AMBA_212_LP082_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP083 | AMBA_212_LP083_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP084 | AMBA_212_LP084_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP085 | AMBA_212_LP085_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP118 | AMBA_212_LP118_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP119 | AMBA_212_LP119_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP001 | AMBA_215_LP001_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP043 | AMBA_215_LP043_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP045 | AMBA_215_LP045_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP094 | AMBA_215_LP094_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP134 | AMBA_215_LP134_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS312 | AMBA_228_BS312_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS220 | AMBA_228_KS220_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS281 | AMBA_228_KS281_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS282 | AMBA_228_KS282_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS324 | AMBA_228_KS324_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS350 | AMBA_228_KS350_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS461 | AMBA_228_KS461_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS476 | AMBA_228_KS476_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS080 | AMBA_229_BS080_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS113 | AMBA_229_BS113_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS114 | AMBA_229_BS114_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS143 | AMBA_229_BS143_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS197 | AMBA_229_BS197_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS230 | AMBA_229_BS230_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS232 | AMBA_229_BS232_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS233 | AMBA_229_BS233_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH065 | AMBA_238_BH065_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH309 | AMBA_238_BH309_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP015 | AMBA_239_LP015_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP046 | AMBA_239_LP046_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP095 | AMBA_239_LP095_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP098 | AMBA_239_LP098_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP109 | AMBA_239_LP109_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP111 | AMBA_239_LP111_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP133 | AMBA_239_LP133_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP903 | AMBA_239_LP903_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN078 | AMBA_24_BN078_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN149 | AMBA_24_BN149_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN276 | AMBA_24_BN276_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN277 | AMBA_24_BN277_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN318 | AMBA_24_BN318_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN468 | AMBA_24_BN468_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN471 | AMBA_24_BN471_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN095 | AMBA_253_BN095_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN408 | AMBA_253_BN408_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN454 | AMBA_253_BN454_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN460 | AMBA_253_BN460_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN461 | AMBA_253_BN461_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN863 | AMBA_253_BN863_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN049 | AMBA_254_KN049_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN086 | AMBA_254_KN086_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN104 | AMBA_254_KN104_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN288 | AMBA_254_KN288_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN307 | AMBA_254_KN307_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN321 | AMBA_254_KN321_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN345 | AMBA_254_KN345_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN346 | AMBA_254_KN346_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN127 | AMBA_55_BN127_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN908 | AMBA_55_BN908_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN116 | AMBA_56_BN116_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN147 | AMBA_56_BN147_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN209 | AMBA_56_BN209_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN215 | AMBA_56_BN215_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN250 | AMBA_56_BN250_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN446 | AMBA_56_BN446_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN448 | AMBA_56_BN448_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN484 | AMBA_56_BN484_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN489 | AMBA_56_BN489_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU038 | AMBA_56_NPU038_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU1591 | AMBA_56_NPU1591_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU352 | AMBA_56_NPU352_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU353 | AMBA_56_NPU353_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN297 | AMBA_61_BN297_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN432 | AMBA_61_BN432_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN403 | AMBA_62_BN403_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN479 | AMBA_62_BN479_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN903 | AMBA_62_BN903_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN905 | AMBA_62_BN905_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN092 | AMBA_63_BN092_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN118 | AMBA_63_BN118_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN148 | AMBA_63_BN148_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN308 | AMBA_63_BN308_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN325 | AMBA_63_BN325_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN137 | AMBA_64_BN137_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN262 | AMBA_64_BN262_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN263 | AMBA_64_BN263_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN288 | AMBA_64_BN288_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN340 | AMBA_64_BN340_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN172 | AMBA_67_BN172_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN231 | AMBA_67_BN231_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN112 | AMBA_BN112_Swap_MVS | Si
BN187 | AMBA_BN187_Swap_MVS | Si | [17 empty] | Wicaps
BN240 | AMBA_BN240_Swap_MVS | Si
BN299 | AMBA_BN299_Swap_MVS | Si
BN304 | AMBA_BN304_Swap_MVS | Si
BN310 | AMBA_BN310_Swap_MVS | Si
BN329 | AMBA_BN329_Swap_MVS | Si
BN344 | AMBA_BN344_Swap_MVS | Si
BN417 | AMBA_BN417_Swap_MVS | Si
BN433 | AMBA_BN433_Swap_MVS | Si
BN447 | AMBA_BN447_Swap_MVS | Si
BN472 | AMBA_BN472_Swap_MVS | Si
BN475 | AMBA_BN475_Swap_MVS | Si
BO021 | AMBA_BO021_Swap_MVS | Si
BO059 | AMBA_BO059_Swap_MVS | Si
BO157 | AMBA_BO157_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO168 | AMBA_BO168_Swap_MVS | Si
BO243 | AMBA_BO243_Swap_MVS | Si
BO255 | AMBA_BO255_Swap_MVS | Si
BO314 | AMBA_BO314_Swap_MVS | Si
BO365 | AMBA_BO365_Swap_MVS | Si
BO369 | AMBA_BO369_Swap_MVS | Si
BO372 | AMBA_BO372_Swap_MVS | Si
BO375 | AMBA_BO375_Swap_MVS | Si
BO440 | AMBA_BO440_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO492 | AMBA_BO492_Swap_MVS | Si
BO494 | AMBA_BO494_Swap_MVS | Si
BO498 | AMBA_BO498_Swap_MVS | Si
BO832 | AMBA_BO832_Swap_MVS | Si
BO834 | AMBA_BO834_Swap_MVS | Si
BO836 | AMBA_BO836_Swap_MVS | Si
BO838 | AMBA_BO838_Swap_MVS | Si
BO841 | AMBA_BO841_Swap_MVS | Si
BO842 | AMBA_BO842_Swap_MVS | Si
BO846 | AMBA_BO846_Swap_MVS | Si
BO861 | AMBA_BO861_Swap_MVS | Si
BO862 | AMBA_BO862_Swap_MVS | Si
BO866 | AMBA_BO866_Swap_MVS | Si
BO873 | AMBA_BO873_Swap_MVS | Si
KN090 | AMBA_KN090_Swap_MVS | Si
KN131 | AMBA_KN131_Swap_MVS | Si
KN242 | AMBA_KN242_Swap_MVS | Si | [17 empty] | Wicaps
KN249 | AMBA_KN249_Swap_MVS | Si | [17 empty] | Wicaps
KN265 | AMBA_KN265_Swap_MVS | Si
KN287 | AMBA_KN287_Swap_MVS | Si | [17 empty] | Wicaps
KO049 | AMBA_KO049_Swap_MVS | Si | [23 empty] | PPI Approved
KO211 | AMBA_KO211_Swap_MVS | Si |  | NA | NA | NA | NA | NA
KO213 | AMBA_KO213_Swap_MVS | Si
KO235 | AMBA_KO235_Swap_MVS | Si
KO237 | AMBA_KO237_Swap_MVS | Si | [23 empty] | PPI Approved
KO241 | AMBA_KO241_Swap_MVS | Si
ARBA0018 | BA_ARBA0018_FARM_Etapa1_MVS
ARBA0121 | BA_ARBA0121_FARM_Etapa1_MVS
ARBA0135 | BA_ARBA0135_FARM_Etapa1_MVS
ARBA0169 | BA_ARBA0169_FARM_Etapa1_MVS
ARBA0222 | BA_ARBA0222_FARM_Etapa1_MVS |  |  |  |  | 2026-01-13 | 2026-01-13 | David Encina WX1367993
ARBA0250 | BA_ARBA0250_FARM_Etapa1_MVS
ARBA0440 | BA_ARBA0440_FARM_Etapa1_MVS
ARBA0464 | BA_ARBA0464_FARM_Dismantle_MVS
ARBA0471 | BA_ARBA0471_FARM_Etapa1_MVS |  |  |  |  | 2026-03-30 | 2026-03-30 | David Encina WX1367993 |  |  | 2026-04-07 | David Encina WX1367993 |  |  | 2026-03-17 | Abraham Jesus Salas Marfil 00237943 | [9 empty] | Survey Pending
ARBA0571 | BA_ARBA0571_FARM_Etapa1_MVS
ARBA0575 | BA_ARBA0575_FARM_Etapa1_MVS
ARBA0588 | BA_ARBA0588_FARM_Etapa1_MVS
ARBA0591 | BA_ARBA0591_FARM_Etapa1_MVS |  |  |  |  | 2026-04-08 | 2026-04-08 | David Encina WX1367993
ARBA0642 | BA_ARBA0642_FARM_Etapa1_MVS
ARBA0707 | BA_ARBA0707_FARM_Etapa1_MVS
ARBA0729 | BA_ARBA0729_FARM_Etapa1_MVS |  |  |  |  | 2026-04-06 | 2026-04-06 | David Encina WX1367993 | [6 empty] | 2026-03-17 | Abraham Jesus Salas Marfil 00237943
ARBA10312 | BA_ARBA10312_FARM_Etapa1_MVS
ARBA10477 | BA_ARBA10477_FARM_Etapa1_MVS
ARBA1189 | BA_ARBA1189_FARM_Etapa1_MVS |  |  |  |  | 2026-01-16 | 2026-01-16 | David Encina WX1367993
ARBA6698 | BA_ARBA6698_FARM_Etapa1_MVS |  |  |  |  | 2026-01-21 | 2026-01-21 | David Encina WX1367993
ARBA8171 | BA_ARBA8171_FARM_Etapa1_MVS |  |  |  |  | 2026-01-12 | 2026-01-12 | David Encina WX1367993
ARBA8267 | BA_ARBA8267_FARM_Etapa1_MVS
ARBA9114 | BA_ARBA9114_FARM_Etapa1_MVS
ARBA9306 | BA_ARBA9306_FARM_Etapa1_MVS
BB003 | BA_BB003_Swap_MVS | Si |  | 2025-11-20 | 2025-11-21 | 2025-12-04 | 2025-12-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-24 | 2026-04-22 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-16 | Yes
BB004 | BA_BB004_Swap_MVS | Si | 1.53 | 2025-11-26 | 2025-11-27 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-28 | 2025-12-17 | Miguel Angel Garcia Martinez 00881238 | RFI Ok | [12 empty] | Ready for Dismantle
BB007 | BA_BB007_Swap_MVS | Si | 1.53 | 2025-11-26 | 2025-11-27 | 2025-12-30 | 2025-12-30 | Agustin Maria Bianchetti 00958351 |  | 2025-11-28 | 2026-03-13 | Agustin Maria Bianchetti 00958351 | RFI Ok |  | 2026-02-11 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | Survey Pending
BB008 | BA_BB008_Swap_MVS | Si | 1.2 | 2026-02-09 | 2026-02-09 | 2026-02-19 | 2026-02-19 | Bautista Turri WX1450521 |  | 2026-02-11 | 2026-03-13 | Bautista Turri WX1450521 |  |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917
BB011 | BA_BB011_Swap_MVS | Si | 1.83 |  |  | 2025-12-18 | 2025-12-18 | David Encina WX1367993 |  |  | 2026-01-14 | David Encina WX1367993 | En stock. Guzmán Nacich Aprobada por Nico Trubbo el 22/12/2025. Aprobado por Ezequiel Fail el 14/01/2026. |  | 2026-02-06 | Claudio Romeo WX1379521 |  |  |  |  | Etapa 01 | 15A | BHBINS05-01 pos 01 | Sala TX01, 1er piso | 00 | SubRack Installed
BB019 | BA_BB019_Swap_MVS | Si | 1.2 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-13 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-18 | 2026-05-07 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-06-01 | Yes | [6 empty] | Survey Pending
BB020 | BA_BB020_Swap_MVS | Si | 1.53 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 2026-02-19 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-20 | 2026-04-01 | Miguel Angel Garcia Martinez 00881238
BB028 | BA_BB028_Swap_MVS | Si | 1.53 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-19 | 2026-03-16 | Miguel Angel Garcia Martinez 00881238
BB031 | BA_BB031_Swap_MVS | Si | 1.53 | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-29 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-31 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-20 | Yes |  |  | 09 | NPTAINS05-01 pos 02 | TX 1er piso | 12
BB032 | BA_BB032_Swap_MVS | Si |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-04 |  | Miguel Angel Garcia Martinez 00881238
BB033 | BA_BB033_Swap_MVS | Si | 1.2 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 2026-02-19 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-20 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
BB039 | BA_BB039_Swap_MVS | Si |  | 2026-02-05 | 2026-02-05 | 2026-02-09 | 2026-02-09 | David Encina WX1367993 |  | 2026-02-09 | 2026-02-20 | David Encina WX1367993 |  |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917
BB042 | BA_BB042_Swap_MVS | Si | 1.53 | 2026-02-18 | 2026-02-18 | 2026-02-12 | 2026-02-19 | Miguel Diaz Sebastiani WX1448333 |  | 2026-02-20 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
BB045 | BA_BB045_Swap_MVS | Si | 1.87 |  |  | 2025-12-13 | 2025-12-13 | zhaofeng 00917583 |  |  | 2026-01-15 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. Aprobada por Pablo Buono el 15/01/2026. |  | 2026-02-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-16 | Yes
BB046 | BA_BB046_Swap_MVS | Si | 1.2 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-15 | 2026-01-15 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. Aprobada por Pablo Buono el 15/01/2026. |  | 2026-02-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-12 | Yes
BB048 | BA_BB048_Swap_MVS | Si | 1.2 | 2026-02-06 | 2026-02-06 | 2026-02-09 | 2026-02-09 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-10 | 2026-03-03 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917 | [9 empty] | Survey Pending
BB056 | BA_BB056_Swap_MVS | Si | 1.53 |  |  | 2026-01-20 | 2026-01-20 | zhaofeng 00917583 |  |  | 2026-01-28 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. 28/01/2026: Aprobada por David Masessa. |  | 2026-02-11 | Joaquin Alejandro Luduena WX1488820
BB058 | BA_BB058_Swap_MVS | Si | 1.53 | 2025-11-18 | 2025-11-19 | 2025-11-25 | 2025-11-25 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | Pending Subrack | Etapa 01 |  |  |  |  | PPI Approved
BB059 | BA_BB059_Swap_MVS | Si | 1.2 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-10 | 2026-03-03 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-20 | Yes
BB062 | BA_BB062_Swap_MVS | Si | 1.53 |  |  | 2025-12-10 | 2025-12-10 | zhaofeng 00917583 |  |  | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
BB063 | BA_BB063_Swap_MVS | Si | 1.53 | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2026-02-23 | Bautista Turri WX1450521 |  | 2026-02-11 | 2026-03-02 | Bautista Turri WX1450521 |  |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917
BB064 | BA_BB064_Swap_MVS | Si |  | 2026-02-06 | 2026-02-06 | 2026-02-09 | 2026-02-09 | David Encina WX1367993 |  | 2026-02-10 | 2026-04-01 | David Encina WX1367993 | RFI Ok 20/02/2026: Aprobada por Nico Trubbo |  | 2026-03-10 | David Encina WX1367993 |  | 2026-05-20 | Yes
BB071 | BA_BB071_Swap_MVS | Si | 2.2 |  |  | 2026-01-18 | 2026-01-18 | zhaofeng 00917583 |  | 2026-01-21 | 2026-01-21 | Miguel Angel Garcia Martinez 00881238 | RFI Ok
BB075 | BA_BB075_Swap_MVS | Si | 1.87 | 2025-11-18 | 2025-11-19 | 2025-11-24 | 2025-11-24 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB076 | BA_BB076_Swap_MVS | Si | 2.2 | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-11 | 2025-12-17 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB077 | BA_BB077_Swap_MVS | Si | 2.2 |  |  | 2025-12-09 | 2025-12-09 | zhaofeng 00917583 |  |  | 2025-12-17 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok | [6 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB081 | BA_BB081_Swap_MVS | Si | 1.2 | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-09 | Agustin Maria Bianchetti 00958351 |  | 2025-12-11 | 2025-12-17 | Agustin Maria Bianchetti 00958351 | [13 empty] | Ready for Dismantle
BB086 | BA_BB086_Swap_MVS | Si |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-10 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 | 20/02/2026: Aprobada por Nico Trubbo |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917
BB090 | BA_BB090_Swap_MVS | Si |  | 2026-05-20 | 2026-05-21 | 2026-05-20 | 2026-05-20 | David Encina WX1367993 |  | 2026-05-22 | 2026-06-03 | David Encina WX1367993
BB094 | BA_BB094_Swap_MVS | Si | 1.2 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-16 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-04-17 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 09 | NPTAINS05-01 pos 03 | TX 1er piso | 12
BB097 | BA_BB097_Swap_MVS | Si |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-10 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Tomas Ezequiel Sanchez WX1486917 | [9 empty] | Survey Pending
BB098 | BA_BB098_Swap_MVS | Si |  | 2025-12-11 | 2025-12-12 | 2025-12-16 | 2025-12-16 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-15 | 2026-01-15 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-09 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-20 | Yes | [6 empty] | Survey Pending
BB099 | BA_BB099_Swap_MVS | Si |  | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-28 | David Encina WX1367993 |  | 2026-05-28 |  | David Encina WX1367993 | [13 empty] | Survey Pending
BB101 | BA_BB101_Swap_MVS | Si | 1.53 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-10 | David Encina WX1367993 |  | 2026-02-12 | 2026-02-20 | David Encina WX1367993 | 0 |  | 2026-03-12 | Tomas Ezequiel Sanchez WX1486917
BB102 | BA_BB102_Swap_MVS | Si |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | Agustin Maria Bianchetti 00958351 |  | 2026-01-27 | 2026-05-28 | Daniel Horacio Rocabado WX1372513 | [5 empty] | 2026-05-20 | Yes
BB109 | BA_BB109_Swap_MVS | Si | 0.87 | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-12 | 2025-12-05 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 12 | INDINS05-01 POS 02 | TX01, 1er Piso | 01 | SubRack Installed
BB113 | BA_BB113_Swap_MVS | Si | 1.53 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-03-11 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-16 | Yes | [6 empty] | PPI Pending
BB122 | BA_BB122_Swap_MVS | Si | 0.53 | 2025-11-26 | 2025-11-27 | 2025-12-02 | 2025-12-02 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-28 | 2025-12-17 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 12 | INDINS05-01 POS 01 | TX01, 1er Piso | 01 | Installed
BB141 | BA_BB141_Swap_MVS | Si |  |  | 2026-05-20 | 2026-05-21 | 2026-05-21 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-22 | 2026-05-26 | Tomas Ezequiel Sanchez WX1486917
BB173 | BA_BB173_Swap_MVS | Si | 1.2 | 2025-11-18 | 2025-11-19 | 2025-11-26 | 2025-11-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-12-05 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB185 | BA_BB185_Swap_MVS | Si | 2.2 | 2025-11-18 | 2025-11-19 | 2025-11-26 | 2025-11-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-11-27 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Ready for Dismantle
BB190 | BA_BB190_Swap_MVS | Si |  | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-21 | 2026-03-10 | Miguel Angel Garcia Martinez 00881238
BB313 | BA_BB313_Swap_MVS | Si |  | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-10 | David Encina WX1367993 |  | 2026-02-11 | 2026-02-11 | David Encina WX1367993 | [5 empty] | 2026-05-20 | Yes
BB314 | BA_BB314_Swap_MVS | Si | 0.53 | 2026-02-05 | 2026-02-05 | 2026-02-06 | 2026-02-06 | David Encina WX1367993 |  | 2026-02-09 | 2026-02-10 | David Encina WX1367993 | RFI Ok |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-07 | Yes | pendiente DCDU | Etapa 01 | 05 | CDRINS05-01 pos 01 | Sala TX, P.B. | 11 | Installed with Issue
BB317 | BA_BB317_Swap_MVS | Si | 1.2 | 2026-02-20 | 2026-02-20 | 2026-02-26 | 2026-02-26 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-03-20 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 |  |  |  |  | Survey Pending
BB319 | BA_BB319_Swap_MVS | Si | 1.2 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-10 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-04 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | Survey Pending
BB323 | BA_BB323_Swap_MVS | Si | 1.53 | 2025-12-17 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-19 | 2026-01-09 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-02-12 | Joaquin Alejandro Luduena WX1488820
BB324 | BA_BB324_Swap_MVS | Si |  | 2026-02-11 | 2026-02-11 | 2026-02-25 | 2026-02-25 | Agustin Maria Bianchetti 00958351 |  | 2026-02-16 | 2026-03-13 | Agustin Maria Bianchetti 00958351 | [5 empty] | 2026-05-20 | Yes
BB330 | BA_BB330_Swap_MVS | Si |  | 2025-11-26 | 2025-11-27 | 2025-12-02 | 2025-12-02 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-28 | 2026-03-16 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
BB336 | BA_BB336_Swap_MVS | Si | 1.2 | 2025-11-26 | 2025-11-27 | 2026-01-13 | 2026-01-13 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-28 | 2026-01-28 | Miguel Angel Garcia Martinez 00881238 | RFI Ok. Instalar en Zunchos existentes. 28/01/2026: Aprobada por David Masessa. |  | 2026-02-13 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 99 | MHRINS05-01 pos 04 | Sala TX, P.B. | 16 | Installed
BB337 | BA_BB337_Swap_MVS | Si | 1.53 | 2025-11-27 | 2025-11-28 | 2025-12-16 | 2025-12-16 | Agustin Maria Bianchetti 00958351 |  | 2025-12-01 | 2026-01-23 | Agustin Maria Bianchetti 00958351 | En stock. Guzmán Nacich Aprobada por Pablo Buono el 23/01/2026. |  | 2026-02-13 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 99 | MHRINS05-01 pos 03 | Sala TX, P.B. | 16 | Installed
BB338 | BA_BB338_Swap_MVS | Si | 1.2 | 2025-11-27 | 2025-12-18 | 2026-01-07 | 2026-01-07 | David Encina WX1367993 |  | 2025-12-01 | 2026-01-23 | David Encina WX1367993 | RFI Ok Aprobada por Pablo Buono el 23/01/2026. |  | 2026-02-13 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | PPI Pending
BB339 | BA_BB339_Swap_MVS | Si | 1.2 | 2025-11-28 | 2025-12-01 | 2025-12-15 | 2025-12-16 | Agustin Maria Bianchetti 00958351 |  | 2025-12-02 | 2026-01-22 | Agustin Maria Bianchetti 00958351 | RFI Ok |  | 2026-02-13 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 99 | MHRINS05-01 pos 02 | Sala TX, P.B. | 16 | Installed
BB340 | BA_BB340_Swap_MVS | Si | 1.2 | 2025-12-11 | 2025-12-12 | 2026-02-06 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-15 | 2026-02-09 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-12 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 99 | MHRINS05-01 pos 01 | Sala TX, P.B. | 16 | Installed
BB341 | BA_BB341_Swap_MVS | Si | 1.53 |  |  | 2026-01-10 | 2026-01-10 | zhaofeng 00917583 |  |  | 2026-01-26 | Miguel Angel Garcia Martinez 00881238 | No lleva Zunchos#， serian pipemounts. En stock. Guzmán Nacich |  | 2026-02-12 | Joaquin Alejandro Luduena WX1488820
BB344 | BA_BB344_Swap_MVS | Si | 1.53 | 2025-12-12 | 2025-12-15 | 2025-12-12 | 2025-12-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-01-09 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820
BB345 | BA_BB345_Swap_MVS | Si | 1.53 | 2026-02-06 | 2026-02-06 | 2026-02-10 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-10 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
BB351 | BA_BB351_Swap_MVS | Si | 0.53 | 2025-11-27 | 2025-11-28 | 2025-12-09 | 2025-12-09 | David Encina WX1367993 |  | 2025-12-01 | 2025-12-17 | David Encina WX1367993 | [7 empty] | Reemplazar UBBPg2 por UBBPg2a | Etapa 01 | 15A | BHBINS05-01 pos 02 | Sala TX01, 1er piso | 00 | Installed
BB370 | BA_BB370_Swap_MVS | Si
BB371 | BA_BB371_Swap_MVS | Si
BB378 | BA_BB378_Swap_MVS | Si | 1.53 |  |  | 2026-01-05 | 2026-01-05 | zhaofeng 00917583 |  | 2026-01-09 | 2026-01-09 | Elvia Carolina Cortes Garcia 00881509 | RFI Ok | [6 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB400 | BA_BB400_Swap_MVS | Si |  | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-11 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
BM021 | BA_BM021_Swap_MVS | Si | 1.2 | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-22 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-19 | 2026-03-16 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 06 | MAJINS05-01 pos 01 | Sala TX, 2do Piso | 15 | Dispatched
BM039 | BA_BM039_Swap_MVS | Si
BM055 | BA_BM055_Swap_MVS | Si | 1.53 |  |  |  |  | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BM056 | BA_BM056_Swap_MVS | Si |  | 2025-12-12 | 2025-12-15 | 2025-12-12 | 2025-12-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238
BM058 | BA_BM058_Swap_MVS | Si | 1.2 | [6 empty] | 2026-01-02 | 2026-01-02 | Adrian Guzman Garcia 00881507 | RFI Ok |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BM099 | BA_BM099_Swap_MVS | Si
BM328 | BA_BM328_Swap_MVS | Si | 1.2 | [7 empty] | 2026-03-30 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | N/A
BM331 | BA_BM331_Swap_MVS | Si | 1.2 | 2025-12-17 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-19 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-12 | Tomas Ezequiel Sanchez WX1486917
BM332 | BA_BM332_Swap_MVS | Si | 1.2 | 2025-12-22 | 2025-12-23 | 2025-12-26 | 2025-12-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BM334 | BA_BM334_Swap_MVS | Si | 1.2 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-19 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BM338 | BA_BM338_Swap_MVS | Si | 1.53 | [7 empty] | 2026-03-30 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820
BM339 | BA_BM339_Swap_MVS | Si |  | 2025-11-27 | 2025-11-28 | 2025-12-04 | 2025-12-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 | 2026-01-06 | Miguel Angel Garcia Martinez 00881238
BM349 | BA_BM349_Swap_MVS | Si |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238
BM353 | BA_BM353_Swap_MVS | Si |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | 06/02/2026: Aprobada por Pablo Buono. | [12 empty] | Survey Pending
BM354 | BA_BM354_Swap_MVS | Si | 1.2 | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-01-30 | Miguel Angel Garcia Martinez 00881238 | 0 |  | 2026-03-12 | Tomas Ezequiel Sanchez WX1486917
BM358 | BA_BM358_Swap_MVS | Si | 1.87 | [7 empty] | 2026-01-05 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820
BM361 | BA_BM361_Swap_MVS | Si | 1.2 |  |  |  |  | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-01-26 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BM362 | BA_BM362_Swap_MVS | Si | 1.53 | [7 empty] | 2026-01-06 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
BM372 | BA_BM372_Swap_MVS | Si | 1.53 | [7 empty] | 2026-01-06 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917
BM394 | BA_BM394_Swap_MVS | Si | 1.2 | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BM531 | BA_BM531_Swap_MVS | Si | 1.87 | [8 empty] | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820
BM576 | BA_BM576_Swap_MVS | Si |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM588 | BA_BM588_Swap_MVS | Si | 1.53 | 2025-11-27 | 2025-11-28 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 | 2026-04-01 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820
BM648 | BA_BM648_Swap_MVS | Si |  | 2025-12-05 | 2026-02-05 | 2026-02-26 | 2026-02-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-09 | 2026-03-10 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM649 | BA_BM649_Swap_MVS | Si | 0.53 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-16 | 2026-03-10 | Adrian Guzman Garcia 00881507 | AProbada por Pablo Buono el 10/03/2026. | [7 empty] | Etapa 01 | 04 | STYINS05-01 pos 02 | Sala TX, 1er Piso | 06 | ML
BM653 | BA_BM653_Swap_MVS | Si | 0.53 | 2025-11-27 | 2025-11-28 | 2025-12-05 | 2025-12-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 | 2026-03-10 | Adrian Guzman Garcia 00881507 | Verificar ubicación de zunchos R0 aprobada el 02/01/20226 R01 aprobada el 20/02/2026. R02 aprobada por Pablo Buono el 10/03/2026. |  | 2026-03-09 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | ML
BM654 | BA_BM654_Swap_MVS | Si | 0.87 | 2025-12-05 | 2025-12-08 | 2025-12-08 | 2025-12-08 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-09 | 2026-02-23 | Adrian Guzman Garcia 00881507 | Verificar ubicación de zunchos 29/12/2026: Primera fecha de aprobacion. 19/02/2026: Aprobada por Pablo Buono modificaciones 23/02/2026: Se sube R04 version con los cambio correcta. |  | 2026-03-09 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 04 | STYINS05-01 pos 01 | Sala TX, 1er Piso | 06 | ML
BM659 | BA_BM659_Swap_MVS | Si | 0.53 | 2025-11-20 | 2025-11-21 | 2025-11-26 | 2025-11-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-24 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 | Aprobado por Nico Trubbo el 09/12/2025. 19/02/2026: Aprobada por Pablo Buono modificaciones. |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 |  |  |  |  | Etapa 01 | 05 | LTNINS05-01 pos 02 | Sala TX, P.B. | 01 | Dispatched
BM661 | BA_BM661_Swap_MVS | Si | 0.87 | 2025-11-20 | 2025-11-21 | 2025-12-04 | 2025-12-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-24 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 | R00: Aprobada el 02/01/2026 R01: Aprobada el 20/02/2026 |  | 2026-03-12 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 05 | LTNINS05-01 pos 03 | Sala TX, P.B. | 01 | ML
BM663 | BA_BM663_Swap_MVS | Si | 0.53 | 2025-11-20 | 2025-11-21 | 2025-11-26 | 2025-11-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-24 | 2026-02-20 | Adrian Guzman Garcia 00881507 | 05/01/2026: Aprobada R0 20/02/2026: Aprobada R01 |  | 2026-03-09 | Tomas Ezequiel Sanchez WX1486917 |  |  |  |  | Etapa 01 | 05 | LTNINS05-02 pos 01 | Sala TX, P.B. | 01 | Dispatched
BM676 | BA_BM676_Swap_MVS | Si | [8 empty] | 2026-01-02 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 06 | MAJINS05-01 pos 02 | Sala TX, 2do Piso | 15
BM680 | BA_BM680_Swap_MVS | Si | [8 empty] | 2026-01-02 | Arturo Gonzalo Antonio Cantu 00879903 | Soportes en stock. Guzmán Nacich Zunchos en stock. CIS Group |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 06 | MAJINS05-02 pos 01 | Sala TX, 2do Piso | 15
BM686 | BA_BM686_Swap_MVS | Si |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-17 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-12 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 06 | MAJINS05-03 pos 03 | Sala TX, 2do Piso | 30
BM688 | BA_BM688_Swap_MVS | Si |  | 2025-12-05 | 2025-12-08 | 2025-12-10 | 2025-12-10 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-09 | 2026-01-07 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-12 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 06 | MAJINS05-03 pos 04 | Sala TX, 2do Piso | 30
BM689 | BA_BM689_Swap_MVS | Si |  | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-17 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 | 10/02/2026: Aprobada R01 20/02/2026: Aprobada por Pablo Buono |  | 2026-03-09 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 06 | MAJINS05-04 pos 02 | Sala TX, 2do Piso | 30
BM690 | BA_BM690_Swap_MVS | Si |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-22 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 | [9 empty] | 06 | MAJINS05-05 pos 01 | Sala TX, 2do Piso | 20
BM691 | BA_BM691_Swap_MVS | Si |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-22 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 | 19/02/2026: Aprobada por Pablo Buono las modificaciones. 23/02/2026: Hubo modificaciones devuelta#， se aprobaron en la fecha. |  | 2026-03-09 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 06 | MAJINS05-04 pos 03 | Sala TX, 2do Piso | 30
BM694 | BA_BM694_Swap_MVS | Si |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-22 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 | 19/02/2026: Aprobada por Pablo Buono modificaciones. 23/02/2026: Aprobada por Pablo Buono devuelta por modificaciones. |  | 2026-03-09 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 06 | MAJINS05-04 pos 04 | Sala TX, 2do Piso | 30
BM745 | BA_BM745_Swap_MVS | Si | [8 empty] | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 06 | MAJINS05-01 pos 04 | Sala TX, 2do Piso | 15
BM746 | BA_BM746_Swap_MVS | Si
BM747 | BA_BM747_Swap_MVS | Si | 0.87 | 2025-12-15 | 2025-12-16 | 2026-02-26 | 2026-02-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-18 | 2026-03-10 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 06 | MAJINS05-01 pos 03 | Sala TX, 2do Piso | 15 | Dispatched
BM748 | BA_BM748_Swap_MVS | Si | [8 empty] | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 06 | MAJINS05-01 pos 03 | Sala TX, 2do Piso | 15
BM757 | BA_BM757_Swap_MVS | Si |  | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-17 | 2026-01-26 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Survey Pending
BM759 | BA_BM759_Swap_MVS | Si | 1.2 | 2025-11-20 | 2025-11-21 | 2025-11-25 | 2025-11-25 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-24 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-12 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 05 | LTNINS05-01 pos 04 | Sala TX, P.B. | 01 | Dispatched
BM760 | BA_BM760_Swap_MVS | Si | 0.87 | [7 empty] | 2025-12-09 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-12 | David Encina WX1367993 |  |  |  |  | Etapa 01 | 05 | LTNINS05-01 pos 01 | Sala TX, P.B. | 01 | Dispatched
BM761 | BA_BM761_Swap_MVS | Si | 0.87 | 2025-11-27 | 2025-11-28 | 2026-02-26 | 2026-02-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 | 2026-03-12 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 04 | STYINS05-02 pos 01 | Sala TX, 1er Piso | 06 | ML
BM762 | BA_BM762_Swap_MVS | Si | 0.87 | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-17 | 2025-12-19 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-09 | Tomas Ezequiel Sanchez WX1486917 |  |  |  |  | Etapa 01 | 04 | STYINS05-01 pos 04 | Sala TX, 1er Piso | 06 | ML
BM763 | BA_BM763_Swap_MVS | Si | 0.87 | 2025-11-27 | 2025-11-28 | 2025-12-10 | 2025-12-10 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 | 2026-01-07 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-09 | Tomas Ezequiel Sanchez WX1486917 |  |  |  |  | Etapa 01 | 04 | STYINS05-01 pos 03 | Sala TX, 1er Piso | 06 | ML
BM764 | BA_BM764_Swap_MVS | Si | [8 empty] | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok 26/01/2026: Aprobado por Pablo Buono. |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 06 | MAJINS05-02 pos 04 | Sala TX, 2do Piso | 15
BM765 | BA_BM765_Swap_MVS | Si | 0.87 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-12 | Bautista Turri WX1450521 |  | 2025-12-12 | 2026-02-06 | Bautista Turri WX1450521 | 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-12 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 06 | MAJINS05-02 pos 01 | Sala TX, 2do Piso | 30 | Dispatched
BM766 | BA_BM766_Swap_MVS | Si | [8 empty] | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok 26/01/2026: Aprobado por Pablo Buono. |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 06 | MAJINS05-02 pos 03 | Sala TX, 2do Piso | 15
BM783 | BA_BM783_Swap_MVS | Si | 0.53 | [6 empty] | 2026-01-26 | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. 26/01/2026: Aprobado por Pablo Buono. |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943 |  |  |  |  | Etapa 01 | 06 | MAJINS05-01 pos 02 | Sala TX, 2do Piso | 15 | Dispatched
BM784 | BA_BM784_Swap_MVS | Si | [8 empty] | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. 26/01/2026: Aprobado por Pablo Buono. |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 06 | MAJINS05-03 pos 01 | Sala TX, 2do Piso | 30
BM785 | BA_BM785_Swap_MVS | Si | [8 empty] | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. 26/01/2026: Aprobado por Pablo Buono. |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 06 | MAJINS05-02 pos 02 | Sala TX, 2do Piso | 15
BM611 | CLUSTER_OPT_SUR_179 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_180 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_181 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_184 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_185 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_186 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_189 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_190 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_191 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_192 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_197 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_198 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_199 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_201 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_204 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_205 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_206 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_207 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_208 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_328 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_330 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_501 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_514 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_515 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_521 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_523 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_524 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_529 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_531 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | CLUSTER_OPT_SUR_533 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC005 | LP_DC005_Swap_MVS | Si | 0.87 |  |  | 2026-01-06 | 2026-01-06 | zhaofeng 00917583 |  | 2026-01-10 | 2026-01-10 | Elvia Carolina Cortes Garcia 00881509 | RFI Ok. Aprobada por Pablo Buono el 10/01/2026. |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
DC006 | LP_DC006_Swap_MVS | Si | 0.87 |  |  | 2026-01-09 | 2026-01-09 | zhaofeng 00917583 |  | 2026-01-14 | 2026-01-14 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobado por Pablo Buono el 14/01/2026. Aprobada por Diego Alvarenga el 14/01/2026. POsterior a la aprobacion se solicitó bajar los paneles de 5G (10/03/2026) |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
DC011 | LP_DC011_Swap_MVS | Si | 1.2 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-12 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-01-23 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobada por Pablo Buono el 23/01/2026. |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
DC115 | LP_DC115_Swap_MVS | Si | 1.87 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-03-30 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-12 | Yes
DC310 | LP_DC310_Swap_MVS | Si | 1.53 | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | Agustin Maria Bianchetti 00958351 |  | 2026-01-15 | 2026-01-19 | Agustin Maria Bianchetti 00958351 | RFI Ok |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
DE002 | LP_DE002_Swap_MVS | Si | 0.87 |  |  | 2026-01-06 | 2026-01-06 | zhaofeng 00917583 |  | 2026-01-10 | 2026-01-10 | Elvia Carolina Cortes Garcia 00881509 | RFI Ok Aprobada por Pablo Buono el 10/01/2026. |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
DE004 | LP_DE004_Swap_MVS | Si | 0.87 | 2025-12-29 | 2025-12-30 | 2026-01-08 | 2026-01-08 | Elvia Carolina Cortes Garcia 00881509 |  | 2025-12-31 | 2026-04-07 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-02-13 | Tomas Ezequiel Sanchez WX1486917
DE006 | LP_DE006_Swap_MVS | Si | 2.2 | 2025-12-18 | 2025-12-19 | 2026-02-05 | 2026-02-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-22 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-06 | Yes
DE007 | LP_DE007_Swap_MVS | Si | 0.87 |  |  | 2025-12-26 | 2025-12-26 | zhaofeng 00917583 |  |  | 2025-12-31 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-02-06 | Claudio Romeo WX1379521 |  |  |  | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
DE009 | LP_DE009_Swap_MVS | Si | 1.87 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-23 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 | 2025-12-30 | Miguel Angel Garcia Martinez 00881238 | Verificar la ubicación de los zunchos para antenas |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917
DE011 | LP_DE011_Swap_MVS | Si |  | 2025-11-18 | 2025-11-19 | 2026-02-18 | 2026-02-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-31 | 2026-02-27 | Miguel Angel Garcia Martinez 00881238 | Asignada la provisión a COBRA#， provee soporte para OMNI |  | 2026-02-13 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-20 | Yes
DE014 | LP_DE014_Swap_MVS | Si | [8 empty] | 2026-01-19 | Abraham Jesus Salas Marfil 00237943 | RFI Ok |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917 | [9 empty] | Survey Pending
DE017 | LP_DE017_Swap_MVS | Si |  | 2026-02-20 | 2026-02-20 | 2026-02-27 | 2026-02-27 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-03-12 | Miguel Angel Garcia Martinez 00881238
DE018 | LP_DE018_Swap_MVS | Si | 1.53 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-11 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820
DE019 | LP_DE019_Swap_MVS | Si | 0.87 | 2025-12-18 | 2025-12-19 | 2026-01-19 | 2026-01-19 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-10 |  | Arturo Gonzalo Antonio Cantu 00879903
DE022 | LP_DE022_Swap_MVS | Si | 0.87 |  |  | 2026-01-10 | 2026-01-10 | zhaofeng 00917583 |  | 2026-01-14 | 2026-01-14 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-02-13 | Tomas Ezequiel Sanchez WX1486917
DE025 | LP_DE025_Swap_MVS | Si |  | 2025-12-22 | 2025-12-23 | 2026-05-05 | 2026-05-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 | 2025-12-31 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-20 | Yes
DE027 | LP_DE027_Swap_MVS | Si |  | 2026-01-05 | 2026-01-06 | 2026-05-05 | 2026-05-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-07 | 2026-03-13 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-20 | Yes
DE028 | LP_DE028_Swap_MVS | Si | 0.53 |  |  | 2026-01-10 | 2026-01-10 | zhaofeng 00917583 |  | 2026-01-19 | 2026-01-19 | Miguel Angel Garcia Martinez 00881238 | En stock. Guzmán Nacich |  | 2026-02-13 | Tomas Ezequiel Sanchez WX1486917
DE029 | LP_DE029_Swap_MVS | Si
DE031 | LP_DE031_Swap_MVS | Si |  | 2025-12-09 | 2025-12-10 | 2025-12-10 | 2025-12-10 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-11 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | Asignado a COBRA. (FECHA?) 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-12 | David Encina WX1367993 |  |  | Yes
DE033 | LP_DE033_Swap_MVS | Si | 0.87 |  |  | 2025-12-26 | 2025-12-26 | zhaofeng 00917583 |  |  | 2026-01-19 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-02-05 | Joaquin Alejandro Luduena WX1488820
DE039 | LP_DE039_Swap_MVS | Si |  | 2025-11-28 | 2025-11-28 | 2026-01-20 | 2026-01-20 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 |  | Miguel Angel Garcia Martinez 00881238
DE043 | LP_DE043_Swap_MVS | Si | 1.2 |  |  | 2025-12-08 | 2025-12-08 | zhaofeng 00917583 |  |  | 2025-12-22 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobada por Nico Trubbo el 22/12/2025. |  | 2026-02-06 | Claudio Romeo WX1379521
DE045 | LP_DE045_Swap_MVS | Si | 1.2 | 2026-01-12 | 2026-01-13 | 2026-01-19 | 2026-01-19 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-14 | 2026-05-28 | Miguel Angel Garcia Martinez 00881238
DE046 | LP_DE046_Swap_MVS | Si |  |  | 2026-06-02 | 2026-06-04 | 2026-06-04 | Joaquin Alejandro Luduena WX1488820 |  | 2026-06-04 |  | Joaquin Alejandro Luduena WX1488820
DE049 | LP_DE049_Swap_MVS | Si |  | 2026-02-09 | 2026-02-09 | 2026-02-12 | 2026-02-12 | Adrian Guzman Garcia 00881507 |  | 2026-02-11 | 2026-02-20 | Adrian Guzman Garcia 00881507 | [5 empty] | 2026-05-20 | Yes
DE062 | LP_DE062_Swap_MVS | Si
DE067 | LP_DE067_Swap_MVS | Si | 2.2 | 2026-01-27 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-29 | 2026-01-29 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
DE068 | LP_DE068_Swap_MVS | Si | 1.53 |  |  | 2025-11-30 | 2025-11-30 | zhaofeng 00917583 |  |  | 2026-01-19 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobado por Nico Trubbo el 02/01/2026. Aprobada por Ezequiel Fail el 19/01/2026. |  | 2026-02-05 | Tomas Ezequiel Sanchez WX1486917 |  |  |  | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
DE072 | LP_DE072_Swap_MVS | Si |  |  | 2026-06-02 | 2026-06-03 | 2026-06-03 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-06-04 |  | Tomas Ezequiel Sanchez WX1486917
DE304 | LP_DE304_Swap_MVS | Si |  | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-16 | 2026-03-20 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-20 | Yes
DEM99 | LP_DEM99_Swap_MVS | Si |  |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | David Encina WX1367993 |  | 2026-06-02 |  | David Encina WX1367993
DN001 | LP_DN001_Swap_MVS | Si |  | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-29 |  | Miguel Angel Garcia Martinez 00881238
DN002 | LP_DN002_Swap_MVS | Si |  |  |  | 2025-12-08 | 2025-12-08 | Elvia Carolina Cortes Garcia 00881509 |  |  | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-12 | David Encina WX1367993 |  |  | Yes
DN012 | LP_DN012_Swap_MVS | Si | 1.2 |  |  | 2026-01-06 | 2026-01-06 | zhaofeng 00917583 |  | 2026-02-20 | 2026-02-20 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917
DN014 | LP_DN014_Swap_MVS | Si | 1.2 | 2026-01-27 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-29 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
DN024 | LP_DN024_Swap_MVS | Si |  | 2026-01-14 | 2026-01-15 | 2026-01-20 | 2026-01-20 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-30 | 2026-01-30 | Miguel Angel Garcia Martinez 00881238 | Sin información |  | 2026-03-12 | David Encina WX1367993
DN025 | LP_DN025_Swap_MVS | Si | 1.2 | 2025-11-27 | 2025-11-28 | 2026-03-02 | 2026-03-02 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01 |  | Miguel Angel Garcia Martinez 00881238
DN026 | LP_DN026_Swap_MVS | Si | 1.2 | 2025-12-09 | 2025-12-10 | 2026-03-02 | 2026-03-02 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-11 | 2026-06-02 | Miguel Angel Garcia Martinez 00881238 | 02/06/2026: Se dio por aprobada por correo de Nico Trubbo.
DN027 | LP_DN027_Swap_MVS | Si
DN032 | LP_DN032_Swap_MVS | Si | 1.2 | 2025-12-09 | 2025-12-10 | 2026-01-19 | 2026-01-19 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-12 |  | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-12 | David Encina WX1367993
DN034 | LP_DN034_Swap_MVS | Si | 1.2 | 2025-12-09 | 2025-12-10 | 2026-01-19 | 2026-01-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-11 | 2026-05-28 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-20 | David Encina WX1367993
DN038 | LP_DN038_Swap_MVS | Si |  | 2025-11-27 | 2025-11-28 | 2026-01-19 | 2026-01-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-01
DN050 | LP_DN050_Swap_MVS | Si | 0.87 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-11 | Elvia Carolina Cortes Garcia 00881509 |  | 2025-12-11 | 2026-01-23 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobada por Pablo Buono el 23/01/2026. |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820
DN052 | LP_DN052_Swap_MVS | Si | 0.87 |  |  | 2025-12-14 | 2025-12-14 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-01-14 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobado por Pablo Buono el 14/01/2026. |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | Survey Pending
DS049 | LP_DS049_Swap_MVS | Si | 0.87 |  |  | 2026-04-28 | 2026-04-28 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-30 | 2026-05-11 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 2026-05-20 | Yes
DS050 | LP_DS050_Swap_MVS | Si | 0.87 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Joaquin Alejandro Luduena WX1488820 | No factible sitio híbrido consumo total 1#，3Kwatt#， solo se podría actualizar 4T4R 1 RRU 5512 o 1 RRU 5502. David Massesa. | 2026-04-29 | 2026-05-12 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 2026-05-20 | Yes
DW009 | LP_DW009_Swap_MVS | Si |  |  | 2026-04-24 |  |  | GSC |  | 2026-04-28 |  | GSC
DW011 | LP_DW011_Swap_MVS | Si |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-29 |  | Tomas Ezequiel Sanchez WX1486917
DW012 | LP_DW012_Swap_MVS | Si | 1.87 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-22 | 2026-02-02 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917
ARNQ0017 | NQ_ARNQ0017_FARM_Etapa1_MVS | [24 empty] | PPI Pending
ARNQ0026 | NQ_ARNQ0026_FARM_Etapa2_MVS | [24 empty] | Installed
ARNQ0047 | NQ_ARNQ0047_FARM_Etapa1_MVS | [24 empty] | Installed
ARNQ0087 | NQ_ARNQ0087_FARM_Etapa1_MVS | [24 empty] | Installed
ARNQ0403 | NQ_ARNQ0403_FARM_Etapa1_MVS | [24 empty] | Installed
ARNQ0487 | NQ_ARNQ0487_FARM_Etapa1_MVS | [24 empty] | Installed with Issue
QC003 | NQ_QC003_Swap_MVS | Si | [8 empty] | 2025-12-04 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943
QC005 | NQ_QC005_Swap_MVS | Si | [18 empty] | Etapa 01 | 03 | CVLINS05-01 pos 01 | Sala TX, 1er piso | 26 | Dismantled
QC007 | NQ_QC007_Swap_MVS | Si | 1.53 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2025-11-04 | zhaofeng 00917583 | RFI Ok | [7 empty] | Etapa 01 | 501 | NQNINS05-01 pos 03 | Sala TX01, 1er piso | 25 | Ready for Dismantle
QC012 | NQ_QC012_Swap_MVS | Si | [18 empty] | Etapa 01 | 03 | CVLINS05-01 pos 02 | Sala TX, 1er piso | 26 | Dismantled
QC013 | NQ_QC013_Swap_MVS | Si | 1.2 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-07 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-11-27 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 02 | 03 | CVLINS05-01 pos 03 | Sala TX, 1er piso | 26 | Dismantled
QC021 | NQ_QC021_Swap_MVS | Si | [17 empty] | Pending Subrark, no space available on RACK, the Rack will be installl by the customer | Etapa 01 | 01 | ABDINS05-01 pos 01 | Sala TX | 16 | Dismantled
QC024 | NQ_QC024_Swap_MVS | Si | [18 empty] | Etapa 01 | 04 | PININS05-01 pos 01 | Sala TX | 06 | Dismantled
QC037 | NQ_QC037_Swap_MVS | Si | 1.2 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2025-11-18 | zhaofeng 00917583 | RFI Ok | [12 empty] | Ready for Dismantle
QC044 | NQ_QC044_Swap_MVS | Si | [23 empty] | Ready for Dismantle
QC052 | NQ_QC052_Swap_MVS | Si | 1.87 |  |  | 2025-10-28 | 2025-10-28 | zhaofeng 00917583 |  |  | 2025-11-03 | Abraham Jesus Salas Marfil 00237943 | RFI Ok | [12 empty] | Dismantled
QC054 | NQ_QC054_Swap_MVS | Si | [23 empty] | Ready for Dismantle
QC055 | NQ_QC055_Swap_MVS | Si | [18 empty] | Etapa 01 | 501 | NQNINS05-01 pos 01 | Sala TX01, 1er piso | 25 | Ready for Dismantle
QC059 | NQ_QC059_Swap_MVS | Si | [18 empty] | Etapa 01 | 501 | NQNINS05-01 pos 02 | Sala TX01, 1er piso | 25 | Ready for Dismantle
QC074 | NQ_QC074_Swap_MVS | Si
QC099 | NQ_QC099_Swap_MVS | Si | [18 empty] | Etapa 01 | 02 | RLDINS05-01 pos 01 | Sala TX | 16 | Dismantled
QC105 | NQ_QC105_Swap_MVS | Si | 0.87 |  |  | 2025-10-28 | 2025-10-28 | zhaofeng 00917583 |  |  | 2025-11-28 | zhaofeng 00917583 | RFI Ok. COBRA
QC348 | NQ_QC348_Swap_MVS | Si | 1.53 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2026-05-04 | zhaofeng 00917583 | RFI Ok. Se subio ingenieria aprobada del proyecto PMF el 04/05/2026.
QCM39 | NQ_QCM39_Swap_MVS | Si
QE037 | NQ_QE037_Swap_MVS | Si | 1.2 | [7 empty] | 2025-11-26 | Arturo Gonzalo Antonio Cantu 00879903
QE039 | NQ_QE039_Swap_MVS | Si | 1.2 | [7 empty] | 2025-11-25 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
QE041 | NQ_QE041_Swap_MVS | Si | 1.53 |  |  | 2026-03-12 | 2026-03-12 | zhaofeng 00917583 |  |  | 2026-03-20 | Joaquin Alejandro Luduena WX1488820 | En fabricación#， listo entre 25 y 30 dias |  | 2026-03-20 | David Encina WX1367993
QE042 | NQ_QE042_Swap_MVS | Si | 0.87 | 2025-10-22 | 2025-10-23 | 2026-02-11 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-24 | 2026-03-05 | Miguel Angel Garcia Martinez 00881238 | Sin información |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-27 | Yes
QN017 | NQ_QN017_Swap_MVS | Si | 1.2 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-13 | Adrian Guzman Garcia 00881507 |  | 2025-11-13 |  | Adrian Guzman Garcia 00881507
QN026 | NQ_QN026_Swap_MVS | Si | 1.2 | 2025-11-13 | 2025-11-14 | 2025-11-14 | 2025-11-14 | David Encina WX1367993 |  | 2025-11-17 | 2025-12-09 | David Encina WX1367993 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
QN045 | NQ_QN045_Swap_MVS | Si |  |  |  | 2025-11-17 | 2025-11-17 | David Encina WX1367993 |  | 2025-11-19 | 2026-04-17 | David Encina WX1367993
QN082 | NQ_QN082_Swap_MVS | Si | 0.87 | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | Agustin Maria Bianchetti 00958351 |  | 2025-11-20 | 2025-12-03 | Daniel Horacio Rocabado WX1372513
QS007 | NQ_QS007_Swap_MVS | Si | 0.87 | 2025-11-05 | 2025-11-06 | 2025-12-19 | 2025-12-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-12-20 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 12 | VANINS05-01 pos 03 | Sala TX, P.B. | 10 | Dismantled
QS013 | NQ_QS013_Swap_MVS | Si | 1.87 | 2025-11-06 | 2025-11-07 | 2026-02-13 | 2026-02-13 | Adrian Guzman Garcia 00881507 |  | 2025-11-10 | 2026-03-20 | Adrian Guzman Garcia 00881507 | RFI Ok 20/02/2026: Aprobada por Nico Trubbo |  | 2026-03-20 | David Encina WX1367993
QS019 | NQ_QS019_Swap_MVS | Si | 1.53 | [7 empty] | 2026-04-17 | Arturo Gonzalo Antonio Cantu 00879903 | En stock. Guzmán Nacich |  | 2026-02-12 | Tomas Ezequiel Sanchez WX1486917
QS025 | NQ_QS025_Swap_MVS | Si | 1.2 | [7 empty] | 2026-04-17 | Daniel Horacio Rocabado WX1372513 | En stock. Guzmán Nacich |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
QS026 | NQ_QS026_Swap_MVS | Si | 0.87 | 2025-11-05 | 2025-11-06 | 2025-12-19 | 2025-12-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-12-20 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 12 | VANINS05-01 pos 04 | Sala TX, P.B. | 10 | Dismantled
QS027 | NQ_QS027_Swap_MVS | Si | 0.87 | 2025-11-05 | 2025-11-06 | 2025-12-04 | 2025-12-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-12-11 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 12 | VANINS05-01 pos 01 | Sala TX, P.B. | 10 | Dismantled
QS028 | NQ_QS028_Swap_MVS | Si | 0.87 |  |  | 2025-12-14 | 2025-12-14 | zhaofeng 00917583 |  |  | 2025-12-19 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. En fabricación. CIS Group |  | 2026-03-09 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | 12 | VANINS05-02 pos 01 | Sala TX, P.B. | 10 | Dismantled
QS029 | NQ_QS029_Swap_MVS | Si | 0.87 | 2025-11-05 | 2025-11-06 | 2025-12-17 | 2025-12-17 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-12-22 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 02 | 12 | VANINS05-02 pos 02 | Sala TX, P.B. | 10 | Dismantled
QS030 | NQ_QS030_Swap_MVS | Si | 0.87 |  |  | 2025-12-14 | 2025-12-14 | zhaofeng 00917583 |  |  | 2025-12-19 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. CIS Group | [7 empty] | Etapa 02 | 12 | VANINS05-02 pos 03 | Sala TX, P.B. | 10 | Dismantled
QS031 | NQ_QS031_Swap_MVS | Si | 0.87 |  |  | 2025-12-14 | 2025-12-14 | zhaofeng 00917583 |  |  | 2025-12-18 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. En stock. CIS Group | [7 empty] | Etapa 02 | 12 | VANINS05-02 pos 04 | Sala TX, P.B. | 10 | Dismantled
QS038 | NQ_QS038_Swap_MVS | Si | 1.2 |  |  | 2025-11-07 | 2025-11-07 | zhaofeng 00917583 |  |  | 2025-11-25 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok | [6 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
QS304 | NQ_QS304_Swap_MVS | Si | [8 empty] | 2026-01-14 | Arturo Gonzalo Antonio Cantu 00879903 | En fabricación. COBRA. Para ABRIL Aprobado por Pablo Buono el 14/01/2026. 20/01/2026: Se modificó la propuesta luego de aprobada para normalizar el sitio#， con instalacion de BBU en sitio QS004 y adecuacion de gabinetes. Aprobada por Pablo Buono el 23/01/2026. |  | 2026-02-27 | Tomas Ezequiel Sanchez WX1486917 |  |  |  | La Adecuacion para la graja la realizar el IM de SWAP | Etapa 01 | N/A | N/A | N/A | N/A
QW009 | NQ_QW009_Swap_MVS | Si | 1.2 |  |  | 2025-11-09 | 2025-11-09 | zhaofeng 00917583 |  |  | 2025-11-20 | Abraham Jesus Salas Marfil 00237943 | RFI Ok. Guzmán Nacich | [6 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
ARRN0050 | RN_ARRN0050_FARM_Etapa1_MVS |  |  |  |  | 2026-05-11 | 2026-05-11 | David Encina WX1367993 |  |  | 2026-05-15 | David Encina WX1367993
BM004 | SUR_179_BM004_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM506 | SUR_179_BM506_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM584 | SUR_179_BM584_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM749 | SUR_179_BM749_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM750 | SUR_179_BM750_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM751 | SUR_179_BM751_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM752 | SUR_179_BM752_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM805 | SUR_179_BM805_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM806 | SUR_179_BM806_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM808 | SUR_179_BM808_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM809 | SUR_179_BM809_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM600 | SUR_181_BM600_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM602 | SUR_181_BM602_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM603 | SUR_181_BM603_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM031 | SUR_184_BM031_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM102 | SUR_184_BM102_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM326 | SUR_184_BM326_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM385 | SUR_184_BM385_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM484 | SUR_184_BM484_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM510 | SUR_184_BM510_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM605 | SUR_184_BM605_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM606 | SUR_184_BM606_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM608 | SUR_184_BM608_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM609 | SUR_184_BM609_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM610 | SUR_184_BM610_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | SUR_184_BM611_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM699 | SUR_184_BM699_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM008 | SUR_185_BM008_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM013 | SUR_185_BM013_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM078 | SUR_185_BM078_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM306 | SUR_185_BM306_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM314 | SUR_185_BM314_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM379 | SUR_185_BM379_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM511 | SUR_185_BM511_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM512 | SUR_185_BM512_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM593 | SUR_185_BM593_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM731 | SUR_185_BM731_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM305 | SUR_186_BM305_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM312 | SUR_186_BM312_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM351 | SUR_186_BM351_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM513 | SUR_186_BM513_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM557 | SUR_186_BM557_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM561 | SUR_186_BM561_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM728 | SUR_186_BM728_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM730 | SUR_186_BM730_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM854 | SUR_186_BM854_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM855 | SUR_186_BM855_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM858 | SUR_186_BM858_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM927 | SUR_186_BM927_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM035 | SUR_187_BM035_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM051 | SUR_187_BM051_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM301 | SUR_187_BM301_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM724 | SUR_187_BM724_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM902 | SUR_187_BM902_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM037 | SUR_188_BM037_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM057 | SUR_188_BM057_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM061 | SUR_188_BM061_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM107 | SUR_188_BM107_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM303 | SUR_188_BM303_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM357 | SUR_188_BM357_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM527 | SUR_188_BM527_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM542 | SUR_188_BM542_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM550 | SUR_188_BM550_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM585 | SUR_188_BM585_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM725 | SUR_188_BM725_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM063 | SUR_189_BM063_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM068 | SUR_189_BM068_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM086 | SUR_189_BM086_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM304 | SUR_189_BM304_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM347 | SUR_189_BM347_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM520 | SUR_189_BM520_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM522 | SUR_189_BM522_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM523 | SUR_189_BM523_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM524 | SUR_189_BM524_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM554 | SUR_189_BM554_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM555 | SUR_189_BM555_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM697 | SUR_189_BM697_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM726 | SUR_189_BM726_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM050 | SUR_190_BM050_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM090 | SUR_190_BM090_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM308 | SUR_190_BM308_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM308 | SUR_190_BM308_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM310 | SUR_190_BM310_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM336 | SUR_190_BM336_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM344 | SUR_190_BM344_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM350 | SUR_190_BM350_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM378 | SUR_190_BM378_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM529 | SUR_190_BM529_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM002 | SUR_191_BM002_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM032 | SUR_191_BM032_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM111 | SUR_191_BM111_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM377 | SUR_191_BM377_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM411 | SUR_191_BM411_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM421 | SUR_191_BM421_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM515 | SUR_191_BM515_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM516 | SUR_191_BM516_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM517 | SUR_191_BM517_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM003 | SUR_192_BM003_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM011 | SUR_192_BM011_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM342 | SUR_197_BM342_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM408 | SUR_197_BM408_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM507 | SUR_197_BM507_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM508 | SUR_197_BM508_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM591 | SUR_197_BM591_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM592 | SUR_197_BM592_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM800 | SUR_197_BM800_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM801 | SUR_197_BM801_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM802 | SUR_197_BM802_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM804 | SUR_197_BM804_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM034 | SUR_198_BM034_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM704 | SUR_198_BM704_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM103 | SUR_199_BM103_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM129 | SUR_199_BM129_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM316 | SUR_199_BM316_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM329 | SUR_199_BM329_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM391 | SUR_199_BM391_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM638 | SUR_199_BM638_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM640 | SUR_199_BM640_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM642 | SUR_199_BM642_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM643 | SUR_199_BM643_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM778 | SUR_199_BM778_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM010 | SUR_200_BM010_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM091 | SUR_200_BM091_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM392 | SUR_200_BM392_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM645 | SUR_200_BM645_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM646 | SUR_200_BM646_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM773 | SUR_200_BM773_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM096 | SUR_201_BM096_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM319 | SUR_201_BM319_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM356 | SUR_201_BM356_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM396 | SUR_201_BM396_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM533 | SUR_201_BM533_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM534 | SUR_201_BM534_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM552 | SUR_201_BM552_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM633 | SUR_201_BM633_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM634 | SUR_201_BM634_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM635 | SUR_201_BM635_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM777 | SUR_201_BM777_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM838 | SUR_201_BM838_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM839 | SUR_201_BM839_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM375 | SUR_204_BM375_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM025 | SUR_205_BM025_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM104 | SUR_205_BM104_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM335 | SUR_205_BM335_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM359 | SUR_205_BM359_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM381 | SUR_205_BM381_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM382 | SUR_205_BM382_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM387 | SUR_205_BM387_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM390 | SUR_205_BM390_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM616 | SUR_205_BM616_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM618 | SUR_205_BM618_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM781 | SUR_205_BM781_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM040 | SUR_206_BM040_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM343 | SUR_206_BM343_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM364 | SUR_206_BM364_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM365 | SUR_206_BM365_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM563 | SUR_206_BM563_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM626 | SUR_206_BM626_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM631 | SUR_206_BM631_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM632 | SUR_206_BM632_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM779 | SUR_206_BM779_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM093 | SUR_207_BM093_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM320 | SUR_207_BM320_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM369 | SUR_207_BM369_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM388 | SUR_207_BM388_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM424 | SUR_207_BM424_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM551 | SUR_207_BM551_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM622 | SUR_207_BM622_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM623 | SUR_207_BM623_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM625 | SUR_207_BM625_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM835 | SUR_207_BM835_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM106 | SUR_208_BM106_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM141 | SUR_329_BM141_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM393 | SUR_329_BM393_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM501 | SUR_329_BM501_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM767 | SUR_329_BM767_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM768 | SUR_329_BM768_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM080 | SUR_330_BM080_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM081 | SUR_330_BM081_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM360 | SUR_330_BM360_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM380 | SUR_330_BM380_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM415 | SUR_330_BM415_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM462 | SUR_330_BM462_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM715 | SUR_330_BM715_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM732 | SUR_330_BM732_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM811 | SUR_330_BM811_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM831 | SUR_330_BM831_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM840 | SUR_330_BM840_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS014 | SUR_501_JS014_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS051 | SUR_501_JS051_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS052 | SUR_501_JS052_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MO002 | SUR_514_MO002_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS011 | SUR_514_MS011_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS019 | SUR_514_MS019_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS023 | SUR_514_MS023_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS028 | SUR_514_MS028_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS030 | SUR_514_MS030_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS032 | SUR_514_MS032_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS035 | SUR_514_MS035_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS038 | SUR_514_MS038_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS041 | SUR_514_MS041_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS042 | SUR_514_MS042_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS044 | SUR_514_MS044_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS062 | SUR_514_MS062_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS063 | SUR_514_MS063_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS122 | SUR_514_MS122_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS001 | SUR_515_MS001_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS005 | SUR_515_MS005_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS006 | SUR_515_MS006_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS009 | SUR_515_MS009_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS017 | SUR_515_MS017_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS054 | SUR_515_MS054_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS059 | SUR_515_MS059_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS061 | SUR_515_MS061_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS066 | SUR_515_MS066_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS067 | SUR_515_MS067_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSM24 | SUR_515_MSM24_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN006 | SUR_516_MN006_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN022 | SUR_516_MN022_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN054 | SUR_516_MN054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN091 | SUR_516_MN091_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN149 | SUR_516_MN149_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN220 | SUR_516_MN220_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN338 | SUR_516_MN338_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MO065 | SUR_516_MO065_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O006 | SUR_519_A33-O006_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O058 | SUR_519_A33-O058_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O059 | SUR_519_A33-O059_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O111 | SUR_519_A33-O111_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O112 | SUR_519_A33-O112_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O143 | SUR_519_A33-O143_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O177 | SUR_519_A33-O177_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O195 | SUR_519_A33-O195_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O384 | SUR_519_A33-O384_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O389 | SUR_519_A33-O389_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O737 | SUR_519_A33-O737_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC024 | SUR_519_MC024_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC028 | SUR_519_MC028_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC037 | SUR_519_MC037_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC054 | SUR_519_MC054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC077 | SUR_519_MC077_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC126 | SUR_519_MC126_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC301 | SUR_519_MC301_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC303 | SUR_519_MC303_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC345 | SUR_519_MC345_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC002 | SUR_521_MC002_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC005 | SUR_521_MC005_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC025 | SUR_521_MC025_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC066 | SUR_521_MC066_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC098 | SUR_521_MC098_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC147 | SUR_521_MC147_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC171 | SUR_521_MC171_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC333 | SUR_521_MC333_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC350 | SUR_521_MC350_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC035 | SUR_523_MC035_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC041 | SUR_523_MC041_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC080 | SUR_523_MC080_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC091 | SUR_523_MC091_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC093 | SUR_523_MC093_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC094 | SUR_523_MC094_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC300 | SUR_523_MC300_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC401 | SUR_523_MC401_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC403 | SUR_523_MC403_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC409 | SUR_523_MC409_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC310 | SUR_524_MC310_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC405 | SUR_524_MC405_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN071 | SUR_524_MN071_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN086 | SUR_524_MN086_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN099 | SUR_524_MN099_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN113 | SUR_524_MN113_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O092 | SUR_529_A32-O092_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O094 | SUR_529_A32-O094_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O101 | SUR_529_A32-O101_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O148 | SUR_529_A32-O148_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O403 | SUR_529_A32-O403_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O425 | SUR_529_A32-O425_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS010 | SUR_529_MS010_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS012 | SUR_529_MS012_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS015 | SUR_529_MS015_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS020 | SUR_529_MS020_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS025 | SUR_529_MS025_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS033 | SUR_529_MS033_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS034 | SUR_529_MS034_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS036 | SUR_529_MS036_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS051 | SUR_529_MS051_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS053 | SUR_529_MS053_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS109 | SUR_529_MS109_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS304 | SUR_529_MS304_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS322 | SUR_529_MS322_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS002 | SUR_531_JS002_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS012 | SUR_531_JS012_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS015 | SUR_531_JS015_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS017 | SUR_531_JS017_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS026 | SUR_531_JS026_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS027 | SUR_531_JS027_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS028 | SUR_531_JS028_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS033 | SUR_531_JS033_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS037 | SUR_531_JS037_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS039 | SUR_531_JS039_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS040 | SUR_531_JS040_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS045 | SUR_531_JS045_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS101 | SUR_531_JS101_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC015 | SUR_533_MC015_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC016 | SUR_533_MC016_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC072 | SUR_533_MC072_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC092 | SUR_533_MC092_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC315 | SUR_533_MC315_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC322 | SUR_533_MC322_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O061 | SUR_534_A33-O061_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC036 | SUR_534_MC036_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC065 | SUR_534_MC065_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC076 | SUR_534_MC076_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC318 | SUR_534_MC318_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B644 | SUR_B772M_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B455 | SUR_B985M_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM103 | SUR_BM103_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM392 | SUR_BM392_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM640 | SUR_BM640_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM642 | SUR_BM642_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM643 | SUR_BM643_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM778 | SUR_BM778_Opt |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B323 | A38-B323_A38-B323_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS011 | AMBA_100_CS011_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS011 | AMBA_100_CS011_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS188 | AMBA_100_CS188_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS188 | AMBA_100_CS188_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS263 | AMBA_100_CS263_RSH_OPT |  | 1.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS263 | AMBA_100_CS263_RSH_OPT_5G |  | 1.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS296 | AMBA_100_CS296_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS296 | AMBA_100_CS296_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS131 | AMBA_101_KS131_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS195 | AMBA_101_KS195_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS280 | AMBA_101_KS280_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS060 | AMBA_104_BS060_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS107 | AMBA_104_BS107_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS107 | AMBA_104_BS107_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS162 | AMBA_104_BS162_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS219 | AMBA_104_BS219_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS308 | AMBA_104_BS308_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS390 | AMBA_104_BS390_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS221 | AMBA_104_KS221_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO215 | AMBA_110_KO215_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO055 | AMBA_111_KO055_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO207 | AMBA_111_KO207_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN214 | AMBA_115_KN214_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN269 | AMBA_116_KN269_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO050 | AMBA_116_KO050_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN262 | AMBA_118_CN262_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN262 | AMBA_118_CN262_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN264 | AMBA_118_CN264_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN264 | AMBA_118_CN264_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN301 | AMBA_118_CN301_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN301 | AMBA_118_CN301_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN313 | AMBA_118_CN313_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN313 | AMBA_118_CN313_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN114 | AMBA_125_KN114_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN118 | AMBA_126_KN118_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN087 | AMBA_127_KN087_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN194 | AMBA_129_CN194_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN210 | AMBA_129_CN210_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN482 | AMBA_129_CN482_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN482 | AMBA_129_CN482_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN483 | AMBA_129_CN483_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN483 | AMBA_129_CN483_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN142 | AMBA_136_CN142_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN445 | AMBA_137_CN445_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN446 | AMBA_137_CN446_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN446 | AMBA_137_CN446_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS073 | AMBA_137_CS073_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS222 | AMBA_137_CS222_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS222 | AMBA_137_CS222_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS231 | AMBA_137_CS231_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN027 | AMBA_138_CN027_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN476 | AMBA_139_CN476_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS276 | AMBA_140_CS276_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN252 | AMBA_144_CN252_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN357 | AMBA_144_CN357_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN357 | AMBA_144_CN357_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN467 | AMBA_144_CN467_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN467 | AMBA_144_CN467_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN172 | AMBA_146_CN172_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN234 | AMBA_146_CN234_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN234 | AMBA_146_CN234_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN236 | AMBA_146_CN236_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN300 | AMBA_146_CN300_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN300 | AMBA_146_CN300_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN012 | AMBA_147_CN012_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN012 | AMBA_147_CN012_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN296 | AMBA_147_CN296_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN296 | AMBA_147_CN296_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN299 | AMBA_147_CN299_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN299 | AMBA_147_CN299_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN810 | AMBA_147_CN810_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN347 | AMBA_149_CN347_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN186 | AMBA_150_CN186_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN186 | AMBA_150_CN186_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN227 | AMBA_150_CN227_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN227 | AMBA_150_CN227_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN348 | AMBA_150_CN348_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN348 | AMBA_150_CN348_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN378 | AMBA_150_CN378_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN378 | AMBA_150_CN378_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN405 | AMBA_151_CN405_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN037 | AMBA_153_CN037_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN202 | AMBA_153_CN202_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN232 | AMBA_153_CN232_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN233 | AMBA_153_CN233_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN240 | AMBA_153_CN240_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN324 | AMBA_153_CN324_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN325 | AMBA_153_CN325_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN425 | AMBA_153_CN425_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN453 | AMBA_153_CN453_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN206 | AMBA_154_CN206_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN248 | AMBA_154_CN248_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN294 | AMBA_154_CN294_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN311 | AMBA_154_CN311_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN409 | AMBA_154_CN409_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN046 | AMBA_157_CN046_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN250 | AMBA_157_CN250_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN275 | AMBA_157_CN275_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN293 | AMBA_157_CN293_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN216 | AMBA_158_CN216_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN372 | AMBA_158_CN372_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN491 | AMBA_158_CN491_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS001 | AMBA_164_CS001_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS001 | AMBA_164_CS001_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS003 | AMBA_164_CS003_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS167 | AMBA_164_CS167_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS167 | AMBA_164_CS167_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS203 | AMBA_164_CS203_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS203 | AMBA_164_CS203_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS221 | AMBA_164_CS221_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS221 | AMBA_164_CS221_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM034 | AMBA_165_CM034_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM034 | AMBA_165_CM034_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN034 | AMBA_165_CN034_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN034 | AMBA_165_CN034_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN205 | AMBA_165_CN205_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN205 | AMBA_165_CN205_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS331 | AMBA_167_CS331_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS331 | AMBA_167_CS331_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS334 | AMBA_167_CS334_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS334 | AMBA_167_CS334_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS337 | AMBA_167_CS337_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS337 | AMBA_167_CS337_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS508 | AMBA_167_CS508_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS508 | AMBA_167_CS508_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU045 | AMBA_167_CU045_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU045 | AMBA_167_CU045_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM005 | AMBA_168_CM005_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU076 | AMBA_168_CU076_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU081 | AMBA_168_CU081_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS097 | AMBA_170_CS097_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS210 | AMBA_170_CS210_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS002 | AMBA_171_CS002_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS029 | AMBA_171_CS029_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS127 | AMBA_171_CS127_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS133 | AMBA_171_CS133_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS136 | AMBA_171_CS136_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS219 | AMBA_171_CS219_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS272 | AMBA_171_CS272_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS339 | AMBA_171_CS339_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS160 | AMBA_172_CS160_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS160 | AMBA_172_CS160_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS187 | AMBA_172_CS187_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS187 | AMBA_172_CS187_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS294 | AMBA_172_CS294_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS294 | AMBA_172_CS294_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS352 | AMBA_172_CS352_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS352 | AMBA_172_CS352_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS168 | AMBA_173_CS168_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS168 | AMBA_173_CS168_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS273 | AMBA_173_CS273_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS273 | AMBA_173_CS273_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS306 | AMBA_173_CS306_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS306 | AMBA_173_CS306_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS105 | AMBA_178_CS105_RSH_OPT |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS105 | AMBA_178_CS105_RSH_OPT_4G |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS170 | AMBA_178_CS170_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS175 | AMBA_178_CS175_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS175 | AMBA_178_CS175_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS190 | AMBA_178_CS190_RSH_OPT |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS190 | AMBA_178_CS190_RSH_OPT_4G |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS293 | AMBA_178_CS293_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS293 | AMBA_178_CS293_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS347 | AMBA_178_CS347_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS347 | AMBA_178_CS347_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS154 | AMBA_179_KS154_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS174 | AMBA_179_KS174_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS464 | AMBA_179_KS464_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS144 | AMBA_181_BS144_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS326 | AMBA_183_KS326_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS188 | AMBA_187_KS188_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS189 | AMBA_187_KS189_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS293 | AMBA_187_KS293_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS097 | AMBA_188_BS097_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS096 | AMBA_190_BS096_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS185 | AMBA_190_KS185_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS203 | AMBA_190_KS203_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS310 | AMBA_190_KS310_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS102 | AMBA_194_BS102_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS176 | AMBA_194_BS176_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS372 | AMBA_194_BS372_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS119 | AMBA_195_KS119_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS302 | AMBA_195_KS302_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS378 | AMBA_195_KS378_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS436 | AMBA_195_KS436_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS702 | AMBA_195_KS702_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS111 | AMBA_196_KS111_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS184 | AMBA_196_KS184_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS325 | AMBA_196_KS325_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS607 | AMBA_196_KS607_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS081 | AMBA_198_BS081_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS069 | AMBA_199_BS069_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS093 | AMBA_199_BS093_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS094 | AMBA_199_BS094_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS098 | AMBA_199_BS098_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS174 | AMBA_199_BS174_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS194 | AMBA_199_BS194_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS195 | AMBA_199_BS195_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP029 | AMBA_200_LP029_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC007 | AMBA_203_LC007_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC059 | AMBA_203_LC059_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC044 | AMBA_204_LC044_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC001 | AMBA_205_LC001_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC040 | AMBA_207_LC040_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC008 | AMBA_211_LC008_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC029 | AMBA_211_LC029_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC035 | AMBA_211_LC035_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC054 | AMBA_211_LC054_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP086 | AMBA_211_LP086_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BO950 | AMBA_213_BO950_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP112 | AMBA_217_LP112_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN156 | AMBA_219_BN156_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN511 | AMBA_220_BN511_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS192 | AMBA_227_KS192_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS286 | AMBA_227_KS286_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS461 | AMBA_228_KS461_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP015 | AMBA_239_LP015_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP111 | AMBA_239_LP111_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS043 | AMBA_256_BS043_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS128 | AMBA_256_BS128_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS129 | AMBA_256_BS129_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS129 | AMBA_256_BS129_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS130 | AMBA_256_BS130_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS130 | AMBA_256_BS130_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS205 | AMBA_256_BS205_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS206 | AMBA_256_BS206_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS207 | AMBA_256_BS207_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS260 | AMBA_256_BS260_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN287 | AMBA_40_BN287_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN458 | AMBA_41_BN458_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN127 | AMBA_55_BN127_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPU351 | AMBA_56_NPU351_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO032 | AMBA_58_KO032_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN045 | AMBA_64_KN045_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN045 | AMBA_64_KN045_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO197 | AMBA_78_KO197_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS052 | AMBA_80_BS052_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS052 | AMBA_80_BS052_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS071 | AMBA_80_BS071_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS213 | AMBA_80_BS213_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS253 | AMBA_80_BS253_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS253 | AMBA_80_BS253_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS287 | AMBA_80_BS287_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS293 | AMBA_80_BS293_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS294 | AMBA_80_BS294_RSH_OPT |  | 0.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS294 | AMBA_80_BS294_RSH_OPT_4G |  | 0.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS297 | AMBA_80_BS297_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS090 | AMBA_82_BS090_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS116 | AMBA_82_BS116_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS117 | AMBA_82_BS117_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS117 | AMBA_82_BS117_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS158 | AMBA_82_BS158_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS159 | AMBA_82_BS159_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS208 | AMBA_82_BS208_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS254 | AMBA_82_BS254_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS254 | AMBA_82_BS254_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS257 | AMBA_82_BS257_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS257 | AMBA_82_BS257_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS289 | AMBA_82_BS289_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS289 | AMBA_82_BS289_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS291 | AMBA_82_BS291_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS077 | AMBA_83_BS077_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS110 | AMBA_83_BS110_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS110 | AMBA_83_BS110_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS235 | AMBA_83_BS235_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS239 | AMBA_83_BS239_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS249 | AMBA_83_BS249_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS251 | AMBA_83_BS251_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS304 | AMBA_83_BS304_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS306 | AMBA_83_BS306_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS307 | AMBA_83_BS307_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS107 | AMBA_84_CS107_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS149 | AMBA_84_CS149_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS152 | AMBA_84_CS152_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS153 | AMBA_84_CS153_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS241 | AMBA_84_CS241_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS241 | AMBA_84_CS241_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS309 | AMBA_84_CS309_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS311 | AMBA_84_CS311_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS311 | AMBA_84_CS311_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS312 | AMBA_84_CS312_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS313 | AMBA_84_CS313_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO037 | AMBA_86_KO037_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO044 | AMBA_86_KO044_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO193 | AMBA_86_KO193_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS472 | AMBA_86_KS472_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS147 | AMBA_88_CS147_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS147 | AMBA_88_CS147_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS148 | AMBA_88_CS148_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS148 | AMBA_88_CS148_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS230 | AMBA_88_CS230_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS287 | AMBA_88_CS287_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN449 | AMBA_89_CN449_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS154 | AMBA_89_CS154_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS158 | AMBA_89_CS158_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS158 | AMBA_89_CS158_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS200 | AMBA_89_CS200_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS200 | AMBA_89_CS200_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS286 | AMBA_89_CS286_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS286 | AMBA_89_CS286_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS116 | AMBA_90_KS116_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS200 | AMBA_90_KS200_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS300 | AMBA_90_KS300_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS134 | AMBA_91_BS134_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS334 | AMBA_91_KS334_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS196 | AMBA_92_BS196_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS159 | AMBA_93_KS159_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS159 | AMBA_93_KS159_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS202 | AMBA_93_KS202_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS343 | AMBA_93_KS343_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS425 | AMBA_93_KS425_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS234 | AMBA_94_BS234_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS127 | AMBA_95_KS127_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS134 | AMBA_95_KS134_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS149 | AMBA_95_KS149_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS204 | AMBA_95_KS204_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS276 | AMBA_95_KS276_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS428 | AMBA_95_KS428_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS033 | AMBA_97_CS033_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS151 | AMBA_97_CS151_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS198 | AMBA_97_CS198_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS198 | AMBA_97_CS198_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS018 | AMBA_97_KS018_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS018 | AMBA_97_KS018_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS014 | AMBA_98_CS014_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS014 | AMBA_98_CS014_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS120 | AMBA_98_CS120_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS120 | AMBA_98_CS120_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS143 | AMBA_98_CS143_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS143 | AMBA_98_CS143_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS146 | AMBA_98_CS146_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS146 | AMBA_98_CS146_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS330 | AMBA_98_CS330_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS330 | AMBA_98_CS330_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS355 | AMBA_98_CS355_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS355 | AMBA_98_CS355_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A42-A051 | AMBA_A42-A051_Mod_TA | Si |  | N/A |  | N/A
A42-B169 | AMBA_A42-B169_Mod_TA | Si |  | N/A |  | N/A | 2026-05-28 | Joaquin Alejandro Luduena WX1488820
A42-B777 | AMBA_A42-B777_Mod_TA | Si |  | N/A |  | N/A | 2026-05-28 | Joaquin Alejandro Luduena WX1488820
A42-B908 | AMBA_A42-B908_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-05-28 | Tomas Ezequiel Sanchez WX1486917
BC172 | AMBA_BC172_Swap_MVS | Si
BH062 | AMBA_BH062_Swap_MVS | Si | 1.53 | 2026-04-27 | 2026-04-27 | 2026-04-29 | 2026-04-29 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-29 | 2026-05-11 | Miguel Angel Garcia Martinez 00881238
BN078 | AMBA_BN078_Swap_MVS | Si
BN100 | AMBA_BN100_Swap_MVS | Si
BN105 | AMBA_BN105_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BN142 | AMBA_BN142_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BN149 | AMBA_BN149_Swap_MVS | Si
BN152 | AMBA_BN152_Swap_MVS | Si
BN155 | AMBA_BN155_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BN156 | AMBA_BN156_Swap_MVS | Si
BN181 | AMBA_BN181_Swap_MVS | Si
BN208 | AMBA_BN208_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BN209 | AMBA_BN209_Swap_MVS | Si | [17 empty] | Wicaps
BN215 | AMBA_BN215_Swap_MVS | Si | [17 empty] | Wicaps
BN233 | AMBA_BN233_Swap_MVS | Si | [17 empty] | Wicaps
BN287 | AMBA_BN287_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BN288 | AMBA_BN288_Swap_MVS | Si | [17 empty] | Wicaps
BN289 | AMBA_BN289_Swap_MVS | Si | [17 empty] | Wicaps
BN303 | AMBA_BN303_Swap_MVS | Si | [17 empty] | Wicaps
BN306 | AMBA_BN306_Swap_MVS | Si | [17 empty] | Wicaps
BN308 | AMBA_BN308_Swap_MVS | Si | [17 empty] | Wicaps
BN316 | AMBA_BN316_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BN335 | AMBA_BN335_Swap_MVS | Si | [17 empty] | Wicaps
BN340 | AMBA_BN340_Swap_MVS | Si | [17 empty] | Wicaps
BN345 | AMBA_BN345_Swap_MVS | Si
BN397 | AMBA_BN397_Swap_MVS | Si | [17 empty] | Wicaps
BN400 | AMBA_BN400_Swap_MVS | Si
BN404 | AMBA_BN404_Swap_MVS | Si | [17 empty] | Wicaps
BN407 | AMBA_BN407_Swap_MVS | Si | [17 empty] | Wicaps
BN408 | AMBA_BN408_Swap_MVS | Si | [17 empty] | Wicaps
BN416 | AMBA_BN416_Swap_MVS | Si
BN430 | AMBA_BN430_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
BN432 | AMBA_BN432_Swap_MVS | Si | [17 empty] | Wicaps
BN446 | AMBA_BN446_Swap_MVS | Si | [17 empty] | Wicaps
BN448 | AMBA_BN448_Swap_MVS | Si | [17 empty] | Wicaps
BN454 | AMBA_BN454_Swap_MVS | Si | [17 empty] | Wicaps
BN456 | AMBA_BN456_Swap_MVS | Si
BN458 | AMBA_BN458_Swap_MVS | Si | [17 empty] | Wicaps
BN460 | AMBA_BN460_Swap_MVS | Si | [17 empty] | Wicaps
BN461 | AMBA_BN461_Swap_MVS | Si | [17 empty] | Wicaps
BN466 | AMBA_BN466_Swap_MVS | Si
BN468 | AMBA_BN468_Swap_MVS | Si | [17 empty] | Wicaps
BN471 | AMBA_BN471_Swap_MVS | Si | [17 empty] | Wicaps
BN473 | AMBA_BN473_Swap_MVS | Si
BN511 | AMBA_BN511_Swap_MVS | Si
BO031 | AMBA_BO031_Swap_MVS | Si
BO035 | AMBA_BO035_Swap_MVS | Si
BO045 | AMBA_BO045_Swap_MVS | Si
BO049 | AMBA_BO049_Swap_MVS | Si
BO121 | AMBA_BO121_Swap_MVS | Si
BO137 | AMBA_BO137_Swap_MVS | Si
BO148 | AMBA_BO148_Swap_MVS | Si
BO191 | AMBA_BO191_Swap_MVS | Si
BO219 | AMBA_BO219_Swap_MVS | Si
BO287 | AMBA_BO287_Swap_MVS | Si
BO318 | AMBA_BO318_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO325 | AMBA_BO325_Swap_MVS | Si
BO345 | AMBA_BO345_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO348 | AMBA_BO348_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO349 | AMBA_BO349_Swap_MVS | Si
BO351 | AMBA_BO351_Swap_MVS | Si
BO352 | AMBA_BO352_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO356 | AMBA_BO356_Swap_MVS | Si
BO360 | AMBA_BO360_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO361 | AMBA_BO361_Swap_MVS | Si
BO364 | AMBA_BO364_Swap_MVS | Si
BO366 | AMBA_BO366_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO368 | AMBA_BO368_Swap_MVS | Si
BO386 | AMBA_BO386_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO387 | AMBA_BO387_Swap_MVS | Si
BO388 | AMBA_BO388_Swap_MVS | Si
BO427 | AMBA_BO427_Swap_MVS | Si
BO438 | AMBA_BO438_Swap_MVS | Si
BO441 | AMBA_BO441_Swap_MVS | Si
BO442 | AMBA_BO442_Swap_MVS | Si
BO443 | AMBA_BO443_Swap_MVS | Si
BO445 | AMBA_BO445_Swap_MVS | Si
BO451 | AMBA_BO451_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO452 | AMBA_BO452_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO453 | AMBA_BO453_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO454 | AMBA_BO454_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO455 | AMBA_BO455_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO456 | AMBA_BO456_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO457 | AMBA_BO457_Swap_MVS | Si
BO459 | AMBA_BO459_Swap_MVS | Si |  | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-11 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-12
BO460 | AMBA_BO460_Swap_MVS | Si
BO461 | AMBA_BO461_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO462 | AMBA_BO462_Swap_MVS | Si
BO463 | AMBA_BO463_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO464 | AMBA_BO464_Swap_MVS | Si
BO465 | AMBA_BO465_Swap_MVS | Si
BO468 | AMBA_BO468_Swap_MVS | Si
BO469 | AMBA_BO469_Swap_MVS | Si
BO473 | AMBA_BO473_Swap_MVS | Si
BO477 | AMBA_BO477_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO478 | AMBA_BO478_Swap_MVS | Si
BO480 | AMBA_BO480_Swap_MVS | Si
BO482 | AMBA_BO482_Swap_MVS | Si
BO484 | AMBA_BO484_Swap_MVS | Si
BO490 | AMBA_BO490_Swap_MVS | Si
BO812 | AMBA_BO812_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO813 | AMBA_BO813_Swap_MVS | Si
BO814 | AMBA_BO814_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO815 | AMBA_BO815_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BO828 | AMBA_BO828_Swap_MVS | Si
BO829 | AMBA_BO829_Swap_MVS | Si
BO833 | AMBA_BO833_Swap_MVS | Si
BO835 | AMBA_BO835_Swap_MVS | Si
BO837 | AMBA_BO837_Swap_MVS | Si
BO839 | AMBA_BO839_Swap_MVS | Si
BO843 | AMBA_BO843_Swap_MVS | Si
BO867 | AMBA_BO867_Swap_MVS | Si
BO868 | AMBA_BO868_Swap_MVS | Si
BO872 | AMBA_BO872_Swap_MVS | Si
BO889 | AMBA_BO889_Swap_MVS | Si
BO910 | AMBA_BO910_Swap_MVS | Si
BO921 | AMBA_BO921_Swap_MVS | Si
BS043 | AMBA_BS043_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS062 | AMBA_BS062_Swap_MVS | Si | [23 empty] | Dismantled
BS090 | AMBA_BS090_Swap_MVS | Si | [17 empty] | No se logró retirar la BBU ya que la misma estaba atrapada en el rack por instalaciones posteriores. | [5 empty] | Ready for Dismantle
BS094 | AMBA_BS094_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS097 | AMBA_BS097_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS102 | AMBA_BS102_Swap_MVS | Si
BS113 | AMBA_BS113_Swap_MVS | Si | [18 empty] | Etapa 01 | 20 | MGRINS05-01 pos 03 | Sala CX 02 P.B. | 23 | Dismantled
BS117 | AMBA_BS117_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS128 | AMBA_BS128_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS134 | AMBA_BS134_Swap_MVS | Si
BS227 | AMBA_BS227_Swap_MVS | Si | [12 empty] | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
BS238 | AMBA_BS238_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS352 | AMBA_BS352_Swap_MVS | Si | [23 empty] | PPI Approved
KN083 | AMBA_KN083_Swap_MVS | Si | [19 empty] | 04 | TTIINS05-01 pos 02 | Sala TX01, 1er Piso | 21 | Ready for Dismantle
KN085 | AMBA_KN085_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN086 | AMBA_KN086_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN087 | AMBA_KN087_Swap_MVS | Si | [8 empty] | 2026-03-23 | David Encina WX1367993 | [13 empty] | Ready for Dismantle
KN106 | AMBA_KN106_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN126 | AMBA_KN126_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN154 | AMBA_KN154_Swap_MVS | Si
KN175 | AMBA_KN175_Swap_MVS | Si | [17 empty] | Wicaps
KN202 | AMBA_KN202_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KN222 | AMBA_KN222_Swap_MVS | Si
KN236 | AMBA_KN236_Swap_MVS | Si | [17 empty] | Wicaps
KN237 | AMBA_KN237_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KN239 | AMBA_KN239_Swap_MVS | Si | [17 empty] | Wicaps
KN240 | AMBA_KN240_Swap_MVS | Si | [17 empty] | Wicaps
KN247 | AMBA_KN247_Swap_MVS | Si | [17 empty] | Wicaps
KN253 | AMBA_KN253_Swap_MVS | Si | [17 empty] | Wicaps
KN254 | AMBA_KN254_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN260 | AMBA_KN260_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN262 | AMBA_KN262_Swap_MVS | Si
KN273 | AMBA_KN273_Swap_MVS | Si
KN274 | AMBA_KN274_Swap_MVS | Si
KN285 | AMBA_KN285_Swap_MVS | Si | [23 empty] | PPI Approved
KN288 | AMBA_KN288_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN291 | AMBA_KN291_Swap_MVS | Si | [17 empty] | Wicaps*
KN295 | AMBA_KN295_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN296 | AMBA_KN296_Swap_MVS | Si | [17 empty] | Wicaps* | [5 empty] | Survey Done
KN297 | AMBA_KN297_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN300 | AMBA_KN300_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN303 | AMBA_KN303_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KN306 | AMBA_KN306_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN307 | AMBA_KN307_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN309 | AMBA_KN309_Swap_MVS | Si | [17 empty] | Wicaps
KN310 | AMBA_KN310_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN311 | AMBA_KN311_Swap_MVS | Si | [17 empty] | Wicaps
KN313 | AMBA_KN313_Swap_MVS | Si | [17 empty] | Wicaps* | [5 empty] | Survey Done
KN314 | AMBA_KN314_Swap_MVS | Si | [17 empty] | Wicaps
KN318 | AMBA_KN318_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN321 | AMBA_KN321_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN329 | AMBA_KN329_Swap_MVS | Si | [17 empty] | Wicaps
KN330 | AMBA_KN330_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN345 | AMBA_KN345_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN346 | AMBA_KN346_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN351 | AMBA_KN351_Swap_MVS | Si | [23 empty] | Survey Done
KN352 | AMBA_KN352_Swap_MVS | Si | [17 empty] | Wicaps
KN356 | AMBA_KN356_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN359 | AMBA_KN359_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN369 | AMBA_KN369_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN376 | AMBA_KN376_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KO037 | AMBA_KO037_Swap_MVS | Si
KO058 | AMBA_KO058_Swap_MVS | Si
KO180 | AMBA_KO180_Swap_MVS | Si |  | NA | NA | NA | NA | NA
KO181 | AMBA_KO181_Swap_MVS | Si |  | NA | NA | NA | NA | NA
KO183 | AMBA_KO183_Swap_MVS | Si
KO184 | AMBA_KO184_Swap_MVS | Si
KO188 | AMBA_KO188_Swap_MVS | Si
KO200 | AMBA_KO200_Swap_MVS | Si | [23 empty] | PPI Approved
KO212 | AMBA_KO212_Swap_MVS | Si
KO214 | AMBA_KO214_Swap_MVS | Si | [18 empty] | Etapa 01 |  |  |  |  | Ready for Dismantle
KO234 | AMBA_KO234_Swap_MVS | Si
KO243 | AMBA_KO243_Swap_MVS | Si
KO256 | AMBA_KO256_Swap_MVS | Si | [23 empty] | PPI Approved
KO901 | AMBA_KO901_Swap_MVS | Si |  | NA | NA | NA | NA | NA
KO904 | AMBA_KO904_Swap_MVS | Si
KO906 | AMBA_KO906_Swap_MVS | Si
KO908 | AMBA_KO908_Swap_MVS | Si
KO909 | AMBA_KO909_Swap_MVS | Si
KO910 | AMBA_KO910_Swap_MVS | Si
KO911 | AMBA_KO911_Swap_MVS | Si
KO912 | AMBA_KO912_Swap_MVS | Si
KO914 | AMBA_KO914_Swap_MVS | Si
KO915 | AMBA_KO915_Swap_MVS | Si
KO918 | AMBA_KO918_Swap_MVS | Si
KS020 | AMBA_KS020_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KS063 | AMBA_KS063_Swap_MVS | Si | [19 empty] | 06 | EDRINS05-01 pos 02 | Sala TX, 1er Piso | 11
KS069 | AMBA_KS069_Swap_MVS | Si | [18 empty] | Etapa 01 |  |  |  |  | Ready for Dismantle
KS082 | AMBA_KS082_Swap_MVS | Si | [18 empty] | Etapa 01 |  |  |  |  | Ready for Dismantle
KS116 | AMBA_KS116_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KS118 | AMBA_KS118_Swap_MVS | Si
KS120 | AMBA_KS120_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KS172 | AMBA_KS172_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KS306 | AMBA_KS306_Swap_MVS | Si | [23 empty] | PPI Approved
KS364 | AMBA_KS364_Swap_MVS | Si | [19 empty] | 06 | EDRINS05-01 pos 04 | Sala TX, 1er Piso | 11
KS432 | AMBA_KS432_Swap_MVS | Si
KS642 | AMBA_KS642_Swap_MVS | Si | [23 empty] | PPI Approved
LC008 | AMBA_LC008_Swap_MVS | Si | [23 empty] | Dismantled
LP027 | AMBA_LP027_Swap_MVS | Si
LP029 | AMBA_LP029_Swap_MVS | Si | [23 empty] | Ready for Dismantle
LP031 | AMBA_LP031_Swap_MVS | Si | [23 empty] | Dismantled
LP044 | AMBA_LP044_Swap_MVS | Si | [19 empty] | 04 | BPSINS05-01 pos 01 | Sala TX, P.B. | 16 | Dismantled
LP048 | AMBA_LP048_Swap_MVS | Si | [23 empty] | Ready for Dismantle
LP049 | AMBA_LP049_Swap_MVS | Si | [23 empty] | Ready for Dismantle
LP061 | AMBA_LP061_Swap_MVS | Si
LP066 | AMBA_LP066_Swap_MVS | Si | [23 empty] | Ready for Dismantle
LP072 | AMBA_LP072_Swap_MVS | Si | [23 empty] | Dismantled
LP074 | AMBA_LP074_Swap_MVS | Si
LP100 | AMBA_LP100_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CS175 | AllRegion_ClusterOPT_March_TLF |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARBA0541 | BA_ARBA0541_FARM_Etapa1_MVS
ARBA1454 | BA_ARBA1454_FARM_Etapa1_MVS
BB006 | BA_BB006_Swap_MVS | Si | 1.53 | 2026-01-28 | 2026-01-29 | 2026-01-28 | 2026-01-28 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-01-30 | 2026-02-26 | Tomas Ezequiel Sanchez WX1486917 | 0 |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-16 | Yes |  |  | 09 | NPTAINS05-01 pos 01 | TX 1er piso | 12
BB140 | BA_BB140_Swap_MVS | Si | 1.53 | 2026-05-21 | 2026-05-21 | 2026-05-25 | 2026-05-25 | David Encina WX1367993 |  | 2026-05-25 | 2026-05-29 | David Encina WX1367993
BB304 | BA_BB304_Swap_MVS | Si | 1.87 | 2025-11-18 | 2025-11-19 | 2025-11-26 | 2025-11-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB360 | BA_BB360_Swap_MVS | Si | 1.53 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2025-11-18 | Abraham Jesus Salas Marfil 00237943 | RFI OK. En stock. Guzmán Nacich | [6 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB372 | BA_BB372_Swap | Si |  | 2026-03-16 | 2026-03-17 | 2026-03-16 | 2026-03-16 | David Encina WX1367993 |  | 2026-03-18 |  | David Encina WX1367993
BB389 | BA_BB389_Swap_MVS | Si | 1.53 |  |  | 2025-02-09 | 2025-02-09 | zhaofeng 00917583 |  |  | 2025-12-17 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobado por Pablo Buono el 17/12/2025. Aprobado por HW Solutiones el 18/12/2025. |  | 2026-02-06 | Claudio Romeo WX1379521 |  |  |  | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB391 | BA_BB391_Swap_MVS | Si | 1.53 | 2025-11-18 | 2025-11-19 | 2025-12-02 | 2025-12-02 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-12-17 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-02-06 | Claudio Romeo WX1379521 |  |  |  | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB475 | BA_BB475_Swap_MVS | Si | 1.53 |  |  | 2025-12-01 | 2025-12-01 | zhaofeng 00917583 |  |  | 2025-12-09 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobado por Nico Trubbo el 09/12/2025. Aprobado por HW Solutions el 16/12/2025. |  | 2026-02-06 | Claudio Romeo WX1379521 |  |  |  | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB482 | BA_BB482_Swap_MVS | Si | 1.87 |  |  | 2026-01-18 | 2026-01-18 | zhaofeng 00917583 |  | 2026-01-21 | 2026-01-21 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobada por Pablo Buono el 21/01/2026. |  | 2026-02-05 | Tomas Ezequiel Sanchez WX1486917 |  |  |  | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BH056 | BA_BH056_Swap_MVS | Si |  |  | 2026-05-17 | 2026-05-17 | 2026-05-17 | Joaquin Alejandro Luduena WX1488820 |  |  | 2026-05-19 | Joaquin Alejandro Luduena WX1488820
BH057 | BA_BH057_Swap_MVS | Si |  | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-03-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-06 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 |  |  |  |  | Survey Pending
BH060 | BA_BH060_Swap_MVS | Si |  |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | David Encina WX1367993
BH068 | BA_BH068_Swap_MVS | Si |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | David Encina WX1367993 |  | 2026-04-29 | 2026-05-06 | David Encina WX1367993
BH069 | BA_BH069_Swap_MVS | Si |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-29 | 2026-05-06 | Tomas Ezequiel Sanchez WX1486917
BH072 | BA_BH072_Swap_MVS | Si |  | 2026-04-29 | 2026-04-30 | 2026-05-02 | 2026-05-02 | David Encina WX1367993 |  | 2026-05-04 | 2026-06-02 | David Encina WX1367993
BH301 | BA_BH301_Swap_MVS | Si |  | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-13 | 2026-06-02 | Joaquin Alejandro Luduena WX1488820
BH302 | BA_BH302_Swap_MVS | Si |  |  | 2026-05-18 | 2026-05-19 | 2026-05-19 | David Encina WX1367993 |  | 2026-05-19 | 2026-05-21 | David Encina WX1367993
BH305 | BA_BH305_Swap_MVS | Si |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-26 | 2026-04-10 | Miguel Angel Garcia Martinez 00881238
BH721 | BA_BH721_Swap_MVS | Si
BH726 | BA_BH726_Swap_MVS | Si |  | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-05-25 | Daniel Horacio Rocabado WX1372513(GSC) |  | 2026-05-27 | 2026-05-27 | Miguel Angel Garcia Martinez 00881238
BH739 | BA_BH739_Swap_MVS | Si |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-26 | 2026-04-13 | Miguel Angel Garcia Martinez 00881238
BM308 | BA_BM308_Swap_MVS | Si | 1.87 |  |  | 2025-08-20 | 2025-08-20 | zhaofeng 00917583 |  |  | 2025-08-28 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok | [12 empty] | Ready for Dismantle
BM318 | BA_BM318_Swap_MVS | Si | 1.53 |  |  | 2026-03-24 | 2026-03-24 | zhaofeng 00917583 |  |  | 2026-04-01 | Tomas Ezequiel Sanchez WX1486917 | Reemplazar nueva estructura. No se tiene mas información.
BM800 | BA_BM800_Swap_MVS | Si | [8 empty] | 2026-04-01 | Tomas Ezequiel Sanchez WX1486917 | [8 empty] | Etapa 02 | 98 | SCMINS05-02 pos 02 | Sala TX, P.B. | 21 | Installed
BM801 | BA_BM801_Swap_MVS | Si | [8 empty] | 2026-04-01 | Joaquin Alejandro Luduena WX1488820 | [8 empty] | Etapa 02 | 98 | SCMINS05-02 pos 03 | Sala TX, P.B. | 21 | Installed
BM802 | BA_BM802_Swap_MVS | Si | [8 empty] | 2026-04-01 | Joaquin Alejandro Luduena WX1488820 | [8 empty] | Etapa 02 | 98 | SCMINS05-02 pos 04 | Sala TX, P.B. | 21 | Installed
BM631 | BM631_TEST | Si |  | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-30 | GSC |  | 2024-09-05 | 2024-12-12 | Abraham Jesus Salas Marfil 00237943
CM012 | CABA_CM012_Swap_MVS | Si
CN058 | CABA_CN058_Swap_MVS | Si
CN108 | CABA_CN108_Swap_MVS | Si
CN139 | CABA_CN139_Swap_MVS | Si
CN142 | CABA_CN142_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CN144 | CABA_CN144_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CN155 | CABA_CN155_Swap_MVS | Si
CN159 | CABA_CN159_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CN169 | CABA_CN169_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CN194 | CABA_CN194_Swap_MVS | Si
CS002 | CABA_CS002_Swap_MVS | Si
CS033 | CABA_CS033_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CS072 | CABA_CS072_Swap_MVS | Si
CS073 | CABA_CS073_Swap_MVS | Si | [23 empty] | Ready for Dismantle
CS081 | CABA_CS081_Swap_MVS | Si
CS095 | CABA_CS095_Swap_MVS | Si
CS097 | CABA_CS097_Swap_MVS | Si
CS099 | CABA_CS099_Swap_MVS | Si
CU006 | CABA_CU006_Swap_MVS | Si
CU014 | CABA_CU014_Swap_MVS | Si
CU045 | CABA_CU045_Swap_MVS | Si
XN008 | CB_XN008_Swap_MVS | Si
XS023 | CB_XS023_Swap_MVS | Si
XS024 | CB_XS024_Swap_MVS | Si
UE008 | CT_UE008_Swap_MVS | Si |  |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-20 | 2026-05-20 | Tomas Ezequiel Sanchez WX1486917
UE017 | CT_UE017_Swap_MVS | Si |  |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-19 | 2026-05-19 | Tomas Ezequiel Sanchez WX1486917
UE023 | CT_UE023_Swap_MVS | Si
UE025 | CT_UE025_Swap_MVS | Si
UE028 | CT_UE028_Swap_MVS | Si
UE051 | CT_UE051_Swap_MVS | Si
UE057 | CT_UE057_Swap_MVS | Si
UE058 | CT_UE058_Swap_MVS | Si
UE069 | CT_UE069_Swap_MVS | Si
UE086 | CT_UE086_Swap_MVS | Si
UE121 | CT_UE121_Swap_MVS | Si
UE125 | CT_UE125_Swap_MVS | Si
UE126 | CT_UE126_Swap_MVS | Si
UE130 | CT_UE130_Swap_MVS | Si
UE314 | CT_UE314_Swap_MVS | Si |  |  | 2026-05-20 | 2026-05-22 | 2026-05-22 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-21 | 2026-06-01 | Joaquin Alejandro Luduena WX1488820
YS009 | JY_YS009_Swap_MVS | Si
ARPA0040 | LP_ARPA0040_FARM_Etapa1_MVS | [24 empty] | PPI Pending
DC002 | LP_DC002_Swap_MVS | Si | 0.87 |  |  | 2025-12-23 | 2025-12-23 | zhaofeng 00917583 |  |  | 2026-01-05 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-02-11 | Joaquin Alejandro Luduena WX1488820
DC022 | LP_DC022_Swap_MVS | Si | 1.53 |  |  | 2025-12-12 | 2025-12-12 | zhaofeng 00917583 |  |  | 2026-04-15 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok |  | 2026-02-05 | Joaquin Alejandro Luduena WX1488820 |  |  |  |  | Etapa 01 | - | STSINS05-01 pos 01 | Subsuelo | - | SubRack Installed
DC023 | LP_DC023_Swap_MVS | Si |  | 2025-11-04 | 2025-11-05 | 2025-12-11 | 2025-12-11 | David Encina WX1367993 |  | 2025-11-06 | 2026-01-23 | David Encina WX1367993 |  |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-20 | Yes | [6 empty] | Survey Pending
DE003 | LP_DE003_Swap_MVS | Si |  | 2025-11-05 | 2025-11-06 | 2025-11-11 | 2025-11-11 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-11-25 | Miguel Angel Garcia Martinez 00881238 | En stock. Guzmán Nacich |  | 2026-02-13 | Tomas Ezequiel Sanchez WX1486917
DE015 | LP_DE015_Swap_MVS | Si |  | 2025-11-18 | 2025-11-19 | 2026-02-18 | 2026-02-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 |  | Miguel Angel Garcia Martinez 00881238
DN006 | LP_DN006_Swap_MVS | Si | 1.2 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-03-20 | Miguel Angel Garcia Martinez 00881238
DN041 | LP_DN041_Swap_MVS | Si | 1.2 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-06-03 | David Encina WX1367993
DS001 | LP_DS001_Swap_MVS | Si |  | 2025-11-18 | 2025-11-19 | 2026-02-20 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2026-03-12 | Miguel Angel Garcia Martinez 00881238 | 12/03: Aprobada por David Masessa. |  |  |  |  | 2026-05-16 | Yes | [6 empty] | Survey Pending
DS033 | LP_DS033_Swap_MVS | Si |  | 2025-11-05 | 2025-11-07 | 2025-12-09 | 2025-12-09 | Agustin Maria Bianchetti 00958351 |  | 2025-12-11 | 2026-02-06 | Agustin Maria Bianchetti 00958351 | Asignado a COBRA. Aprobada por Nico Trubbo el 22/12/2025. 30/01/2026: Se rechazó la propuesta luego de aprobada#， Ezequiel Fail. 30/01/2026: Se envia la Rev01 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-16 | Yes | [6 empty] | Survey Pending
DS047 | LP_DS047_Swap_MVS | Si | 0.87 |  |  | 2025-11-08 | 2025-11-08 | Elvia Carolina Cortes Garcia 00881509 |  |  | 2026-03-31 | Elvia Carolina Cortes Garcia 00881509 | RFI Ok. Aprobado por Nico Trubbo el 09/12/2025. |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917
DW017 | LP_DW017_Swap_MVS | Si | 1.2 | 2025-11-05 | 2025-11-06 | 2025-11-12 | 2025-11-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-07 | 2025-11-25 | Adrian Guzman Garcia 00881507 | En stock. Guzmán Nacich |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 |  |  | Yes
XW009 | MEDI_65_XW009_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XW083 | MEDI_65_XW083_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XW095 | MEDI_65_XW095_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XW097 | MEDI_65_XW097_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XWM07 | MEDI_65_XWM07_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC107 | MEDI_MC107_SWAP_MVS | Si | 1.53 | 2025-02-05 | 2025-02-06 | 2025-05-28 | 2025-05-28 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-02-07 | 2025-06-26 | Arturo Gonzalo Antonio Cantu 00879903
MC307 | MEDI_MC307_SWAP_MVS | Si | 0.53 |  |  | 2026-05-06 | 2026-05-06 | Joaquin Alejandro Luduena WX1488820 |  |  |  | Abraham Jesus Salas Marfil 00237943 | [13 empty] | Dismantled
OS002 | MEDI_OS002_Swap_MVS | Si
XC074 | MEDI_XC074_Swap_MVS | Si
XN092 | MEDI_XN092_Swap_MVS | Si
XW075 | MEDI_XW075_Swap_MVS | Si
XW305 | MEDI_XW305_Swap_MVS | Si
MC004 | MZ_MC004_Swap_MVS | Si | 1.53 |  |  | 2026-01-09 | 2026-01-09 | zhaofeng 00917583 |  |  | 2026-01-23 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobada por Diego Alvarenga el 28/01/2026. El proyecto se aprobó sin 5G. Luego de aprobada#， se solicitó la actualizacion a una config coin 5G. Aprobada por Pablo Buono el 23/01/2026. |  | 2026-02-05 | Tomas Ezequiel Sanchez WX1486917 | [9 empty] | Ready for Dismantle
MC035 | MZ_MC035_Swap_MVS | Si | 0.87 |  |  | 2025-06-17 | 2025-06-17 | zhaofeng 00917583 |  |  | 2025-06-20 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok | [7 empty] | Etapa 02 | 03 | LCYINS05-01 pos 02 | Sala TX 01, P.B. | 11 | Dismantled
MC041 | MZ_MC041_Swap_MVS | Si | [17 empty] | Pendientes menores de Instalacion | Etapa 01 | 03 | LCYINS05-01 pos 03 | Sala TX 01, P.B. | 11 | Installed with Issue
MC063 | MZ_MC063_Swap_MVS | Si
MC064 | MZ_MC064_Swap_MVS | Si | [8 empty] | 2026-04-14 | Arturo Gonzalo Antonio Cantu 00879903 | REVISAR ESTATUS CON CIS Asignado a CIS. Se hace en conjunto con el swap. |  | 2026-02-09 | Abraham Jesus Salas Marfil 00237943
MC076 | MZ_MC076_Swap_MVS | Si | 1.2 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2025-09-30 | zhaofeng 00917583 | RFI Ok | [7 empty] | Etapa 01 | 23 | ARQINS05-01 pos 01 | Sala TX02, 1er piso | 00 | SubRack Installed
MC077 | MZ_MC077_Swap_MVS | Si
MC080 | MZ_MC080_Swap_MVS | Si | 0.87 |  |  | 2025-06-02 | 2025-06-02 | zhaofeng 00917583 |  |  | 2025-06-10 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. Se hará al momento del swap. CIS Group. | [7 empty] | Etapa 02 | 03 | LCYINS05-01 pos 03 | Sala TX 01, P.B. | 11 | Dismantled
MC126 | MZ_MC126_Swap_MVS | Si
MC305 | MZ_MC305_Swap_MVS | Si |  | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-13 | 2026-04-24 | David Encina WX1367993 | RFI Ok. 20/02/2026: Aprobada por Nico Trubbo |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-20 | Yes
MC397 | MZ_MC397_Swap_MVS | Si | 1.53 | 2026-02-11 | 2026-02-11 | 2026-05-05 | 2026-05-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-13 | 2026-05-05 | Miguel Angel Garcia Martinez 00881238 | RFI Ok. 20/02/2026: Aprobada por Nico Trubbo |  | 2026-03-04 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-16 | Yes
MC401 | MZ_MC401_Swap_MVS | Si | 0.87 |  |  | 2025-06-04 | 2025-06-04 | zhaofeng 00917583 |  |  | 2025-06-12 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok | [7 empty] | Etapa 02 | 03 | LCYINS05-01 pos 01 | Sala TX 01, P.B. | 11 | Dismantled
MN008 | MZ_MN008_Swap_MVS | Si | 1.2 |  |  | 2025-09-02 | 2025-09-02 | zhaofeng 00917583 |  |  | 2025-09-03 | Arturo Gonzalo Antonio Cantu 00879903 | Cambio de pedestal. CIS Group |  | 2026-02-24 | Tomas Ezequiel Sanchez WX1486917
MN078 | MZ_MN078_Swap_MVS | Si
MN083 | MZ_MN083_Swap_MVS | Si | 1.53 | [7 empty] | 2023-12-22 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 2026-05-20 | Yes
MN084 | MZ_MN084_Swap_MVS | Si | 1.53 | [7 empty] | 2024-12-06 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 2026-05-20 | Yes
MN088 | MZ_MN088_Swap_MVS | Si | 1.53 | [7 empty] | 2025-07-24 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 2026-05-20 | Yes
MN379 | MZ_MN379_Swap_MVS | Si |  | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-13 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-16 | Yes
MS006 | MZ_MS006_Swap_MVS | Si | 0.87 | 2025-08-15 | 2025-08-18 | 2025-08-18 | 2025-08-18 | GSC |  |  | 2026-01-20 | Abraham Jesus Salas Marfil 00237943 | RFI Ok
MS028 | MZ_MS028_Swap_MVS | Si | 1.2 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2025-10-19 | zhaofeng 00917583 | RFI Ok | [12 empty] | Ready for Dismantle
MS032 | MZ_MS032_Swap_MVS | Si | 1.53 | [7 empty] | 2025-09-08 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 2026-05-16 | Yes
QE004 | NQ_QE004_Swap_MVS | Si | 1.87 | 2025-03-05 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-03-07 | 2025-12-23 | Arturo Gonzalo Antonio Cantu 00879903 | 13/03: Aprobada por Diego ALvarenga R01.
QE378 | NQ_QE378_Swap_MVS | Si
QN036 | NQ_QN036_Swap_MVS | Si |  | 2025-03-13 | 2025-03-14 | 2025-03-14 | 2025-03-14 |  |  | 2025-03-18 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238
QW013 | NQ_QW013_Swap_MVS | Si | 0.53 | 2026-03-03 | 2026-03-03 | 2026-03-04 | 2026-03-04 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-05 | 2026-05-21 | Miguel Angel Garcia Martinez 00881238
RE004 | RN_RE004_Swap_MVS | Si |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | David Encina WX1367993 |  | 2026-06-09 |  | David Encina WX1367993
RE009 | RN_RE009_Swap_MVS | Si
RE011 | RN_RE011_Swap_MVS | Si |  | 2026-06-08 | 2026-06-09 |  |  | Daniel Horacio Rocabado WX1372513 |  | 2026-06-10 |  | Daniel Horacio Rocabado WX1372513
RE022 | RN_RE022_Swap_MVS | Si |  |  | 2026-06-07 | 2026-06-07 | 2026-06-07 | David Encina WX1367993
RE063 | RN_RE063_Swap_MVS | Si |  | 2026-06-09 | 2026-06-09 |  |  | Joaquin Alejandro Luduena WX1488820 |  |  |  | Joaquin Alejandro Luduena WX1488820
RN002 | RN_RN002_Swap_MVS | Si |  | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-08 | David Encina WX1367993 |  |  | 2026-04-17 | David Encina WX1367993
RN013 | RN_RN013_Swap_MVS | Si | 1.53 | 2026-04-16 | 2026-04-16 | 2026-04-27 | 2026-04-27 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-20 | 2026-04-28 | Tomas Ezequiel Sanchez WX1486917 | [13 empty] | Survey Pending
RN016 | RN_RN016_Swap_MVS | Si |  | 2026-04-16 | 2026-04-17 | 2026-04-23 | 2026-04-23 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-21 |  | Tomas Ezequiel Sanchez WX1486917
RN028 | RN_RN028_Swap_MVS | Si |  | 2026-04-16 | 2026-04-16 | 2026-04-23 | 2026-04-23 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-20 | 2026-05-08 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | 08 | GRCINS05-01 pos 01 | Sala TS, 3er Piso | 26 | PPI Pending
RN030 | RN_RN030_Swap_MVS | Si |  | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | David Encina WX1367993 |  | 2026-04-17 | 2026-04-29 | David Encina WX1367993 | [9 empty] | 08 | GRCINS05-01 pos 02 | Sala TS, 3er Piso | 26 | PPI Approved
RN035 | RN_RN035_Swap_MVS | Si | 1.53 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-20 | 2026-04-21 | Joaquin Alejandro Luduena WX1488820
RN037 | RN_RN037_Swap_MVS | Si | 1.2 | 2026-04-16 | 2026-04-17 | 2026-04-20 | 2026-04-20 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-21 | 2026-04-27 | Joaquin Alejandro Luduena WX1488820
RN053 | RN_RN053_Swap_MVS | Si |  | 2026-04-01 | 2026-04-01 | 2026-04-20 | 2026-04-20 | Bautista Turri WX1450521 |  | 2026-04-07 |  | Bautista Turri WX1450521
RN072 | RN_RN072_Swap_MVS | Si |  | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-21 | 2026-05-04 | Miguel Angel Garcia Martinez 00881238
RN301 | RN_RN301_Swap_MVS | Si |  | 2026-04-01 | 2026-04-01 | 2026-04-06 | 2026-04-06 | David Encina WX1367993 |  | 2026-04-07 | 2026-04-15 | David Encina WX1367993 | [9 empty] | 08 | GRCINS05-01 pos 03 | Sala TS, 3er Piso | 26 | PPI Pending
RN302 | RN_RN302_Swap_MVS | Si |  | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-21 |  | GSC | [9 empty] | 08 | GRCINS05-01 pos 04 | Sala TS, 3er Piso | 26 | PPI Pending
RN303 | RN_RN303_Swap_MVS | Si |  | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-21 |  | GSC | [9 empty] | 08 | GRCINS05-02 pos 01 | Sala TS, 3er Piso | 26 | PPI Pending
RN304 | RN_RN304_Swap_MVS | Si |  | 2026-04-01 | 2026-04-01 | 2026-04-07 | 2026-04-07 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-07 | 2026-05-07 | Tomas Ezequiel Sanchez WX1486917 | [9 empty] | 08 | GRCINS05-02 pos 02 | Sala TS, 3er Piso | 26 | PPI Pending
RN305 | RN_RN305_Swap_MVS | Si |  | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-21 | 2026-05-06 | Miguel Angel Garcia Martinez 00881238
RN344 | RN_RN344_Swap_MVS | Si |  | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-21 | 2026-05-18 | Miguel Angel Garcia Martinez 00881238
RS003 | RN_RS003_Swap_MVS | Si | 1.2 | 2026-03-23 | 2026-03-24 | 2026-03-31 | 2026-03-31 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-25 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
RS014 | RN_RS014_Swap_MVS | Si | 1.53 | 2026-03-30 | 2026-03-31 | 2026-04-06 | 2026-04-06 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-01 | 2026-04-14 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 2026-05-20 | Yes |  | Etapa 01 |  |  |  |  | N/A
RS046 | RN_RS046_Swap_MVS | Si | 1.53 | 2026-03-13 | 2026-03-17 | 2026-04-07 | 2026-04-07 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-18 | 2026-04-07 | Miguel Angel Garcia Martinez 00881238
RS056 | RN_RS056_Swap_MVS | Si | 1.53 | 2026-03-18 | 2026-03-19 | 2026-04-10 | 2026-04-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-20 | 2026-04-13 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-20 | Yes
RS070 | RN_RS070_Swap_MVS | Si |  | 2026-03-25 | 2026-03-26 | 2026-03-31 | 2026-03-31 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-27 | 2026-04-14 | Miguel Angel Garcia Martinez 00881238
RS126 | RN_RS126_Swap_MVS | Si |  | 2026-03-23 | 2026-03-24 | 2026-03-31 | 2026-03-31 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-25 | 2026-04-13 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-20 | Yes |  | Etapa 01 | 21 | BRLINS05-01 pos 01 | Sala TX02, 1er piso | 36 | Installed
AN015 | SA_AN015_Swap_MVS | Si | 1.53 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-13 | 2026-04-21 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 2026-05-20 | Yes
VC003 | SC_VC003_Swap_MVS | Si
VE002 | SC_VE002_Swap_MVS | Si
VE014 | SC_VE014_Swap_MVS | Si
VE022 | SC_VE022_Swap_MVS | Si
VN010 | SC_VN010_Swap_MVS | Si
VW030 | SC_VW030_Swap_MVS | Si
JC003 | SJ_JC003_Swap_MVS | Si |  | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-24 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 | 2026-02-19 | Miguel Angel Garcia Martinez 00881238
JC004 | SJ_JC004_Swap_MVS | Si |  | 2025-12-22 | 2025-12-23 | 2025-12-26 | 2025-12-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 | 2026-02-19 | Miguel Angel Garcia Martinez 00881238
JC008 | SJ_JC008_Swap_MVS | Si |  | 2025-12-22 | 2025-12-23 | 2026-03-06 | 2026-03-06 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 |  | GSC
JC024 | SJ_JC024_Swap_MVS | Si |  | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-26 | 2026-01-21 | Miguel Angel Garcia Martinez 00881238
JC025 | SJ_JC025_Swap_MVS | Si
JC026 | SJ_JC026_Swap_MVS | Si
JC029 | SJ_JC029_Swap_MVS | Si |  | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-31 | 2026-01-21 | Miguel Angel Garcia Martinez 00881238
JC054 | SJ_JC054_Swap_MVS | Si |  | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-26 | 2026-02-19 | Miguel Angel Garcia Martinez 00881238
JC101 | SJ_JC101_Swap_MVS | Si |  | 2025-11-30 | 2025-12-01 | 2025-12-01 | 2025-12-01 | David Encina WX1367993 |  | 2025-12-02
JC302 | SJ_JC302_Swap_MVS | Si |  | 2025-12-23 | 2025-12-24 | 2026-01-24 | 2026-01-24 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-26 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | 06/02/2026: Aprobada por Pablo Buono.
JC322 | SJ_JC322_Swap_MVS | Si
JC326 | SJ_JC326_Swap_MVS | Si
JC336 | SJ_JC336_Swap_MVS | Si |  | 2025-12-23 | 2025-12-24 | 2025-12-23 | 2025-12-23 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-26 | 2025-12-30 | Miguel Angel Garcia Martinez 00881238
JS011 | SJ_JS011_Swap_MVS | Si |  | 2025-12-22 | 2025-12-23 | 2025-12-26 | 2025-12-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-24 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238
JS307 | SJ_JS307_Swap_MVS | Si
FC001 | SL_FC001_Swap_MVS | Si |  | 2026-02-09 | 2026-02-09 | 2026-02-13 | 2026-02-13 | Agustin Maria Bianchetti 00958351 |  | 2026-02-09 | 2026-03-16 | Agustin Maria Bianchetti 00958351 | [5 empty] | 2026-05-20 | Yes
FC003 | SL_FC003_Swap_MVS | Si | 1.53 | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-12 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-20 | Yes
FC004 | SL_FC004_Swap_MVS | Si | 1.87 | 2026-02-12 | 2026-02-12 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-13 | 2026-03-17 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917
FC006 | SL_FC006_Swap_MVS | Si | 1.53 | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-27 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-02 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
FC007 | SL_FC007_Swap_MVS | Si | 1.53 | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-27 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-02 | 2026-03-25 | Miguel Angel Garcia Martinez 00881238(GSC) | [5 empty] | 2026-05-16 | Yes
FC022 | SL_FC022_Swap_MVS | Si | 1.53 | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-27 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-02 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
FC032 | SL_FC032_Swap_MVS | Si | 1.87 | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12 | David Encina WX1367993 |  | 2026-02-13 | 2026-04-17 | David Encina WX1367993 | RFI Ok |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917
FC036 | SL_FC036_Swap_MVS | Si |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | David Encina WX1367993 |  |  | 2026-04-10 | David Encina WX1367993 | [5 empty] | 2026-05-16 | Yes
FC037 | SL_FC037_Swap_MVS | Si |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-11 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917
FC302 | SL_FC302_Swap_MVS | Si | 2.2 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-19 | 2026-03-26 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
FC333 | SL_FC333_Swap_MVS | Si | 1.87 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | David Encina WX1367993 |  | 2026-03-05 |  | David Encina WX1367993
FE012 | SL_FE012_Swap_MVS | Si | 1.87 | 2026-01-29 | 2026-01-29 | 2026-02-05 | 2026-02-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-06 | 2026-02-06 | Arturo Gonzalo Antonio Cantu 00879903 | 20/02/2026: Aprobada por Nico Trubbo |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
FE014 | SL_FE014_Swap_MVS | Si | 1.87 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | David Encina WX1367993 |  | 2026-03-03 | 2026-03-31 | David Encina WX1367993
FE017 | SL_FE017_Swap_MVS | Si |  | 2026-02-19 | 2026-02-19 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-23
FE019 | SL_FE019_Swap_MVS | Si | 1.87 | 2026-01-27 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-29 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | 29/01/2026: Aprobado por Pablo Buono. |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
FE020 | SL_FE020_Swap_MVS | Si |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-20 |  | Tomas Ezequiel Sanchez WX1486917
FE021 | SL_FE021_Swap_MVS | Si | 1.53 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-11 | 2026-02-11 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-16 | David Encina WX1367993
FE041 | SL_FE041_Swap_MVS | Si | 1.2 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-11 | 2026-04-24 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
FE047 | SL_FE047_Swap_MVS | Si | 1.53 | 2026-01-27 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-29 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | RFI Ok. 29/01/2026: Aprobado por Pablo Buono. |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
FE048 | SL_FE048_Swap_MVS | Si | 0.87 | 2026-02-09 | 2026-02-09 | 2026-04-22 | 2026-04-22 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-05-04 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 |  |  |  |  | Survey Pending
FE055 | SL_FE055_Swap_MVS | Si | 1.53 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-02 | 2026-02-02 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
FE056 | SL_FE056_Swap_MVS | Si | 0.53 | 2026-01-29 | 2026-01-29 | 2026-01-30 | 2026-02-04 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-06 | 2026-05-29 | Miguel Angel Garcia Martinez 00881238
FE343 | SL_FE343_Swap_MVS | Si | 1.53 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-29 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | En stock. Guzmán Nacich |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-20 | Yes
FEM22 | SL_FEM22_Swap_MVS | Si |  | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-27 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-02 |  | Miguel Angel Garcia Martinez 00881238
FEM44 | SL_FEM44_Swap_MVS | Si |  | 2026-02-26 | 2026-02-26 | 2026-03-02 | 2026-03-02 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-02 |  | Miguel Angel Garcia Martinez 00881238
FN001 | SL_FN001_Swap_MVS | Si |  | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-19
FN002 | SL_FN002_Swap_MVS | Si | 1.2 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-11 | 2026-06-04 | Joaquin Alejandro Luduena WX1488820
FN004 | SL_FN004_Swap_MVS | Si |  | 2026-02-18 | 2026-02-18 | 2026-02-19 | 2026-02-19 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-20
FN007 | SL_FN007_Swap_MVS | Si |  | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-10 |  | GSC
FN010 | SL_FN010_Swap_MVS | Si | 0.87 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-20 | 2026-06-03 | Miguel Angel Garcia Martinez 00881238
FN019 | SL_FN019_Swap_MVS | Si | 0.87 | 2026-02-19 | 2026-02-19 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-23 | 2026-05-28 | Miguel Angel Garcia Martinez 00881238
FN026 | SL_FN026_Swap_MVS | Si | 1.2 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-12 | 2026-04-24 | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
FN032 | SL_FN032_Swap_MVS | Si | 1.53 | 2026-02-12 | 2026-02-12 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-18 | 2026-06-03 | Miguel Angel Garcia Martinez 00881238
FN036 | SL_FN036_Swap_MVS | Si | 1.87 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-19 | 2026-06-03
FN129 | SL_FN129_Swap_MVS | Si | 1.53 | 2026-02-19 | 2026-02-19 | 2026-02-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-23 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
FO013 | SL_FO013_Swap_MVS | Si |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-12 |  | Miguel Angel Garcia Martinez 00881238 |  |  | 2026-03-13 | Joaquin Alejandro Luduena WX1488820
FO112 | SL_FO112_Swap_MVS | Si |  | 2026-03-17 | 2026-03-18 | 2026-03-26 | 2026-03-26 | David Encina WX1367993 |  | 2026-03-19 |  | David Encina WX1367993
A38-B315 | SOUTH_A38-B315_5G | No | 0.53 | 2026-02-12 | 2026-02-12 |  |  | GSC |  |  | 2026-03-19 | Abraham Jesus Salas Marfil 00237943 | RFI Ok
A38-B322 | SOUTH_A38-B322_5G | No |  | 2026-02-12 | 2026-02-12 |  |  | GSC |  |  | 2026-03-10 | Abraham Jesus Salas Marfil 00237943
QE005 | SUR_123_QE005_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC006 | SUR_130_QC006_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC006 | SUR_130_QC006_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC012 | SUR_130_QC012_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC013 | SUR_130_QC013_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC023 | SUR_130_QC023_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC023 | SUR_130_QC023_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC037 | SUR_130_QC037_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC037 | SUR_130_QC037_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC044 | SUR_130_QC044_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC053 | SUR_130_QC053_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC053 | SUR_130_QC053_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC054 | SUR_130_QC054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC076 | SUR_130_QC076_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q003 | SUR_131_A30-Q003_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q003 | SUR_131_A30-Q003_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q048 | SUR_131_A30-Q048_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q076 | SUR_131_A30-Q076_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC074 | SUR_131_QC074_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC105 | SUR_131_QC105_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q007 | SUR_134_A30-Q007_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q029 | SUR_134_A30-Q029_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE009 | SUR_134_QE009_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE037 | SUR_134_QE037_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE051 | SUR_134_QE051_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE083 | SUR_134_QE083_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM004 | SUR_179_BM004_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM116 | SUR_179_BM116_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM506 | SUR_179_BM506_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM584 | SUR_179_BM584_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM749 | SUR_179_BM749_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM750 | SUR_179_BM750_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM751 | SUR_179_BM751_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM752 | SUR_179_BM752_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM805 | SUR_179_BM805_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM806 | SUR_179_BM806_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM808 | SUR_179_BM808_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM809 | SUR_179_BM809_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM538 | SUR_181 _BM538_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM540 | SUR_181_BM540_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM541 | SUR_181_BM541_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM543 | SUR_181_BM543_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM544 | SUR_181_BM544_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM545 | SUR_181_BM545_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM546 | SUR_181_BM546_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM547 | SUR_181_BM547_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM548 | SUR_181_BM548_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM484 | SUR_184_BM484_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM611 | SUR_184_BM611_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM008 | SUR_185_BM008_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM312 | SUR_186_BM312_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM057 | SUR_188_BM057_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM303 | SUR_188_BM303_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM357 | SUR_188_BM357_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM550 | SUR_188_BM550_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM725 | SUR_188_BM725_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM129 | SUR_199_BM129_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM316 | SUR_199_BM316_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM329 | SUR_199_BM329_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM391 | SUR_199_BM391_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM638 | SUR_199_BM638_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM640 | SUR_199_BM640_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM642 | SUR_199_BM642_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM643 | SUR_199_BM643_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM778 | SUR_199_BM778_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM010 | SUR_200_BM010_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM096 | SUR_201_BM096_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH045 | SUR_202 _BH045_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM083 | SUR_204_BM083_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM083 | SUR_204_BM083_OPT_Adec |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM094 | SUR_204_BM094_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM094 | SUR_204_BM094_OPT_Adec |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM375 | SUR_204_BM375_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM025 | SUR_205_BM025_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM104 | SUR_205_BM104_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM040 | SUR_206_BM040_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM631 | SUR_206_BM631_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM625 | SUR_207_BM625_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM106 | SUR_208_BM106_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-B060 | SUR_247_A37-B060_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BT042 | SUR_247_BT042_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BT043 | SUR_247_BT043_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A42-B393 | SUR_283_A42-B393_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A42-B394 | SUR_283_A42-B394_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH001 | SUR_283_BH001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH043 | SUR_283_BH043_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH062 | SUR_283_BH062_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH073 | SUR_283_BH073_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM033 | SUR_329_BM033_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM141 | SUR_329_BM141_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM393 | SUR_329_BM393_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM501 | SUR_329_BM501_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM767 | SUR_329_BM767_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM768 | SUR_329_BM768_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM018 | SUR_334_BM018_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B051 | SUR_3_A38-B051_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B051 | SUR_3_A38-B051_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B055 | SUR_3_A38-B055_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B318 | SUR_3_A38-B318_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B323 | SUR_3_A38-B323_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB064 | SUR_3_BB064_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB064 | SUR_3_BB064_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB173 | SUR_3_BB173_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB173 | SUR_3_BB173_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB307 | SUR_3_BB307_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB307 | SUR_3_BB307_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB351 | SUR_3_BB351_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB391 | SUR_3_BB391_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB482 | SUR_3_BB482_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS502 | SUR_501_JS502_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC005 | SUR_502_JC005_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC053 | SUR_502_JC053_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC101 | SUR_502_JC101_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC341 | SUR_502_JC341_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MO002 | SUR_514_MO002_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS011 | SUR_514_MS011_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS019 | SUR_514_MS019_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS023 | SUR_514_MS023_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS028 | SUR_514_MS028_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS030 | SUR_514_MS030_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS032 | SUR_514_MS032_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS035 | SUR_514_MS035_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS038 | SUR_514_MS038_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS041 | SUR_514_MS041_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS042 | SUR_514_MS042_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS044 | SUR_514_MS044_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS062 | SUR_514_MS062_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS063 | SUR_514_MS063_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS122 | SUR_514_MS122_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS001 | SUR_515_MS001_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS005 | SUR_515_MS005_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS006 | SUR_515_MS006_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS009 | SUR_515_MS009_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS017 | SUR_515_MS017_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS054 | SUR_515_MS054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS059 | SUR_515_MS059_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS061 | SUR_515_MS061_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS066 | SUR_515_MS066_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS067 | SUR_515_MS067_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS075 | SUR_515_MS075_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS503 | SUR_515_MS503_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSM24 | SUR_515_MSM24_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC006 | SUR_518_MC006_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC010 | SUR_518_MC010_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC068 | SUR_518_MC068_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC073 | SUR_518_MC073_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC305 | SUR_519_MC305_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC017 | SUR_520_MC017_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC033 | SUR_520_MC033_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC051 | SUR_520_MC051_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC326 | SUR_521_MC326_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC326 | SUR_521_MC326_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC039 | SUR_522_MC039_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC107 | SUR_522_MC107_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC307 | SUR_522_MC307_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC348 | SUR_522_MC348_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC035 | SUR_523_MC035_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC041 | SUR_523_MC041_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC080 | SUR_523_MC080_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC091 | SUR_523_MC091_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC093 | SUR_523_MC093_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC094 | SUR_523_MC094_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC300 | SUR_523_MC300_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC401 | SUR_523_MC401_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC403 | SUR_523_MC403_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC409 | SUR_523_MC409_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN510 | SUR_524_MN510_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS014 | SUR_529_MS014_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS022 | SUR_529_MS022_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC316 | SUR_530_MC316_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC319 | SUR_530_MC319_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS002 | SUR_531_JS002_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS012 | SUR_531_JS012_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS015 | SUR_531_JS015_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS017 | SUR_531_JS017_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS026 | SUR_531_JS026_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS027 | SUR_531_JS027_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS028 | SUR_531_JS028_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS033 | SUR_531_JS033_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS037 | SUR_531_JS037_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS039 | SUR_531_JS039_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS040 | SUR_531_JS040_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS045 | SUR_531_JS045_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS101 | SUR_531_JS101_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC016 | SUR_533_MC016_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC092 | SUR_533_MC092_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC315 | SUR_533_MC315_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M0016 | SUR_534_M0016_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O006 | South_A33-O006_Mod_TA | Si |  | N/A |  | N/A
A33-O010 | South_A33-O010_Mod_TA | Si |  | N/A | 2026-05-15 | N/A | 2026-05-15 | Tomas Ezequiel Sanchez WX1486917
A33-O045 | South_A33-O045_Mod_TA | Si |  | N/A |  | N/A
A33-O059 | South_A33-O059_Mod_TA | Si |  | N/A | 2026-05-13 | N/A | 2026-06-01 | GSC
A33-O064 | South_A33-O064_Mod_TA | Si |  | N/A | 2026-05-08 | N/A | 2026-05-12 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-05-12 |  | Arturo Gonzalo Antonio Cantu 00879903
A33-O073 | South_A33-O073_Mod_TA | Si |  | N/A |  | N/A
A33-O088 | South_A33-O088_Mod_TA | Si | 0.53 | N/A | 2026-04-24 | N/A | 2026-04-24 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-28 | 2026-05-08 | Joaquin Alejandro Luduena WX1488820 | [5 empty] | 2026-05-31 | Yes
A33-O091 | South_A33-O091_Mod_TA | Si |  | N/A | 2026-05-14 | N/A | 2026-06-01 | Daniel Horacio Rocabado WX1372513(GSC) |  | 2026-05-18
A33-O112 | South_A33-O112_Mod_TA | Si |  | N/A | 2026-05-11 | N/A | 2026-05-21 | GSC |  | 2026-05-21 |  | Miguel Angel Garcia Martinez 00881238
A33-O143 | South_A33-O143_Mod_TA | Si |  | N/A | 2026-05-12 | N/A | 2026-05-21 | GSC
A33-O218 | South_A33-O218_Mod_TA | Si |  | N/A |  | N/A
A33-O245 | South_A33-O245_Mod_TA | Si |  | N/A | 2026-05-07 | N/A |  | GSC |  | 2026-05-07
A33-O381 | South_A33-O381_Mod_TA | Si |  | N/A |  | N/A
A33-O389 | South_A33-O389_Mod_TA | Si |  | N/A |  | N/A
A33-O574 | South_A33-O574_Mod_TA | Si |  | N/A |  | N/A
A33-O737 | South_A33-O737_Mod_TA | Si |  | N/A | 2026-05-14 | N/A | 2026-05-21 | GSC |  | 2026-05-18
A35-D036 | South_A35-D036_Mod_TA | Si | 0.53 | N/A | 2026-04-24 | N/A | 2026-05-04 | Arturo Gonzalo Antonio Cantu 00879903(GSC) |  | 2026-04-28 | 2026-05-27 | Arturo Gonzalo Antonio Cantu 00879903
A37-B060 | South_A37-B060_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-03-27 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-04-17 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 2026-04-29 | Yes
A37-B131 | South_A37-B131_Mod_TA | Si | 1.2 | N/A |  | N/A | 2026-03-26 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-04-17 | Abraham Jesus Salas Marfil 00237943 | [5 empty] | 2026-05-16 | Yes
MC373 | South_MC373_Swap_MVS | Si
Storage_March
IC001 | TF_IC001_Swap_MVS | Si
IC002 | TF_IC002_Swap_MVS | Si
IC005 | TF_IC005_Swap_MVS | Si
IC008 | TF_IC008_Swap_MVS | Si
IC015 | TF_IC015_Swap_MVS | Si
IC017 | TF_IC017_Swap_MVS | Si
IC021 | TF_IC021_Swap_MVS | Si
IC024 | TF_IC024_Swap_MVS | Si
IN001 | TF_IN001_Swap_MVS | Si
TC040 | TU_TC040_Swap_MVS | Si | 1.53 |  | 2026-05-07 | 2026-05-07 | 2026-05-07 | Miguel Angel Garcia Martinez 00881238 |  | 2026-05-07
TE006 | TU_TE006_Swap_MVS | Si
TE007 | TU_TE007_Swap_MVS | Si
TE013 | TU_TE013_Swap_MVS | Si
TN001 | TU_TN001_Swap_MVS | Si
TN010 | TU_TN010_Swap_MVS | Si
TN130 | TU_TN130_Swap_MVS | Si | 1.53 |  | 2026-05-07 | 2026-05-07 | 2026-05-07 | Miguel Angel Garcia Martinez 00881238 |  | 2026-05-07 |  | Miguel Angel Garcia Martinez 00881238
TS012 | TU_TS012_Swap_MVS | Si
TS052 | TU_TS052_Swap_MVS | Si
KS173 | AMBA_102_KS173_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS237 | AMBA_102_KS237_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS348 | AMBA_102_KS348_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS349 | AMBA_102_KS349_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS375 | AMBA_102_KS375_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS608 | AMBA_102_KS608_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS374 | AMBA_103_BS374_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS107 | AMBA_104_BS107_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN105 | AMBA_106_BN105_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN243 | AMBA_106_BN243_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN266 | AMBA_106_BN266_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN322 | AMBA_108_KN322_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO059 | AMBA_110_KO059_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO066 | AMBA_110_KO066_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO215 | AMBA_110_KO215_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN214 | AMBA_115_KN214_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN269 | AMBA_116_KN269_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO050 | AMBA_116_KO050_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN188 | AMBA_117_CN188_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN267 | AMBA_117_CN267_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN355 | AMBA_117_CN355_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN174 | AMBA_120_BN174_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN249 | AMBA_120_BN249_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN103 | AMBA_121_KN103_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN258 | AMBA_121_KN258_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN323 | AMBA_121_KN323_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN175 | AMBA_122_BN175_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN226 | AMBA_122_BN226_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN166 | AMBA_123_KN166_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN202 | AMBA_123_KN202_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN203 | AMBA_123_KN203_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN364 | AMBA_123_KN364_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN118 | AMBA_126_KN118_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN087 | AMBA_127_KN087_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN194 | AMBA_129_CN194_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN209 | AMBA_130_KN209_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN016 | AMBA_131_CN016_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN363 | AMBA_131_KN363_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN079 | AMBA_132_KN079_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN080 | AMBA_132_KN080_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN134 | AMBA_132_KN134_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN163 | AMBA_132_KN163_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN206 | AMBA_132_KN206_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN303 | AMBA_132_KN303_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN082 | AMBA_133_KN082_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN259 | AMBA_133_KN259_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN109 | AMBA_134_KN109_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN154 | AMBA_134_KN154_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN155 | AMBA_134_KN155_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN215 | AMBA_134_KN215_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN063 | AMBA_135_CN063_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN314 | AMBA_135_CN314_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN318 | AMBA_135_CN318_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN025 | AMBA_136_CN025_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN142 | AMBA_136_CN142_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN142 | AMBA_136_CN142_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN214 | AMBA_136_CN214_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN317 | AMBA_136_CN317_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN448 | AMBA_136_CN448_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN454 | AMBA_136_CN454_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS102 | AMBA_136_CS102_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS102 | AMBA_136_CS102_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS073 | AMBA_137_CS073_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN027 | AMBA_138_CN027_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN228 | AMBA_138_CN228_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN280 | AMBA_138_CN280_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS277 | AMBA_138_CS277_RSH_OPT_4G |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS806 | AMBA_138_CS806_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN231 | AMBA_139_CN231_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN281 | AMBA_139_CN281_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN292 | AMBA_139_CN292_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN352 | AMBA_139_CN352_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN476 | AMBA_139_CN476_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN478 | AMBA_139_CN478_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS046 | AMBA_140_CS046_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS098 | AMBA_140_CS098_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS162 | AMBA_140_CS162_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS276 | AMBA_140_CS276_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN212 | AMBA_141_CN212_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN259 | AMBA_141_CN259_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN306 | AMBA_141_CN306_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN444 | AMBA_141_CN444_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN819 | AMBA_141_CN819_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN159 | AMBA_142_CN159_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN193 | AMBA_142_CN193_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN253 | AMBA_142_CN253_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN254 | AMBA_142_CN254_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN312 | AMBA_142_CN312_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN830 | AMBA_142_CN830_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN307 | AMBA_143_CN307_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN077 | AMBA_143_KN077_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN120 | AMBA_143_KN120_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN191 | AMBA_143_KN191_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN169 | AMBA_145_CN169_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN274 | AMBA_145_CN274_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN493 | AMBA_145_CN493_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN185 | AMBA_149_CN185_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN225 | AMBA_149_CN225_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN226 | AMBA_149_CN226_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN347 | AMBA_149_CN347_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS090 | AMBA_149_CS090_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS140 | AMBA_149_CS140_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS268 | AMBA_149_CS268_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS269 | AMBA_149_CS269_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN199 | AMBA_151_CN199_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN297 | AMBA_151_CN297_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN298 | AMBA_151_CN298_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN393 | AMBA_151_CN393_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN404 | AMBA_151_CN404_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN405 | AMBA_151_CN405_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN394 | AMBA_152_CN394_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN396 | AMBA_152_CN396_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN823 | AMBA_152_CN823_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS131 | AMBA_152_CS131_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS250 | AMBA_152_CS250_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS251 | AMBA_152_CS251_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS256 | AMBA_152_CS256_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS324 | AMBA_152_CS324_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN037 | AMBA_153_CN037_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN202 | AMBA_153_CN202_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN232 | AMBA_153_CN232_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN233 | AMBA_153_CN233_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN240 | AMBA_153_CN240_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN324 | AMBA_153_CN324_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN325 | AMBA_153_CN325_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN425 | AMBA_153_CN425_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN206 | AMBA_154_CN206_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN248 | AMBA_154_CN248_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN294 | AMBA_154_CN294_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN311 | AMBA_154_CN311_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN108 | AMBA_155_CN108_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN144 | AMBA_155_CN144_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN428 | AMBA_155_CN428_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN321 | AMBA_156_CN321_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN343 | AMBA_156_CN343_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN344 | AMBA_156_CN344_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN046 | AMBA_157_CN046_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN250 | AMBA_157_CN250_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN275 | AMBA_157_CN275_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN293 | AMBA_157_CN293_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN216 | AMBA_158_CN216_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN372 | AMBA_158_CN372_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN491 | AMBA_158_CN491_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM001 | AMBA_159_CM001_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM026 | AMBA_159_CM026_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM029 | AMBA_159_CM029_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM036 | AMBA_159_CM036_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN291 | AMBA_159_CN291_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN247 | AMBA_160_CN247_RSH_OPT_5G |  | 2.53 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN167 | AMBA_161_CN167_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN244 | AMBA_161_CN244_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN155 | AMBA_162_CN155_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU003 | AMBA_162_CU003_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU049 | AMBA_162_CU049_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU007 | AMBA_163_CU007_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU048 | AMBA_163_CU048_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU067 | AMBA_163_CU067_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS003 | AMBA_164_CS003_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS026 | AMBA_166_CS026_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS289 | AMBA_166_CS289_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU005 | AMBA_166_CU005_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU068 | AMBA_166_CU068_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS331 | AMBA_167_CS331_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS334 | AMBA_167_CS334_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS337 | AMBA_167_CS337_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM005 | AMBA_168_CM005_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU081 | AMBA_168_CU081_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN127 | AMBA_168_KN127_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CM033 | AMBA_170_CM033_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS002 | AMBA_171_CS002_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS029 | AMBA_171_CS029_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS127 | AMBA_171_CS127_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS133 | AMBA_171_CS133_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS136 | AMBA_171_CS136_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS219 | AMBA_171_CS219_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS272 | AMBA_171_CS272_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS105 | AMBA_178_CS105_RSH_OPT_5G |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS170 | AMBA_178_CS170_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS175 | AMBA_178_CS175_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS190 | AMBA_178_CS190_RSH_OPT_5G |  | 1.87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS224 | AMBA_178_CS224_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS293 | AMBA_178_CS293_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS347 | AMBA_178_CS347_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS618 | AMBA_178_KS618_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS464 | AMBA_179_KS464_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS067 | AMBA_180_BS067_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS120 | AMBA_180_KS120_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS144 | AMBA_181_BS144_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS326 | AMBA_183_KS326_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS189 | AMBA_187_KS189_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS198 | AMBA_187_KS198_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS097 | AMBA_188_BS097_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS203 | AMBA_190_KS203_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS102 | AMBA_194_BS102_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS176 | AMBA_194_BS176_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS372 | AMBA_194_BS372_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS111 | AMBA_196_KS111_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS184 | AMBA_196_KS184_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS325 | AMBA_196_KS325_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS607 | AMBA_196_KS607_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS081 | AMBA_198_BS081_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS069 | AMBA_199_BS069_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS093 | AMBA_199_BS093_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS094 | AMBA_199_BS094_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS194 | AMBA_199_BS194_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS195 | AMBA_199_BS195_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP048 | AMBA_200_LP048_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP061 | AMBA_202_LP061_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC058 | AMBA_203_LC058_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC014 | AMBA_204_LC014_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC046 | AMBA_205_LC046_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC021 | AMBA_207_LC021_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC031 | AMBA_207_LC031_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC033 | AMBA_207_LC033_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC034 | AMBA_207_LC034_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC038 | AMBA_207_LC038_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC039 | AMBA_207_LC039_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC052 | AMBA_207_LC052_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP031 | AMBA_209_LP031_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP127 | AMBA_209_LP127_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC026 | AMBA_211_LC026_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC053 | AMBA_211_LC053_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC055 | AMBA_211_LC055_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP045 | AMBA_215_LP045_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN511 | AMBA_220_BN511_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS192 | AMBA_227_KS192_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS231 | AMBA_227_KS231_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS286 | AMBA_227_KS286_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS482 | AMBA_227_KS482_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS282 | AMBA_228_KS282_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS080 | AMBA_229_BS080_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS114 | AMBA_229_BS114_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS230 | AMBA_229_BS230_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS233 | AMBA_229_BS233_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP109 | AMBA_239_LP109_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN078 | AMBA_24_BN078_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN149 | AMBA_24_BN149_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN276 | AMBA_24_BN276_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN095 | AMBA_253_BN095_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN104 | AMBA_254_KN104_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BO162 | AMBA_31_BO162_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BO363 | AMBA_36_BO363_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN147 | AMBA_56_BN147_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN484 | AMBA_56_BN484_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN489 | AMBA_56_BN489_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO032 | AMBA_58_KO032_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN092 | AMBA_63_BN092_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN118 | AMBA_63_BN118_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN148 | AMBA_63_BN148_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN263 | AMBA_64_BN263_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN231 | AMBA_67_BN231_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO197 | AMBA_78_KO197_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS287 | AMBA_80_BS287_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS090 | AMBA_82_BS090_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS117 | AMBA_82_BS117_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS158 | AMBA_82_BS158_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS159 | AMBA_82_BS159_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS110 | AMBA_83_BS110_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS304 | AMBA_83_BS304_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO037 | AMBA_86_KO037_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO193 | AMBA_86_KO193_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS472 | AMBA_86_KS472_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS116 | AMBA_90_KS116_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS300 | AMBA_90_KS300_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS134 | AMBA_91_BS134_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS196 | AMBA_92_BS196_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS033 | AMBA_97_CS033_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS119 | AMBA_99_CS119_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS141 | AMBA_99_CS141_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS144 | AMBA_99_CS144_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS163 | AMBA_99_CS163_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS279 | AMBA_99_CS279_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS280 | AMBA_99_CS280_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS302 | AMBA_99_CS302_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BC031 | AMBA_BC031_Swap_MVS | Si
BC075 | AMBA_BC075_Swap_MVS | Si
BC079 | AMBA_BC079_Swap_MVS | Si
BC116 | AMBA_BC116_Swap_MVS | Si
BC754 | AMBA_BC754_Swap_MVS | Si
BH039 | AMBA_BH039_Swap_MVS | Si | 0.53 | 2025-07-22 | 2025-07-23 | 2026-03-09 | 2026-03-09 | Miguel Angel Garcia Martinez 00881238 |  | 2025-07-24 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238 | [8 empty] | Etapa 01 | 07 | GLWINS05-01 pos 01 | Sala TX, 1er Piso | 06 | PPI Pending
BH041 | AMBA_BH041_Swap_MVS | Si | 1.53 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-22 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-22 | 2026-03-19 | Miguel Angel Garcia Martinez 00881238 | 16/03/2026: Aprobada por HW Solutions. 19/032026: AprobadAa por Ezequiel Fail.
BH042 | AMBA_BH042_Swap_MVS | Si |  | 2026-02-12 | 2026-02-12 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-13 | 2026-06-03 | Arvid Emmanuel Grados Zamudio 00922495
BH046 | AMBA_BH046_Swap_MVS | Si |  | 2025-07-22 | 2025-07-23 | 2025-11-10 | 2025-11-10 | Miguel Angel Garcia Martinez 00881238 |  | 2025-07-24 | 2025-11-17 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Survey Pending
BH051 | AMBA_BH051_Swap_MVS | Si | [8 empty] | 2025-10-23 | Arturo Gonzalo Antonio Cantu 00879903
BH071 | AMBA_BH071_Swap_MVS | Si | 1.2 |  |  | 2025-11-10 | 2025-11-10 | zhaofeng 00917583 |  |  | 2025-11-18 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobado por Nico Trubbo (18/11/2025) |  | 2026-02-19 | Tomas Ezequiel Sanchez WX1486917
BH144 | AMBA_BH144_Swap_MVS | Si
BH311 | AMBA_BH311_Swap_MVS | Si |  | 2026-01-21 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-04 | 2026-02-04 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Survey Pending
BN006 | AMBA_BN006_Swap_MVS | Si |  | 2025-11-18 | 2025-11-19 | 2026-01-28 | 2026-01-28 | Bautista Turri WX1450521 |  | 2025-11-20 | 2026-04-10 | Bautista Turri WX1450521
BN024 | AMBA_BN024_Swap_MVS | Si |  | 2025-11-18 | 2025-11-19 | 2026-01-02 | 2026-01-02 | David Encina WX1367993 |  | 2025-11-20 | 2026-04-22 | David Encina WX1367993
BN026 | AMBA_BN026_Swap_MVS | Si | 1.87 | 2025-10-29 | 2025-10-30 | 2025-12-15 | 2025-12-15 | Agustin Maria Bianchetti 00958351 |  | 2025-10-31 | 2026-04-22 | Agustin Maria Bianchetti 00958351
BN079 | AMBA_BN079_Swap_MVS | Si |  | 2025-11-03 | 2025-11-04 | 2025-11-06 | 2025-11-06 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-05 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238
BN091 | AMBA_BN091_Swap_MVS | Si | 1.53 | 2025-10-28 | 2025-10-29 | 2026-01-02 | 2026-01-02 | Agustin Maria Bianchetti 00958351 | Reasignada a Agustin Bianchetti el 02/01/2026 | 2025-10-30 | 2026-04-22 | Agustin Maria Bianchetti 00958351
BN099 | AMBA_BN099_Swap_MVS | Si
BN108 | AMBA_BN108_Swap_MVS | Si
BN115 | AMBA_BN115_Swap_MVS | Si |  | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | David Encina WX1367993 |  | 2026-05-04 | 2026-05-28 | David Encina WX1367993
BN118 | AMBA_BN118_Swap_MVS | Si |  | 2025-09-05 | 2025-09-08 | 2025-09-08 | 2025-09-08 | Adrian Guzman Garcia 00881507 |  | 2025-09-09 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238
BN123 | AMBA_BN123_Swap_MVS | Si
BN147 | AMBA_BN147_Swap_MVS | Si | 1.2 | 2025-08-12 | 2025-08-13 | 2025-08-13 | 2025-08-13 | David Encina WX1367993 |  | 2025-08-14 | 2026-02-06 | David Encina WX1367993 | RFI Ok ATC rezagado 19/02/2026: Aprobada R01 por HW |  | 2026-02-19 | Tomas Ezequiel Sanchez WX1486917
BN148 | AMBA_BN148_Swap_MVS | Si |  |  |  | 2025-08-13 | 2025-08-13 | GSC |  |  |  | GSC | Se instala sin el 5G
BN166 | AMBA_BN166_Swap_MVS | Si
BN167 | AMBA_BN167_Swap_MVS | Si
BN170 | AMBA_BN170_Swap_MVS | Si
BN182 | AMBA_BN182_Swap_MVS | Si |  | 2026-04-30 | 2026-04-30 | 2026-05-02 | 2026-05-02 | David Encina WX1367993 |  | 2026-05-05 | 2026-06-02 | David Encina WX1367993
BN188 | AMBA_BN188_Swap_MVS | Si |  | 2025-10-27 | 2025-10-28 | 2025-11-05 | 2025-11-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-29 | 2025-12-22 | Miguel Angel Garcia Martinez 00881238
BN192 | AMBA_BN192_Swap_MVS | Si |  | 2025-11-26 | 2025-11-27 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-28 | 2026-04-17 | Miguel Angel Garcia Martinez 00881238
BN210 | AMBA_BN210_Swap_MVS | Si |  | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-12 | Elvia Carolina Cortes Garcia 00881509 |  | 2025-12-12 | 2025-12-22 | Elvia Carolina Cortes Garcia 00881509
BN214 | AMBA_BN214_Swap_MVS | Si | 1.53 | 2025-10-13 | 2025-10-14 | 2025-11-12 | 2025-11-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-15 | 2026-05-13 | Miguel Angel Garcia Martinez 00881238
BN226 | AMBA_BN226_Swap_MVS | Si | 1.2 | 2025-09-05 | 2025-09-08 | 2025-09-05 | 2025-09-05 | GSC |  | 2025-09-09 | 2026-01-28 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-17 | Yes
BN231 | AMBA_BN231_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BN249 | AMBA_BN249_Swap_MVS | Si |  | 2025-09-10 | 2025-09-11 | 2025-09-10 | 2025-09-10 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-09-12 | 2026-03-09 | Miguel Angel Garcia Martinez 00881238
BN250 | AMBA_BN250_Swap_MVS | Si | [23 empty] | PPI Approved
BN268 | AMBA_BN268_Swap_MVS | Si |  |  |  | 2026-01-22 | 2026-01-22 | Miguel Angel Garcia Martinez 00881238
BN332 | AMBA_BN332_Swap_MVS | Si
BN402 | AMBA_BN402_Swap_MVS | Si |  | 2025-11-20 | 2025-11-21 | 2025-11-21 | 2025-11-21 | David Encina WX1367993 |  | 2025-11-24 | 2026-04-17 | David Encina WX1367993
BN403 | AMBA_BN403_Swap_MVS | Si |  | NA | NA | NA | NA | NA
BN431 | AMBA_BN431_Swap_MVS | Si |  | 2026-01-22 | 2026-01-22 | 2026-01-21 | 2026-01-21 | David Encina WX1367993 |  | 2026-01-23 |  | David Encina WX1367993
BN484 | AMBA_BN484_Swap_MVS | Si |  | NA | NA | NA | NA | NA | [17 empty] | PPI Approved
BN489 | AMBA_BN489_Swap_MVS | Si
BN880 | AMBA_BN880_Swap_MVS | Si | 1.87 | 2025-10-13 | 2025-10-14 | 2026-01-16 | 2026-01-16 | Tomas Ezequiel Sanchez WX1486917 |  | 2025-10-15 | 2026-04-27 | Tomas Ezequiel Sanchez WX1486917
BO030 | AMBA_BO030_Swap_MVS | Si
BO097 | AMBA_BO097_Swap_MVS | Si |  | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-10-31 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-31 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238
BO099 | AMBA_BO099_Swap_MVS | Si
BO102 | AMBA_BO102_Swap_MVS | Si |  | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-11 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-12 |  | Miguel Angel Garcia Martinez 00881238
BO106 | AMBA_BO106_Swap_MVS | Si |  | 2025-12-16 | 2025-12-17 | 2025-12-17 | 2025-12-17 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-18 | 2026-04-15 | Miguel Angel Garcia Martinez 00881238
BO107 | AMBA_BO107_Swap_MVS | Si |  | 2025-10-29 | 2025-10-30 | 2025-11-06 | 2025-11-06 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-31 |  | Miguel Angel Garcia Martinez 00881238
BO110 | AMBA_BO110_Swap_MVS | Si |  | 2025-10-15 | 2025-10-16 | 2025-11-04 | 2025-11-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-17 | 2026-02-06 | Miguel Angel Garcia Martinez 00881238 | 06/02/2026: Aprobada por Pablo Buono.
BO113 | AMBA_BO113_Swap_MVS | Si |  | 2025-01-10 | 2025-01-13 | 2025-01-13 | 2025-01-13 | Agustin Maria Bianchetti 00958351(GSC) |  | 2025-01-14 |  | Arturo Gonzalo Antonio Cantu 00879903
BO114 | AMBA_BO114_Swap_MVS | Si |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | 2026-01-08 | David Encina WX1367993 |  | 2026-01-12 | 2026-04-27 | David Encina WX1367993
BO120 | AMBA_BO120_Swap_MVS | Si
BO128 | AMBA_BO128_Swap_MVS | Si
BO140 | AMBA_BO140_Swap_MVS | Si |  | 2025-11-18 | 2025-11-19 | 2025-12-31 | 2025-12-31 | David Encina WX1367993 |  | 2025-11-20 |  | David Encina WX1367993
BO147 | AMBA_BO147_Swap_MVS | Si
BO183 | AMBA_BO183_Swap_MVS | Si |  | 2025-10-22 | 2025-10-23 | 2025-11-20 | 2025-11-20 | David Encina WX1367993 |  | 2025-10-24 | 2025-12-09 | David Encina WX1367993 | 09/12/2025: Aprobado por Nico Trubbo. | [12 empty] | Survey Pending
BO190 | AMBA_BO190_Swap_MVS | Si |  | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-18 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-18 | 2026-03-23 | Miguel Angel Garcia Martinez 00881238
BO202 | AMBA_BO202_Swap_MVS | Si
BO204 | AMBA_BO204_Swap_MVS | Si |  | 2025-12-08 | 2025-12-09 | 2025-12-09 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-10 |  | Miguel Angel Garcia Martinez 00881238
BO225 | AMBA_BO225_Swap_MVS | Si
BO249 | AMBA_BO249_Swap_MVS | Si |  | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-12 | Elvia Carolina Cortes Garcia 00881509 |  | 2025-12-12 | 2026-02-12 | Adrian Guzman Garcia 00881507
BO268 | AMBA_BO268_Swap_MVS | Si | [8 empty] | 2025-11-18 | Miguel Angel Garcia Martinez 00881238
BO296 | AMBA_BO296_Swap_MVS | Si | [8 empty] | 2025-11-18 | David Encina WX1367993
BO324 | AMBA_BO324_Swap_MVS | Si
BO373 | AMBA_BO373_Swap_MVS | Si |  | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-10 | Miguel Angel Garcia Martinez 00881238 |  | 2025-12-10 | 2026-04-10 | Miguel Angel Garcia Martinez 00881238
BO378 | AMBA_BO378_Swap_MVS | Si | [8 empty] | 2025-11-18 | Miguel Angel Garcia Martinez 00881238
BO435 | AMBA_BO435_Swap_MVS | Si | [8 empty] | 2025-11-18 | Miguel Angel Garcia Martinez 00881238
BO471 | AMBA_BO471_Swap_MVS | Si
BO803 | AMBA_BO803_Swap_MVS | Si |  | 2025-10-27 | 2025-10-28 | 2025-11-04 | 2025-11-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-29 | 2025-11-18 | Miguel Angel Garcia Martinez 00881238
BO806 | AMBA_BO806_Swap_MVS | Si |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-29 | 2026-05-05 | Joaquin Alejandro Luduena WX1488820
BO827 | AMBA_BO827_Swap_MVS | Si
BS006 | AMBA_BS006_Swap_MVS | Si
BS009 | AMBA_BS009_Swap_MVS | Si
BS050 | AMBA_BS050_Swap_MVS | Si | 1.53 | 2025-03-18 | 2025-03-19 | 2025-03-19 | 2025-03-19 | Daniel Horacio Rocabado WX1372513 |  |  | 2026-04-01 | David Encina WX1367993 | RFI Ok 07/08/2025: Aprobada |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-22 | Yes
BS059 | AMBA_BS059_Swap_MVS | Si
BS061 | AMBA_BS061_Swap_MVS | Si |  |  |  | 2025-03-25 | 2025-03-25 | GSC | [17 empty] | PPI Pending
BS063 | AMBA_BS063_Swap_MVS | Si
BS065 | AMBA_BS065_Swap_MVS | Si | 0.87 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-10 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-01-10 | 2025-09-19 | David Encina WX1367993 | RFI Ok 21/01/2026: Se envio nuevo diseño con Standard TECO. |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-17 | Yes
BS077 | AMBA_BS077_Swap_MVS | Si |  | 2025-06-20 | 2025-06-21 | 2025-07-01 | 2025-07-01 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-06-29 |  | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BS087 | AMBA_BS087_Swap_MVS | Si | 1.53 | 2025-01-29 | 2025-01-30 | 2025-01-29 | 2025-01-29 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-01-29 | 2025-06-18 | David Encina WX1367993 | RFI Ok 21/01/2026: Se envio nuevo diseño con Standard TECO. Aprobada por David Masessa el 22/01/2026. |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820
BS088 | AMBA_BS088_Swap_MVS | Si |  | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-08-28 | David Encina WX1367993 |  | 2025-09-01 | 2026-06-05 | David Encina WX1367993 | 02/06/2026: PROPUESTA OK#， CON OBSERVACIONES – ACTUALZIAR ESQUEMA DE PLACAS DE BBU ( POR CAPACIDAD Y RSH) Y RRU 02/06/2026: Propuest aprobada enviada el 28/08/2025.
BS105 | AMBA_BS105_Swap_MVS | Si | 0.87 | 2025-01-10 | 2025-01-13 | 2025-01-15 | 2025-01-15 | Miguel Angel Garcia Martinez 00881238 |  | 2025-01-14 | 2026-01-16 | Miguel Angel Garcia Martinez 00881238 | En stock. Guzmán Nacich |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-17 | Yes
BS107 | AMBA_BS107_Swap_MVS | Si | 1.2 | [7 empty] | 2025-05-10 | Daniel Horacio Rocabado WX1372513 | RFI Ok |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820
BS124 | AMBA_BS124_Swap_MVS | Si
BS125 | AMBA_BS125_Swap_MVS | Si | [8 empty] | 2025-11-19 | David Encina WX1367993 | [13 empty] | PPI Approved
BS140 | AMBA_BS140_Swap_MVS | Si | 1.87 | 2025-10-29 | 2025-10-30 | 2025-10-30 | 2025-10-30 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-31 | 2026-03-16 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-16 | Yes
BS210 | AMBA_BS210_Swap_MVS | Si | 1.53 | 2025-01-10 | 2025-01-13 | 2025-01-14 | 2025-01-14 | Miguel Angel Garcia Martinez 00881238 |  | 2025-01-14 | 2025-06-06 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | PPI Approved
BS211 | AMBA_BS211_Swap_MVS | Si | 1.87 | 2025-12-31 | 2026-01-02 | 2025-12-31 | 2026-01-02 | Agustin Maria Bianchetti 00958351 |  | 2026-01-05 | 2026-01-06 | Agustin Maria Bianchetti 00958351
BS216 | AMBA_BS216_Swap_MVS | Si | 1.2 |  |  | 2025-06-26 | 2025-06-26 | zhaofeng 00917583 |  |  | 2025-07-04 | Arturo Gonzalo Antonio Cantu 00879903(GSC) | RFI Ok
BS241 | AMBA_BS241_Swap_MVS | Si
BS246 | AMBA_BS246_Swap_MVS | Si |  | 2025-10-29 | 2025-10-30 | 2026-03-12 | 2026-03-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-31 | 2026-04-08 | Miguel Angel Garcia Martinez 00881238 | [5 empty] | 2026-05-16 | Yes
BS248 | AMBA_BS248_Swap_MVS | Si
BS257 | AMBA_BS257_Swap_MVS | Si
BS263 | AMBA_BS263_Swap_MVS | Si
BS298 | AMBA_BS298_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BS302 | AMBA_BS302_Swap_MVS | Si |  | 2025-10-28 | 2025-10-29 | 2025-12-16 | 2025-12-16 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-30 | 2025-12-22 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-11 | Tomas Ezequiel Sanchez WX1486917
BS308 | AMBA_BS308_Swap_MVS | Si | 0.87 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-24 | Miguel Angel Garcia Martinez 00881238 |  | 2025-07-24 | 2025-08-07 | Arturo Gonzalo Antonio Cantu 00879903 | [8 empty] | Etapa 02 | 22 | LNGINS05-01 pos 03 | Sala TX, P.B. | 36 | Installed
BS314 | AMBA_BS314_Swap_MVS | Si | 1.53 | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-17 | David Encina WX1367993 |  | 2026-03-19 | 2026-03-19 | David Encina WX1367993
BS367 | AMBA_BS367_Swap_MVS | Si
CN025 | AMBA_CN025_Swap_MVS | Si |  | 2025-10-13 | 2025-10-14 | 2025-10-14 | 2025-10-17 | Miguel Angel Garcia Martinez 00881238 | Missing PDG#， planning 2026 | 2025-10-15 |  | Miguel Angel Garcia Martinez 00881238
CN185 | AMBA_CN185_Swap_MVS | Si |  | 2025-09-01 | 2025-09-02 | 2025-09-12 | 2025-09-12 | Adrian Guzman Garcia 00881507 |  | 2025-09-03 | 2026-04-30 | Miguel Angel Garcia Martinez 00881238
CN186 | AMBA_CN186_Swap_MVS | Si | 1.2 |  |  | 2026-01-20 | 2026-01-20 | zhaofeng 00917583 |  |  | 2026-01-23 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. 24/01/2026: Se envio R01 por ajuste al formato Standard TECO. | [6 empty] | Pending Subrack | Etapa 01 | 15 | VLEINS05-01 pos 01 | Sala TX, 1er Piso | 05 | Installed with Issue
CN188 | AMBA_CN188_Swap_MVS | Si |  |  |  | 2026-05-04 | 2026-05-04 | Arturo Gonzalo Antonio Cantu 00879903
CS001 | AMBA_CS001_Swap_MVS | Si |  | 2025-09-02 | 2025-09-03 | 2025-11-03 | 2025-11-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-09-04 |  | Miguel Angel Garcia Martinez 00881238
CS014 | AMBA_CS014_Swap_MVS | Si | 1.2 |  |  | 2026-01-01 | 2026-01-01 | zhaofeng 00917583 |  |  | 2026-01-09 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok | [6 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
CS026 | AMBA_CS026_Swap_MVS | Si
CS090 | AMBA_CS090_Swap_MVS | Si | 0.87 |  |  | 2026-01-20 | 2026-01-20 | zhaofeng 00917583 |  |  | 2026-01-23 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobado por Pablo Buono el 17/12/2025. 25/01/2026: Se envio R01 por ajuste al formato Standard TECO. | [6 empty] | SWAP cerrado en el Proyecto 56A0SZK | [5 empty] | Ready for Dismantle
CS098 | AMBA_CS098_Swap_MVS | Si | [18 empty] | Etapa 02 | 10 | CLPINS05-02 pos 03 | Sala TX, 4to piso | 20 | Installed
CS102 | AMBA_CS102_Swap_MVS | Si | 1.2 |  |  | 2025-10-28 | 2025-10-28 | zhaofeng 00917583 |  |  | 2025-10-31 | Arturo Gonzalo Antonio Cantu 00879903(GSC) | RFI Ok | [6 empty] | SWAP cerrado en el Proyecto 56A0SZK | [5 empty] | Ready for Dismantle
CS107 | AMBA_CS107_Swap_MVS | No | [10 empty] | RFI Ok | [12 empty] | Ready for Dismantle
CS119 | AMBA_CS119_Swap_MVS | Si |  | 2025-10-08 | 2025-10-09 | 2026-02-16 | 2026-02-16 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-10 |  | Miguel Angel Garcia Martinez 00881238
CS143 | AMBA_CS143_Swap_MVS | Si |  | 2025-10-09 | 2025-10-10 | 2025-10-08 | 2025-10-08 | Elvia Carolina Cortes Garcia 00881509 |  | 2025-10-13 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 | Aprobado por Nico Trubbo el 09/12/2025. 12/02/2026: Se envia propuesta con 5G a pedido del cliente. 20/02/2026: Aprobada por Nico Trubbo
CS175 | AMBA_CS175_Swap_MVS | Si |  | 2025-10-02 | 2025-10-03 | 2025-09-30 | 2025-09-30 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-06 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
CS352 | AMBA_CS352_Swap_MVS | Si |  | 2025-10-02 | 2025-10-03 | 2025-12-12 | 2025-12-12 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-06 | 2026-04-17 | Miguel Angel Garcia Martinez 00881238
KN049 | AMBA_KN049_Swap_MVS | Si |  | NA | NA | NA | NA | NA | [17 empty] | Survey Done
KN060 | AMBA_KN060_Swap_MVS | Si | [9 empty] | Daniel Horacio Rocabado WX1372513 | [13 empty] | SubRack Installed
KN251 | AMBA_KN251_Swap_MVS | Si | [17 empty] | Wicaps | [5 empty] | Survey Done
KN255 | AMBA_KN255_Swap_MVS | Si
KN350 | AMBA_KN350_Swap_MVS | Si
KO004 | AMBA_KO004_Swap_MVS | Si | 1.87 | 2025-03-03 | 2025-03-04 | 2025-03-04 | 2025-03-04 |  |  | 2025-03-05 | 2025-12-22 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917
KO008 | AMBA_KO008_Swap_MVS | Si |  | 2024-10-08 | 2024-10-09 | 2024-10-18 | 2024-10-18 | GSC |  | 2025-01-23 | 2025-01-23 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Ready for Dismantle
KO010 | AMBA_KO010_Swap_MVS | Si
KO023 | AMBA_KO023_Swap_MVS | Si |  | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-10-31 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-31 |  | Miguel Angel Garcia Martinez 00881238
KO041 | AMBA_KO041_Swap_MVS | Si |  | 2024-12-10 | 2024-12-11 | 2024-12-24 | 2024-12-24 | Adrian Guzman Garcia 00881507 | Dec 24: to be sent | 2025-04-16 | 2026-03-19 | Adrian Guzman Garcia 00881507 | [13 empty] | PPI Approved
KO042 | AMBA_KO042_Swap_MVS | Si |  | 2025-04-11 | 2025-04-14 | 2025-04-11 | 2025-04-11 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-04-15 | 2026-05-04 | Miguel Angel Garcia Martinez 00881238
KO238 | AMBA_KO238_Swap_MVS | Si
KO240 | AMBA_KO240_Swap_MVS | Si |  | NA | NA | NA | NA | NA | [17 empty] | PPI Approved
KS008 | AMBA_KS008_Swap_MVS | Si | 1.87 | 2025-10-22 | 2025-10-23 | 2025-10-08 | 2025-10-08 | David Encina WX1367993 |  | 2025-10-24 | 2025-11-19 | David Encina WX1367993 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820
KS009 | AMBA_KS009_Swap_MVS | Si | 1.2 | 2025-10-22 | 2025-10-23 | 2025-10-27 | 2025-10-27 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-24 | 2026-03-23 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820
KS018 | AMBA_KS018_Swap_MVS | Si | 1.53 |  |  | 2025-12-08 | 2025-12-08 | zhaofeng 00917583 |  |  | 2025-12-16 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok 25/01/2026: Se envió R01 por ajuste al formato Standard TECO. Aprobada por David Masessa el 26/01/2026. |  | 2026-02-06 | Joaquin Alejandro Luduena WX1488820
KS023 | AMBA_KS023_Swap_MVS | Si | 1.87 | 2025-10-17 | 2025-10-20 | 2025-10-23 | 2025-10-23 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-21 | 2025-11-04 | Miguel Angel Garcia Martinez 00881238 | RFI Ok | 2026-02-13 | 2026-02-13 | Agustin Maria Bianchetti 00958351
KS037 | AMBA_KS037_Swap_MVS | Si | 1.87 | 2025-10-17 | 2025-10-20 | 2025-10-20 | 2025-10-20 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-21 | 2025-11-04 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-22 | Yes
KS065 | AMBA_KS065_Swap_MVS | Si | [19 empty] | 14 | MRCINS05-01 pos 01 | Sala TX, 1er piso | 06
KS067 | AMBA_KS067_Swap_MVS | Si
KS090 | AMBA_KS090_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KS105 | AMBA_KS105_Swap_MVS | Si | 1.53 | 2025-10-23 | 2025-10-24 | 2025-10-17 | 2025-10-17 | Elvia Carolina Cortes Garcia 00881509 |  | 2025-10-27 | 2025-12-09 | Elvia Carolina Cortes Garcia 00881509 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820
KS107 | AMBA_KS107_Swap_MVS | Si | [23 empty] | Ready for Dismantle
KS108 | AMBA_KS108_Swap_MVS | Si |  | 2025-10-22 | 2025-10-23 | 2025-11-07 | 2025-11-07 | David Encina WX1367993 | On hold#， needs survey. | 2025-10-24 | 2026-03-17 | David Encina WX1367993
KS111 | AMBA_KS111_Swap_MVS | Si | 1.87 |  |  | 2025-11-02 | 2025-11-02 | zhaofeng 00917583 |  |  | 2025-11-10 | Arturo Gonzalo Antonio Cantu 00879903(GSC) | RFI Ok |  | 2026-03-12 | David Encina WX1367993
KS134 | AMBA_KS134_Swap_MVS | Si | 1.87 |  |  | 2025-10-27 | 2025-10-27 | zhaofeng 00917583 |  |  | 2025-11-04 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok 25-01/2026: Se envio R02 por ajuste al formato Standard TECO. |  | 2026-02-06 | Joaquin Alejandro Luduena WX1488820
KS142 | AMBA_KS142_Swap_MVS | Si | 1.53 | 2025-10-21 | 2025-10-22 | 2025-10-24 | 2025-10-24 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-23 | 2026-01-28 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 |  |  | Yes | [6 empty] | PPI Approved
KS143 | AMBA_KS143_Swap_MVS | Si | [8 empty] | 2025-05-13 | Arturo Gonzalo Antonio Cantu 00879903(GSC)
KS147 | AMBA_KS147_Swap_MVS | Si | [23 empty] | PPI Approved
KS151 | AMBA_KS151_Swap_MVS | Si | 1.87 | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-29 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-27 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 | RFI Ok |  | 2026-03-10 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-17 | Yes
KS201 | AMBA_KS201_Swap_MVS | Si | [23 empty] | PPI Approved
KS202 | AMBA_KS202_Swap_MVS | Si |  | 2024-10-15 | 2024-10-16 | 2024-10-21 | 2024-10-21 | GSC |  |  | 2025-11-18 | Miguel Angel Garcia Martinez 00881238
KS342 | AMBA_KS342_Swap_MVS | Si | [9 empty] | Claudio Romeo WX1379521 | [7 empty] | Pending Subrack | Etapa 02 | 14 | MRCINS05-01 pos 03 | Sala TX, 1er piso | 06 | Installed with Issue
KS374 | AMBA_KS374_Swap_MVS | Si | 0.87 |  |  | 2026-01-23 | 2026-01-23 | zhaofeng 00917583 |  | 2026-01-26 | 2026-01-26 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok 26/01/2026: Se envio R02 por ajuste al formato Standard TECO. | 2026-02-13 | 2026-02-13 | Agustin Maria Bianchetti 00958351
KS378 | AMBA_KS378_Swap_MVS | Si | 1.53 |  |  | 2025-09-11 | 2025-09-11 | zhaofeng 00917583 |  |  | 2025-09-19 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok
KS401 | AMBA_KS401_Swap_MVS | Si | 1.2 | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-29 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-27 | 2026-01-29 | Miguel Angel Garcia Martinez 00881238 | RFI Ok Aprobado por Nico Trubbo (18/11/2025). 24/01/2026: Se envio R01 por ajuste al formato Standard TECO. 29/01/2026: Aprobada por David Masessa. |  | 2026-03-03 | Joaquin Alejandro Luduena WX1488820
KS425 | AMBA_KS425_Swap_MVS | Si | 1.2 |  |  | 2026-01-20 | 2026-01-20 | zhaofeng 00917583 |  | 2026-01-23 | 2026-01-23 | David Encina WX1367993 | RFI Ok 23/01/2026: Se envio R03 por ajuste al formato Standard TECO. 27/01/2026: Aprobada R03 por David Masessa. |  | 2026-02-09 | Abraham Jesus Salas Marfil 00237943
KS446 | AMBA_KS446_Swap_MVS | Si
KS494 | AMBA_KS494_Swap_MVS | Si
KS622 | AMBA_KS622_Swap_MVS | Si
KS623 | AMBA_KS623_Swap_MVS | Si
KS624 | AMBA_KS624_Swap_MVS | Si
KS626 | AMBA_KS626_Swap_MVS | Si
KS627 | AMBA_KS627_Swap_MVS | Si
KS628 | AMBA_KS628_Swap_MVS | Si
KS629 | AMBA_KS629_Swap_MVS | Si
KS630 | AMBA_KS630_Swap_MVS | Si
KS631 | AMBA_KS631_Swap_MVS | Si
KS632 | AMBA_KS632_Swap_MVS | Si
KS633 | AMBA_KS633_Swap_MVS | Si
KS634 | AMBA_KS634_Swap_MVS | Si
KS635 | AMBA_KS635_Swap_MVS | Si
KS637 | AMBA_KS637_Swap_MVS | Si
KS639 | AMBA_KS639_Swap_MVS | Si
KS644 | AMBA_KS644_Swap_MVS | Si
KS701 | AMBA_KS701_Swap_MVS | Si | 1.53 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-29 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-28 | 2025-11-04 | Miguel Angel Garcia Martinez 00881238 | Asignado a NG |  | 2026-03-10 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-16 | Yes
KS702 | AMBA_KS702_Swap_MVS | Si | 1.2 |  |  | 2025-10-01 | 2025-10-01 | zhaofeng 00917583 |  |  | 2025-10-09 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok
KS707 | AMBA_KS707_Swap_MVS | Si | 1.2 | [7 empty] | 2026-03-18 | Agustin Maria Bianchetti 00958351 | RFI Ok |  | 2026-03-12 | David Encina WX1367993 |  | 2026-05-29 | Yes
KS711 | AMBA_KS711_Swap_MVS | Si | [23 empty] | PPI Approved
KS908 | AMBA_KS908_Swap_MVS | Si |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | Miguel Angel Garcia Martinez 00881238 |  | 2025-10-24 | 2025-12-09 | Miguel Angel Garcia Martinez 00881238 | Aprobado por Nico Trubbo el 09/12/2025.
LP037 | AMBA_LP037_Swap_MVS | Si
BM606 | AllRegion_ClusterOPT_Feb_TLF |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LC007 | AllRegion_ClusterOPT_Jan |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AllRegion_ClusterOPT_TLF_V2 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARBA6402 | BA_ARBA6402_FARM_Etapa1_MVS
BB092 | BA_BB092_Swap_MVS | Si | 1.87 | 2025-11-20 | 2025-11-21 | 2025-12-01 | 2025-12-01 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-24 | 2025-12-11 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
BB310 | BA_BB310_Swap_MVS | Si | 1.53 | 2025-11-18 | 2025-11-19 | 2025-11-26 | 2025-11-26 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-20 | 2025-12-02 | Miguel Angel Garcia Martinez 00881238 | [7 empty] | SWAP cerrado en el Proyecto 56A0T4Y | [5 empty] | Ready for Dismantle
A33-O003 | MEDI_A33-O003_Mod_TA | Si |  | N/A |  | N/A
A33-O005 | MEDI_A33-O005_Mod_TA | Si |  | N/A |  | N/A
A33-O013 | MEDI_A33-O013_Mod_TA | Si |  | N/A | 2026-06-02 | N/A |  | David Encina WX1367993 |  | 2026-06-04 |  | David Encina WX1367993
A33-O054 | MEDI_A33-O054_Mod_TA | Si | 0.87 | N/A | 2026-04-30 | N/A | 2026-04-30 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-05 |  | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 2026-05-31 | Yes
A33-O058 | MEDI_A33-O058_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O061 | MEDI_A33-O061_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O063 | MEDI_A33-O063_Mod_TA | Si |  | NA | NA | NA | NA | NA |  |  | 2026-06-05 | Abraham Jesus Salas Marfil 00237943
A33-O065 | MEDI_A33-O065_Mod_TA | Si |  | N/A |  | N/A
A33-O066 | MEDI_A33-O066_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O067 | MEDI_A33-O067_Mod_TA | Si |  | N/A | 2026-05-14 | N/A | 2026-06-01 | GSC |  | 2026-05-18
A33-O068 | MEDI_A33-O068_Mod_TA | Si |  | N/A |  | N/A
A33-O069 | MEDI_A33-O069_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O071 | MEDI_A33-O071_Mod_TA | Si | 0.87 | N/A | 2026-04-29 | N/A | 2026-05-12 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-30 |  | Arturo Gonzalo Antonio Cantu 00879903 | [5 empty] | 2026-05-31 | Yes
A33-O075 | MEDI_A33-O075_Mod_TA | Si | 0.87 | N/A |  | N/A
A33-O079 | MEDI_A33-O079_Mod_TA | Si | 1.2 | N/A |  | N/A | 2026-04-09 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-06-04 | Miguel Angel Garcia Martinez 00881238 | 08/06/2026: Ok con observaciones. Aprobada por Martin Cuocci.
A33-O084 | MEDI_A33-O084_Mod_TA | Si |  | N/A |  | N/A | 2026-04-06 | Joaquin Alejandro Luduena WX1488820 |  |  | 2026-05-11 | Joaquin Alejandro Luduena WX1488820
A33-O085 | MEDI_A33-O085_Mod_TA | Si | 0.87 | N/A | 2026-05-04 | N/A | 2026-05-05 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-05-06 |  | Arturo Gonzalo Antonio Cantu 00879903
A33-O118 | MEDI_A33-O118_Mod_TA | Si |  | N/A |  | N/A
A33-O120 | MEDI_A33-O120_Mod_TA | Si |  | N/A | 2026-04-14 | N/A | 2026-04-23 | Arturo Gonzalo Antonio Cantu 00879903(GSC)
A33-O131 | MEDI_A33-O131_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-03-19 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-05-28 | Miguel Angel Garcia Martinez 00881238
A33-O133 | MEDI_A33-O133_Mod_TA | Si |  | N/A |  | N/A
A33-O149 | MEDI_A33-O149_Mod_TA | Si |  | N/A |  | N/A
A33-O153 | MEDI_A33-O153_Mod_TA | Si |  | N/A |  | N/A
A33-O157 | MEDI_A33-O157_Mod_TA | Si | 0.87 | N/A |  | N/A
A33-O158 | MEDI_A33-O158_Mod_TA | Si |  | N/A | 2026-04-14 | N/A | 2026-04-24 | Arturo Gonzalo Antonio Cantu 00879903
A33-O162 | MEDI_A33-O162_Mod_TA | Si |  | N/A |  | N/A
A33-O165 | MEDI_A33-O165_Mod_TA | Si |  | N/A |  | N/A | 2026-03-21 | Arturo Gonzalo Antonio Cantu 00879903
A33-O177 | MEDI_A33-O177_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O194 | MEDI_A33-O194_Mod_TA | Si |  | N/A |  | N/A | 2026-04-13 | Joaquin Alejandro Luduena WX1488820
A33-O195 | MEDI_A33-O195_Mod_TA | Si | 0.87 | N/A | 2026-04-30 | N/A | 2026-04-30 | Tomas Ezequiel Sanchez WX1486917 |  |  |  | Tomas Ezequiel Sanchez WX1486917
A33-O246 | MEDI_A33-O246_Mod_TA | Si | 0.87 | N/A | 2026-04-18 | N/A | 2026-04-20 | Tomas Ezequiel Sanchez WX1486917 |  |  | 2026-05-11 | Tomas Ezequiel Sanchez WX1486917 | [5 empty] | 2026-06-01 | Yes
A33-O249 | MEDI_A33-O249_Mod_TA | Si | 1.2 | N/A | 2026-04-16 | N/A | 2026-04-30 | Mario Andres Silva Martin 00866503 |  | 2026-04-20 | 2026-05-29 | Miguel Angel Garcia Martinez 00881238
A33-O316 | MEDI_A33-O316_Mod_TA | Si |  | N/A |  | N/A
A33-O319 | MEDI_A33-O319_Mod_TA | Si |  | N/A |  | N/A | 2026-04-01 | Joaquin Alejandro Luduena WX1488820
A33-O320 | MEDI_A33-O320_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O359 | MEDI_A33-O359_Mod_TA | Si |  | NA | NA | NA | NA | NA
A33-O369 | MEDI_A33-O369_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-04-01 | Tomas Ezequiel Sanchez WX1486917 |  |  |  | Tomas Ezequiel Sanchez WX1486917
A33-O380 | MEDI_A33-O380_Mod_TA | Si |  | N/A |  | N/A
A33-O382 | MEDI_A33-O382_Mod_TA | Si | 0.53 | N/A | 2026-04-24 | N/A | 2026-05-05 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-28 | 2026-06-02 | Arturo Gonzalo Antonio Cantu 00879903
A33-O383 | MEDI_A33-O383_Mod_TA | Si |  | N/A |  | N/A
A33-O384 | MEDI_A33-O384_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-04-06 | Tomas Ezequiel Sanchez WX1486917 |  |  | 2026-05-11 | Tomas Ezequiel Sanchez WX1486917
A33-O386 | MEDI_A33-O386_Mod_TA | Si |  | N/A |  | N/A
A33-O419 | MEDI_A33-O419_Mod_TA | Si |  | N/A |  | N/A
A33-O655 | MEDI_A33-O655_Mod_TA | Si |  | N/A |  | N/A
A33-O734 | MEDI_A33-O734_Mod_TA | Si |  | N/A |  | N/A
A35-D001 | MEDI_A35-D001_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-04-10 | Arturo Gonzalo Antonio Cantu 00879903
A35-D002 | MEDI_A35-D002_Mod_TA | Si |  | N/A |  | N/A | 2026-03-06 | Elvia Carolina Cortes Garcia 00881509
A35-D011 | MEDI_A35-D011_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-20 | Luis Fernando Castro Ortega 00881502
A35-D037 | MEDI_A35-D037_Mod_TA | Si | 1.53 | N/A |  | N/A | 2026-03-12 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-06-02 | David Encina WX1367993
A35-D038 | MEDI_A35-D038_Mod_TA | Si |  | N/A |  | N/A | 2026-03-06 | Elvia Carolina Cortes Garcia 00881509
A35-D039 | MEDI_A35-D039_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-03-09 | Elvia Carolina Cortes Garcia 00881509 |  | 2026-06-02 | 2026-06-02 | Arturo Gonzalo Antonio Cantu 00879903
A35-D041 | MEDI_A35-D041_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-09 | Elvia Carolina Cortes Garcia 00881509
A35-D042 | MEDI_A35-D042_Mod_TA | Si |  | N/A |  | N/A | 2026-03-05 | Elvia Carolina Cortes Garcia 00881509
A35-D043 | MEDI_A35-D043_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-12 | Arturo Gonzalo Antonio Cantu 00879903
A35-D044 | MEDI_A35-D044_Mod_TA | Si |  | N/A |  | N/A | 2026-03-09 | Elvia Carolina Cortes Garcia 00881509
A35-D056 | MEDI_A35-D056_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-17 | Luis Fernando Castro Ortega 00881502
A35-D073 | MEDI_A35-D073_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-04-10 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-05-18 | Arturo Gonzalo Antonio Cantu 00879903
A35-D074 | MEDI_A35-D074_Mod_TA | Si |  | N/A |  | N/A | 2026-03-21 | Arturo Gonzalo Antonio Cantu 00879903
A35-D126 | MEDI_A35-D126_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-25 | Luis Fernando Castro Ortega 00881502 |  | 2026-06-04 | 2026-06-04 | Arturo Gonzalo Antonio Cantu 00879903
A37-F039 | MEDI_A37-F039_Mod_TA | Si |  | N/A |  | N/A | 2026-06-06 | Joaquin Alejandro Luduena WX1488820
A37-F040 | MEDI_A37-F040_Mod_TA | Si |  | N/A | 2026-06-05 | N/A | 2026-06-05 | GSC |  | 2026-06-09
MC345 | MEDI_MC345_SWAP_MVS | Si | 0.53
ARME0060 | MZA_ARME0060_FARM_Etapa1_MVS
ARME0006 | MZ_ARME0006_FARM_Dismantle_MVS
ARME0009 | MZ_ARME0009_FARM_Dismantle_MVS
ARME0014 | MZ_ARME0014_FARM_Dismantle_MVS
ARME0061 | MZ_ARME0061_FARM_Dismantle_MVS
ARME0062 | MZ_ARME0062_FARM_Dismantle_MVS
ARME0099 | MZ_ARME0099_FARM_Dismantle_MVS
ARME0115 | MZ_ARME0115_FARM_Dismantle_MVS
ARME0702 | MZ_ARME0702_FARM_Dismantle_MVS
ARME0817 | MZ_ARME0817_FARM_Dismantle_MVS
ARME0838 | MZ_ARME0838_FARM_Dismantle_MVS
ARME0840 | MZ_ARME0840_FARM_Dismantle_MVS
ARME0841 | MZ_ARME0841_FARM_Dismantle_MVS
ARME0842 | MZ_ARME0842_FARM_Dismantle_MVS
ARME0843 | MZ_ARME0843_FARM_Dismantle_MVS
ARME0849 | MZ_ARME0849_FARM_Dismantle_MVS
ARME0864 | MZ_ARME0864_FARM_Dismantle_MVS
ARME1042 | MZ_ARME1042_FARM_Dismantle_MVS
ARNQ0017 | NQ_ARNQ0017_FARM_Etapa2_MVS
QC048 | NQ_QC048_Swap_MVS | Si | 1.87 |  |  | 2025-05-30 | 2025-05-30 | zhaofeng 00917583 |  |  | 2026-01-23 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok. Aprobada por Pablo Buono el 23/01/2026. |  | 2026-02-05 | Tomas Ezequiel Sanchez WX1486917
QC053 | NQ_QC053_Swap_MVS | Si | 1.87 | 2025-01-21 | 2025-01-22 | 2025-01-24 | 2025-01-24 | Miguel Angel Garcia Martinez 00881238 |  | 2025-01-23 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 | RFI Ok. Aprobada por Nico Trubbo el 23/01/2026. 20/02/2026: Se sube R02 con cambios solicitados por el cliente. |  | 2026-02-05 | Joaquin Alejandro Luduena WX1488820
QC349 | NQ_QC349_Swap_MVS | Si |  | 2025-03-03 | 2025-03-04 | 2025-03-07 | 2025-03-07 | Arturo Gonzalo Antonio Cantu 00879903 | March 03 PDG missing March 07#， CUSTOMER RELEASED SITE | 2025-03-05
QE029 | NQ_QE029_Swap_MVS | Si
QS003 | NQ_QS003_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS003 | NQ_QS003_Swap_MVS | Si | 0.87 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 |  | 2026-02-24 | 2026-02-23 | Miguel Angel Garcia Martinez 00881238 | En stock. Guzmán Nacich |  |  |  |  | 2026-05-20 | Yes |  |  | 12 | VANINS05-01 pos 02 | TXSala TX, P.B. | 10 | SubRack Installed
RS027 | RN_RS027_Swap_MVS | Si | 1.2 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | David Encina WX1367993 |  | 2026-03-16 | 2026-04-16 | David Encina WX1367993
RS033 | RN_RS033_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS033 | RN_RS033_Swap_MVS | Si | 1.87 | 2026-03-17 | 2026-03-18 | 2026-03-25 | 2026-03-25 | David Encina WX1367993 |  | 2026-03-19 | 2026-04-07 | David Encina WX1367993
RS035 | RN_RS035_Swap_MVS | Si | 1.53 | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-12 | 2026-03-13 | Miguel Angel Garcia Martinez 00881238
RS036 | RN_RS036_Swap_MVS | Si | 1.87 | 2026-03-12 | 2026-03-13 | 2026-03-17 | 2026-03-17 | David Encina WX1367993 |  | 2026-03-16 | 2026-04-08 | David Encina WX1367993 | [5 empty] | 2026-05-20 | Yes
QE005 | SUR_123_QE005_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE004 | SUR_128_QE004_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE004 | SUR_128_QE004_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE029 | SUR_128_QE029_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QE053 | SUR_128_QE053_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC044 | SUR_130_QC044_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC054 | SUR_130_QC054_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC001 | SUR_131_QC001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC003 | SUR_131_QC003_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC058 | SUR_131_QC058_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC074 | SUR_131_QC074_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC105 | SUR_131_QC105_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC149 | SUR_131_QC149_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC346 | SUR_131_QC346_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q092 | SUR_132_A30-Q092_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q255 | SUR_132_A30-Q255_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q257 | SUR_132_A30-Q257_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q258 | SUR_132_A30-Q258_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q265 | SUR_132_A30-Q265_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q266 | SUR_132_A30-Q266_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q267 | SUR_132_A30-Q267_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q268 | SUR_132_A30-Q268_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC002 | SUR_132_QC002_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC005 | SUR_132_QC005_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC021 | SUR_132_QC021_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC024 | SUR_132_QC024_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC045 | SUR_132_QC045_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC048 | SUR_132_QC048_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC050 | SUR_132_QC050_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC050 | SUR_132_QC050_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC050 | SUR_132_QC050_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC051 | SUR_132_QC051_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC059 | SUR_132_QC059_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC348 | SUR_132_QC348_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC007 | SUR_133_QC007_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC014 | SUR_133_QC014_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC052 | SUR_133_QC052_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC055 | SUR_133_QC055_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC056 | SUR_133_QC056_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC099 | SUR_133_QC099_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC354 | SUR_133_QC354_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC354 | SUR_133_QC354_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QCM39 | SUR_133_QCM39_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM116 | SUR_179_BM116_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM116 | SUR_179_BM116_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM031 | SUR_184_BM031_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM102 | SUR_184_BM102_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM078 | SUR_185_BM078_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM306 | SUR_185_BM306_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM379 | SUR_185_BM379_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM305 | SUR_186_BM305_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM035 | SUR_187_BM035_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM051 | SUR_187_BM051_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM301 | SUR_187_BM301_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM057 | SUR_188_BM057_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM303 | SUR_188_BM303_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM357 | SUR_188_BM357_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM063 | SUR_189_BM063_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM086 | SUR_189_BM086_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM304 | SUR_189_BM304_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM522 | SUR_189_BM522_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM050 | SUR_190_BM050_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM090 | SUR_190_BM090_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM310 | SUR_190_BM310_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM002 | SUR_191_BM002_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM129 | SUR_199_BM129_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM316 | SUR_199_BM316_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM329 | SUR_199_BM329_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM640 | SUR_199_BM640_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB188 | SUR_1_BB188_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB308 | SUR_1_BB308_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB310 | SUR_1_BB310_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM091 | SUR_200_BM091_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM838 | SUR_201_BM838_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM839 | SUR_201_BM839_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM335 | SUR_205_BM335_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM390 | SUR_205_BM390_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM781 | SUR_205_BM781_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM343 | SUR_206_BM343_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B176 | SUR_223_A41-B176_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB003 | SUR_2_BB003_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB004 | SUR_2_BB004_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB004 | SUR_2_BB004_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB011 | SUR_2_BB011_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB076 | SUR_2_BB076_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB076 | SUR_2_BB076_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB081 | SUR_2_BB081_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB081 | SUR_2_BB081_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB185 | SUR_2_BB185_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB378 | SUR_2_BB378_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB378 | SUR_2_BB378_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B004 | SUR_309_A43-B004_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B011 | SUR_309_A43-B011_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B237 | SUR_309_A43-B237_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B604 | SUR_309_A43-B604_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B811 | SUR_309_A43-B811_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM141 | SUR_329_BM141_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM380 | SUR_330_BM380_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM811 | SUR_330_BM811_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM831 | SUR_330_BM831_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM840 | SUR_330_BM840_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM018 | SUR_334_BM018_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB071 | SUR_4_BB071_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB075 | SUR_4_BB075_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB077 | SUR_4_BB077_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB077 | SUR_4_BB077_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB092 | SUR_4_BB092_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB109 | SUR_4_BB109_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB122 | SUR_4_BB122_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB304 | SUR_4_BB304_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB475 | SUR_4_BB475_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC005 | SUR_502_JC005_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC053 | SUR_502_JC053_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC101 | SUR_502_JC101_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC341 | SUR_502_JC341_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC006 | SUR_518_MC006_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC010 | SUR_518_MC010_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC068 | SUR_518_MC068_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC073 | SUR_518_MC073_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O006 | SUR_519_A33-O006_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC024 | SUR_519_MC024_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC028 | SUR_519_MC028_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC037 | SUR_519_MC037_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC054 | SUR_519_MC054_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC126 | SUR_519_MC126_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC301 | SUR_519_MC301_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC303 | SUR_519_MC303_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC017 | SUR_520_MC017_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC033 | SUR_520_MC033_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC051 | SUR_520_MC051_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC002 | SUR_521_MC002_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC005 | SUR_521_MC005_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC025 | SUR_521_MC025_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC066 | SUR_521_MC066_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC098 | SUR_521_MC098_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC147 | SUR_521_MC147_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC171 | SUR_521_MC171_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC333 | SUR_521_MC333_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC350 | SUR_521_MC350_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC039 | SUR_522_MC039_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC107 | SUR_522_MC107_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC307 | SUR_522_MC307_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC348 | SUR_522_MC348_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC093 | SUR_523_MC093_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC405 | SUR_524_MC405_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MN007 | SUR_526_MN007_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS010 | SUR_529_MS010_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS020 | SUR_529_MS020_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS025 | SUR_529_MS025_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS033 | SUR_529_MS033_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC316 | SUR_530_MC316_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC319 | SUR_530_MC319_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC036 | SUR_534_MC036_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC076 | SUR_534_MC076_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB058 | SUR_5_BB058_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB360 | SUR_5_BB360_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB389 | SUR_5_BB389_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A24-V007 | South_A24-V007_Mod_TA | Si |  | N/A |  | N/A
A24-V012 | South_A24-V012_Mod_TA | Si |  | N/A |  | N/A
A26-U035 | South_A26-U035_Mod_TA | Si |  | N/A | 2026-04-20 | N/A | 2026-04-21 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-22 |  | Joaquin Alejandro Luduena WX1488820
A26-Z019 | South_A26-Z019_Mod_TA | Si |  | N/A | 2026-04-20 | N/A | 2026-04-22 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-22 |  | Tomas Ezequiel Sanchez WX1486917
A27-U002 | South_A27-U002_Mod_TA | Si | 0.87 | N/A | 2026-05-19 | N/A | 2026-05-20 | David Encina WX1367993 |  | 2026-05-21 | 2026-05-28 | David Encina WX1367993
A27-U008 | South_A27-U008_Mod_TA | Si |  | N/A | 2026-06-04 | N/A | 2026-06-04 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-06-05 |  | Tomas Ezequiel Sanchez WX1486917
A27-U026 | South_A27-U026_Mod_TA | Si |  | N/A |  | N/A
A27-U089 | South_A27-U089_Mod_TA | Si |  | N/A |  | N/A
A28-Q078 | South_A28-Q078_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-13 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-05-21 | Luis Fernando Castro Ortega 00881502 | [5 empty] | 2026-05-29 | Yes
A28-Q160 | South_A28-Q160_Mod_TA | Si |  | N/A |  | N/A | 2026-03-12 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-06-05 | David Encina WX1367993
A28-R051 | South_A28-R051_Mod_TA | Si | 0.53 | N/A | 2026-04-14 | N/A | 2026-04-28 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-05-13 | Miguel Angel Garcia Martinez 00881238
A30-Q001 | South_A30-Q001_Mod_TA | Si | 1.53 | N/A |  | N/A | 2026-03-03 | zhaofeng 00917583 |  |  | 2026-03-11 | Abraham Jesus Salas Marfil 00237943 | RFI Ok
A30-Q003 | South_A30-Q003_Mod_TA | Si | 1.87 | N/A |  | N/A | 2025-09-09 | zhaofeng 00917583 |  |  | 2026-04-17 | Abraham Jesus Salas Marfil 00237943
A30-Q041 | South_A30-Q041_Mod_TA | Si | 1.2 | N/A | 2026-04-16 | N/A | 2026-04-30 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-05-13 | Arturo Gonzalo Antonio Cantu 00879903
A30-Q048 | South_A30-Q048_Mod_TA | Si | 0.53 | N/A | 2026-04-16 | N/A | 2026-04-30 | Arturo Gonzalo Antonio Cantu 00879903 |  |  | 2026-05-11 | Arturo Gonzalo Antonio Cantu 00879903
A30-Q076 | South_A30-Q076_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-03 | Elvia Carolina Cortes Garcia 00881509 |  |  | 2026-04-17 | Luis Fernando Castro Ortega 00881502 | RFI Ok |  |  |  |  | 2026-05-16 | Yes
A30-Q092 | South_A30-Q092_Mod_TA | Si | 1.2 | N/A |  | N/A | 2026-03-05 | Elvia Carolina Cortes Garcia 00881509 |  |  | 2026-03-06 | Luis Fernando Castro Ortega 00881502 | RFI Ok
A30-Q099 | South_A30-Q099_Mod_TA | Si | 1.53 | N/A |  | N/A | 2026-02-27 | Elvia Carolina Cortes Garcia 00881509 |  |  | 2026-03-13 | Luis Fernando Castro Ortega 00881502 | [5 empty] | 2026-05-28 | Yes
A30-R040 | South_A30-R040_Mod_TA | Si |  | N/A | 2026-04-16 | N/A | 2026-04-30 | Mario Andres Silva Martin 00866503 |  | 2026-04-20 |  | Mario Andres Silva Martin 00866503
A30-R109 | South_A30-R109_Mod_TA | Si |  | N/A | 2026-04-16 | N/A | 2026-04-21 | David Encina WX1367993 |  | 2026-04-20 | 2026-06-05 | David Encina WX1367993
A38-A110 | South_A38-A110_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-02-27 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-05 | Luis Fernando Castro Ortega 00881502 | RFI Ok
A38-B051 | South_A38-B051_Mod_TA | Si |  | N/A |  | N/A | 2026-03-17 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-17 | Luis Fernando Castro Ortega 00881502 | [5 empty] | 2026-05-16 | Yes
A38-B315 | South_A38-B315_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-02-17 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-19 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok
A38-B320 | South_A38-B320_Mod_TA | Si | 0.53 | N/A |  | N/A | 2026-03-19 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-25 | Arturo Gonzalo Antonio Cantu 00879903 | [5 empty] | 2026-04-29 | Yes
A38-B321 | South_A38-B321_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-03-12 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-17 | Joaquin Alejandro Luduena WX1488820 | RFI Ok
A38-B322 | South_A38-B322_Mod_TA | Si | 1.53 | N/A |  | N/A | 2026-02-17 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-10 | Luis Fernando Castro Ortega 00881502 | RFI Ok
A38-B323 | South_A38-B323_Mod_TA | Si | 0.87 | N/A |  | N/A | 2026-03-09 | Luis Fernando Castro Ortega 00881502 |  |  | 2026-03-10 | Luis Fernando Castro Ortega 00881502
A38-B326 | South_A38-B326_Mod_TA | Si | 0.53 | N/A | 2026-05-08 | N/A | 2026-05-08 | Miguel Angel Garcia Martinez 00881238 |  | 2026-05-07 | 2026-05-27 | Arturo Gonzalo Antonio Cantu 00879903 | 05/06/2026: Se actualizó el ML. La ingeniería esta aprobada.
A39-B047 | South_A39-B047_Mod_TA | Si | 0.53 | N/A | 2026-06-01 | N/A | 2026-06-01 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-06-02 | 2026-06-04 | Tomas Ezequiel Sanchez WX1486917
A40-B299 | South_A40-B299_Mod_TA | Si |  | N/A |  | N/A
A40-B300 | South_A40-B300_Mod_TA | Si |  | N/A |  | N/A
A41-A005 | South_A41-A005_Mod_TA | Si |  | N/A |  | N/A
A41-A006 | South_A41-A006_Mod_TA | Si |  | N/A |  | N/A
A41-A037 | South_A41-A037_Mod_TA | Si |  | N/A |  | N/A | 2026-04-06 | Joaquin Alejandro Luduena WX1488820 |  |  | 2026-04-28 | Joaquin Alejandro Luduena WX1488820
A41-A467 | South_A41-A467_Mod_TA | Si |  | N/A | 2026-04-16 | N/A | 2026-05-08 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-20 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-A595 | South_A41-A595_Mod_TA | Si |  | N/A | 2026-04-16 | N/A | 2026-05-01 | Mario Andres Silva Martin 00866503 |  | 2026-04-20 |  | Mario Andres Silva Martin 00866503
A41-A649 | South_A41-A649_Mod_TA | Si |  | N/A |  | N/A
A41-A652 | South_A41-A652_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-05-07 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-21 |  | GSC
A41-A653 | South_A41-A653_Mod_TA | Si |  | N/A |  | N/A | 2026-06-05 | GSC
A41-B015 | South_A41-B015_Mod_TA | Si |  | N/A |  | N/A
A41-B018 | South_A41-B018_Mod_TA | Si |  | N/A |  | N/A
A41-B022 | South_A41-B022_Mod_TA | Si |  | N/A | 2026-05-12 | N/A | 2026-06-03 | Miguel Angel Garcia Martinez 00881238
A41-B023 | South_A41-B023_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-05-06 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-21 | 2026-05-12 | Arturo Gonzalo Antonio Cantu 00879903
A41-B025 | South_A41-B025_Mod_TA | Si |  | N/A |  | N/A
A41-B028 | South_A41-B028_Mod_TA | Si |  | N/A | 2026-04-20 | N/A | 2026-04-21 | David Encina WX1367993 |  | 2026-04-22 |  | David Encina WX1367993
A41-B033 | South_A41-B033_Mod_TA | Si |  | N/A | 2026-04-16 | N/A | 2026-05-11 | GSC
A41-B041 | South_A41-B041_Mod_TA | Si |  | N/A | 2026-04-20 | N/A | 2026-04-23 | David Encina WX1367993 |  | 2026-04-22 |  | David Encina WX1367993
A41-B266 | South_A41-B266_Mod_TA | Si |  | N/A | 2026-04-27 | N/A | 2026-05-05 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-29 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-B268 | South_A41-B268_Mod_TA | Si |  | N/A |  | N/A
A41-B269 | South_A41-B269_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-05-11 | GSC |  | 2026-04-21 |  | GSC
A41-B270 | South_A41-B270_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-05-08 | GSC |  | 2026-04-21 |  | GSC
A41-B272 | South_A41-B272_Mod_TA | Si |  | N/A |  | N/A
A41-B274 | South_A41-B274_Mod_TA | Si |  | N/A | 2026-05-07 | N/A | 2026-05-12 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-05-11 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-B275 | South_A41-B275_Mod_TA | Si |  | N/A | 2026-04-27 | N/A | 2026-05-08 | GSC |  | 2026-04-29 |  | GSC
A41-B276 | South_A41-B276_Mod_TA | Si |  | N/A | 2026-04-15 | N/A | 2026-04-15 | David Encina WX1367993 |  |  | 2026-04-29 | David Encina WX1367993
A41-B277 | South_A41-B277_Mod_TA | Si |  | N/A |  | N/A
A41-B278 | South_A41-B278_Mod_TA | Si |  | N/A |  | N/A
A41-B282 | South_A41-B282_Mod_TA | Si |  | N/A | 2026-05-08 | N/A | 2026-05-12 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-05-12 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-B291 | South_A41-B291_Mod_TA | Si |  | N/A | 2026-05-15 | N/A | 2026-05-15 | Joaquin Alejandro Luduena WX1488820
A41-B292 | South_A41-B292_Mod_TA | Si |  | N/A |  | N/A
A41-B295 | South_A41-B295_Mod_TA | Si |  | N/A |  | N/A
A41-B298 | South_A41-B298_Mod_TA | Si |  | N/A |  | N/A
A41-B389 | South_A41-B389_Mod_TA | Si |  | N/A |  | N/A
A41-B411 | South_A41-B411_Mod_TA | Si |  | N/A |  | N/A
A41-B436 | South_A41-B436_Mod_TA | Si |  | N/A | 2026-05-14 | N/A | 2026-06-02 | GSC |  | 2026-05-18
A41-B438 | South_A41-B438_Mod_TA | Si |  | N/A |  | N/A
A41-B439 | South_A41-B439_Mod_TA | Si |  | N/A | 2026-05-07 | N/A | 2026-05-12 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-05-11 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-B445 | South_A41-B445_Mod_TA | Si |  | N/A | 2026-04-16 | N/A | 2026-05-13 | GSC |  |  |  | GSC
A41-B455 | South_A41-B455_Mod_TA | Si |  | N/A | 2026-05-20 | N/A | 2026-05-20 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-21 |  | Tomas Ezequiel Sanchez WX1486917
A41-B464 | South_A41-B464_Mod_TA | Si |  | N/A |  | N/A
A41-B475 | South_A41-B475_Mod_TA | Si |  | N/A | 2026-05-21 | N/A | 2026-05-22 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-25 |  | Tomas Ezequiel Sanchez WX1486917
A41-B518 | South_A41-B518_Mod_TA | Si |  | N/A | 2026-05-18 | N/A | 2026-05-18 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-19 |  | Joaquin Alejandro Luduena WX1488820
A41-B541 | South_A41-B541_Mod_TA | Si |  | N/A | 2026-05-20 | N/A | 2026-05-20 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-22 |  | Joaquin Alejandro Luduena WX1488820
A41-B571 | South_A41-B571_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-05-05 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-21 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-B574 | South_A41-B574_Mod_TA | Si |  | N/A | 2026-05-27 | N/A | 2026-05-26 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-28 |  | Tomas Ezequiel Sanchez WX1486917
A41-B577 | South_A41-B577_Mod_TA | Si |  | N/A |  | N/A
A41-B577 | South_A41-B577_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B591 | South_A41-B591_Mod_TA | Si |  | N/A |  | N/A
A41-B594 | South_A41-B594_Mod_TA | Si |  | N/A |  | N/A
A41-B595 | South_A41-B595_Mod_TA | Si |  | N/A |  | N/A
A41-B623 | South_A41-B623_Mod_TA | Si |  | N/A | 2026-04-28 | N/A | 2026-05-08 | GSC
A41-B644 | South_A41-B644_Mod_TA | Si |  | N/A |  | N/A
A41-B795 | South_A41-B795_Mod_TA | Si |  | N/A | 2026-05-08 | N/A |  | GSC
A41-B814 | South_A41-B814_Mod_TA | Si |  | N/A | 2026-05-12 | N/A | 2026-06-03 | Miguel Angel Garcia Martinez 00881238
A41-B833 | South_A41-B833_Mod_TA | Si |  | N/A |  | N/A
A41-B834 | South_A41-B834_Mod_TA | Si |  | N/A |  | N/A
A41-B873 | South_A41-B873_Mod_TA | Si |  | N/A |  | N/A
A41-B876 | South_A41-B876_Mod_TA | Si |  | N/A |  | N/A
A41-B909 | South_A41-B909_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-05-08 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2026-04-21 |  | Arturo Gonzalo Antonio Cantu 00879903
A41-B910 | South_A41-B910_Mod_TA | Si |  | N/A | 2026-04-17 | N/A | 2026-04-24 | David Encina WX1367993 |  | 2026-04-21 | 2026-05-06 | David Encina WX1367993
A41-B916 | South_A41-B916_Mod_TA | Si |  | N/A | 2026-05-18 | N/A | 2026-05-19 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-20 |  | Joaquin Alejandro Luduena WX1488820
A41-B935 | South_A41-B935_Mod_TA | Si |  | N/A |  | N/A
A41-B938 | South_A41-B938_Mod_TA | Si |  | N/A | 2026-04-27 | N/A |  | GSC |  | 2026-04-29 |  | GSC
A41-B958 | South_A41-B958_Mod_TA | Si |  | N/A |  | N/A
A41-B958 | South_A41-B958_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B237 | South_A43-B237_Mod_TA | Si |  | N/A |  | N/A
BA003 | South_BA003_Swap_MVS | Si
BA007 | South_BA007_Swap_MVS | Si
BA009 | South_BA009_Swap_MVS | Si |  | 2026-06-01 | 2026-06-01 | 2026-06-05 | 2026-06-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-06-02
BA011 | South_BA011_Swap_MVS | Si |  |  | 2026-05-28 | 2026-06-04 | 2026-06-04 | David Encina WX1367993 |  | 2026-06-01 |  | David Encina WX1367993
BA013 | South_BA013_Swap_MVS | Si
BA016 | South_BA016_Swap_MVS | Si
BA022 | South_BA022_Swap_MVS | Si |  |  | 2026-06-01 | 2026-05-29 | 2026-05-29 | Joaquin Alejandro Luduena WX1488820 |  | 2026-06-02 | 2026-06-09 | Joaquin Alejandro Luduena WX1488820
BA023 | South_BA023_Swap_MVS | Si
BA025 | South_BA025_Swap_MVS | Si |  | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-05-25 | Miguel Angel Garcia Martinez 00881238 |  | 2026-05-27 | 2026-06-05 | Miguel Angel Garcia Martinez 00881238
BA027 | South_BA027_Swap_MVS | Si |  | 2026-03-25 | 2026-03-26 | 2026-03-30 | 2026-03-30 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-27 | 2026-04-28 | Miguel Angel Garcia Martinez 00881238
BA030 | South_BA030_Swap_MVS | Si |  |  |  | 2026-05-26 | 2026-05-26 | Joaquin Alejandro Luduena WX1488820 |  |  | 2026-06-05 | Joaquin Alejandro Luduena WX1488820
BA032 | South_BA032_Swap_MVS | Si |  | 2026-05-26 | 2026-05-27 | 2026-05-26 | 2026-05-26 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-28 | 2026-06-05 | Joaquin Alejandro Luduena WX1488820
BA038 | South_BA038_Swap_MVS | Si
BA039 | South_BA039_Swap_MVS | Si
BA040 | South_BA040_Swap_MVS | Si |  | 2026-03-25 | 2026-03-26 | 2026-03-30 | 2026-03-30 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-27 | 2026-06-05 | Miguel Angel Garcia Martinez 00881238
BA041 | South_BA041_Swap_MVS | Si |  | 2026-05-26 | 2026-05-27 | 2026-05-26 | 2026-05-26 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-05-28 | 2026-06-03 | Tomas Ezequiel Sanchez WX1486917
BA043 | South_BA043_Swap_MVS | Si |  | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-04-01 | 2026-03-31 | Tomas Ezequiel Sanchez WX1486917
BA048 | South_BA048_Swap_MVS | Si
BA053 | South_BA053_Swap_MVS | Si |  | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-16 | David Encina WX1367993 |  |  | 2026-05-04 | David Encina WX1367993
BA056 | South_BA056_Swap_MVS | Si |  | 2026-04-14 | 2026-04-15 | 2026-04-20 | 2026-04-20 | David Encina WX1367993 |  |  | 2026-04-22 | David Encina WX1367993
BA075 | South_BA075_Swap_MVS | Si |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | Miguel Angel Garcia Martinez 00881238 |  | 2026-06-02 | 2026-06-04 | Miguel Angel Garcia Martinez 00881238
BA431 | South_BA431_Swap_MVS | Si |  | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | GSC |  | 2026-06-02
BA700 | South_BA700_Swap_MVS | Si
BB070 | South_BB070_Swap_MVS | Si
BB103 | South_BB103_Swap_MVS | Si | 0.87 |  |  | 2025-12-05 | 2025-12-05 | zhaofeng 00917583 |  |  | 2026-01-02 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok Aprobado por Nico Trubbo el 02/01/2026. |  | 2026-02-11 | Tomas Ezequiel Sanchez WX1486917
BB188 | South_BB188_Swap_MVS | Si
BB307 | South_BB307_Swap_MVS | Si | 1.2 | 2025-11-10 | 2025-11-11 | 2026-02-05 | 2026-02-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-12 | 2026-03-23 | Miguel Angel Garcia Martinez 00881238 | En stock. CIS Group 06/02/2026: Aprobada por Pablo Buono. |  | 2026-03-11 | Joaquin Alejandro Luduena WX1488820 | [9 empty] | Survey Pending
BB308 | South_BB308_Swap_MVS | Si | 1.2 |  |  | 2025-11-15 | 2025-11-15 | zhaofeng 00917583 |  |  | 2025-11-25 | zhaofeng 00917583 | RFI Ok | [12 empty] | Ready for Dismantle
BC013 | South_BC013_Swap_MVS | Si
BC014 | South_BC014_Swap_MVS | Si
BC018 | South_BC018_Swap_MVS | Si
BC028 | South_BC028_Swap_MVS | Si
BC035 | South_BC035_Swap_MVS | Si
BC042 | South_BC042_Swap_MVS | Si |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | 2026-01-08 | Agustin Maria Bianchetti 00958351 |  | 2025-08-12 | 2026-01-09 | Agustin Maria Bianchetti 00958351
BC047 | South_BC047_Swap_MVS | Si
BC052 | South_BC052_Swap_MVS | Si
BC053 | South_BC053_Swap_MVS | Si
BC059 | South_BC059_Swap_MVS | Si
BC062 | South_BC062_Swap_MVS | Si
BC065 | South_BC065_Swap_MVS | Si
BC069 | South_BC069_Swap_MVS | Si
BC070 | South_BC070_Swap_MVS | Si
BC081 | South_BC081_Swap_MVS | Si
BC082 | South_BC082_Swap_MVS | Si
BC084 | South_BC084_Swap_MVS | Si
BC088 | South_BC088_Swap_MVS | Si
BC089 | South_BC089_Swap_MVS | Si
BC091 | South_BC091_Swap_MVS | Si
BC099 | South_BC099_Swap_MVS | Si
BC100 | South_BC100_Swap_MVS | Si
BC102 | South_BC102_Swap_MVS | Si
BC109 | South_BC109_Swap_MVS | Si
BC117 | South_BC117_Swap_MVS | Si
BC122 | South_BC122_Swap_MVS | Si
BC125 | South_BC125_Swap_MVS | Si
BC127 | South_BC127_Swap_MVS | Si
BC151 | South_BC151_Swap_MVS | Si
BC301 | South_BC301_Swap_MVS | Si
BC303 | South_BC303_Swap_MVS | Si
BC304 | South_BC304_Swap_MVS | Si
BC306 | South_BC306_Swap_MVS | Si
BC310 | South_BC310_Swap_MVS | Si
BC311 | South_BC311_Swap_MVS | Si
BC317 | South_BC317_Swap_MVS | Si
BC318 | South_BC318_Swap_MVS | Si
BC326 | South_BC326_Swap_MVS | Si
BC327 | South_BC327_Swap_MVS | Si
BC328 | South_BC328_Swap_MVS | Si
BC329 | South_BC329_Swap_MVS | Si
BC340 | South_BC340_Swap_MVS | Si
BC341 | South_BC341_Swap_MVS | Si
BC342 | South_BC342_Swap_MVS | Si
BC350 | South_BC350_Swap_MVS | Si
BC385 | South_BC385_Swap_MVS | Si
BC391 | South_BC391_Swap_MVS | Si
BC392 | South_BC392_Swap_MVS | Si
BC398 | South_BC398_Swap_MVS | Si
BC399 | South_BC399_Swap_MVS | Si
BC401 | South_BC401_Swap_MVS | Si
BC423 | South_BC423_Swap_MVS | Si
BC700 | South_BC700_Swap_MVS | Si
BC701 | South_BC701_Swap_MVS | Si | [7 empty] | 2026-01-20 | 2026-01-20 | Daniel Horacio Rocabado WX1372513
BC711 | South_BC711_Swap_MVS | Si
BC742 | South_BC742_Swap_MVS | Si
BC758 | South_BC758_Swap_MVS | Si |  | 2026-06-08 | 2026-06-08 | 2026-06-07 | 2026-06-08 | GSC |  | 2026-06-09
BH001 | South_BH001_Swap_MVS | Si | 1.53 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-09 | David Encina WX1367993 |  | 2026-04-13 | 2026-04-20 | David Encina WX1367993 | [13 empty] | Survey Pending
BH003 | South_BH003_Swap_MVS | Si | [17 empty] | Subrack Installed by ICS/El desmonte va por parte de la contratista que realiza el SWAP. | Etapa 01 | 11 | CHSINS05-01 pos 02 | Sala TX02, 1er Piso | 16 | SubRack Installed
BH004 | South_BH004_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BH006 | South_BH006_Swap_MVS | Si | 1.2 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | David Encina WX1367993 |  |  | 2026-04-01 | David Encina WX1367993 | [9 empty] | 04 | N/A | Sala TX, 1er Piso | 00 | Survey Done
BH026 | South_BH026_Swap_MVS | Si
BH040 | South_BH040_Swap_MVS | Si | 1.53 | 2026-04-07 | 2026-04-08 | 2026-04-10 | 2026-04-10 | Tomas Ezequiel Sanchez WX1486917 | Design to be made with historical records received 2026-04-06 | 2026-04-09 | 2026-04-13 | Tomas Ezequiel Sanchez WX1486917
BH043 | South_BH043_Swap_MVS | Si | 1.53 | 2026-04-09 | 2026-04-10 | 2026-04-29 | 2026-04-29 | David Encina WX1367993 |  |  | 2026-04-30 | David Encina WX1367993 | [8 empty] | Etapa 01 |  |  |  |  | Survey Done
BH045 | South_BH045_Swap_MVS | Si | [18 empty] | Etapa 01 | 97 | DLRINS05-01 pos 01 | Sala de TX, 2do piso | 16 | SubRack Installed
BH054 | South_BH054_Swap_MVS | Si | 1.53 |  |  | 2026-03-31 | 2026-03-31 | David Encina WX1367993 |  |  | 2026-04-01 | David Encina WX1367993
BH059 | South_BH059_Swap_MVS | Si |  |  | 2026-05-21 | 2026-05-26 | 2026-05-26 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-25 | 2026-06-05 | Joaquin Alejandro Luduena WX1488820
BH065 | South_BH065_Swap_MVS | Si | 1.2 |  |  | 2026-06-01 | 2026-06-01 | Joaquin Alejandro Luduena WX1488820 |  |  |  | Joaquin Alejandro Luduena WX1488820
BH073 | South_BH073_Swap_MVS | Si | 1.53 | 2026-03-23 | 2026-03-24 | 2026-03-30 | 2026-03-30 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-25 | 2026-04-01 | Miguel Angel Garcia Martinez 00881238
BH076 | South_BH076_Swap_MVS | Si |  | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-05-25 | Miguel Angel Garcia Martinez 00881238 |  | 2026-05-27 | 2026-06-05 | Miguel Angel Garcia Martinez 00881238
BH081 | South_BH081_Swap_MVS | Si | [18 empty] | Etapa 01 | 11 | CHSINS05-01 pos 01 | Sala TX02, 1er Piso | 16 | Ready for Dismantle
BH082 | South_BH082_Swap_MVS | Si |  |  |  | 2025-10-22 | 2025-10-22 | David Encina WX1367993 |  | 2025-10-24 | 2025-12-09 | David Encina WX1367993
BH086 | South_BH086_Swap_MVS | Si
BH100 | South_BH100_Swap_MVS | Si
BH105 | South_BH105_Swap_MVS | Si |  | 2026-06-02 | 2026-06-03 | 2026-06-03 | 2026-06-03 | GSC |  | 2026-06-04
BH107 | South_BH107_Swap_MVS | Si
BH189 | South_BH189_Swap_MVS | Si |  | 2026-06-01 | 2026-06-01 | 2026-06-02 | 2026-06-02 | Miguel Angel Garcia Martinez 00881238 |  | 2026-06-02
BH309 | South_BH309_Swap_MVS | Si | [17 empty] | Only install Subrack and GPS by CYAC | Etapa 01 | 05 | LOLINS05-01 pos 01 | Sala TX, P.B. | 11 | SubRack Installed
BH750 | South_BH750_Swap_MVS | Si | 0.87 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-04-07 | David Encina WX1367993 | Design to be made with historical records received 2026-04-06 |  | 2026-04-09 | David Encina WX1367993
BH761 | South_BH761_Swap_MVS | Si
BL001 | South_BL001_Swap_MVS | Si | 1.53 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-05 | Arturo Gonzalo Antonio Cantu 00879903(GSC) |  |  | 2026-05-14 | Miguel Angel Garcia Martinez 00881238
BL006 | South_BL006_Swap_MVS | Si
BL009 | South_BL009_Swap_MVS | Si
BL011 | South_BL011_Swap_MVS | Si
BL012 | South_BL012_Swap_MVS | Si
BL020 | South_BL020_Swap_MVS | Si
BL023 | South_BL023_Swap_MVS | Si | 1.2 | 2026-03-30 | 2026-03-31 | 2026-04-10 | 2026-04-10 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-01 | 2026-04-14 | Joaquin Alejandro Luduena WX1488820 | [8 empty] | Etapa 01 |  |  |  |  | Survey Pending
BL031 | South_BL031_Swap_MVS | Si
BL076 | South_BL076_Swap_MVS | Si
BL323 | South_BL323_Swap_MVS | Si | 1.53 | 2026-04-01 | 2026-04-01 | 2026-04-09 | 2026-04-09 | Joaquin Alejandro Luduena WX1488820 |  | 2026-04-07 | 2026-04-15 | Joaquin Alejandro Luduena WX1488820 | [13 empty] | N/A
BM003 | South_BM003_Swap_MVS | Si | [23 empty] | Dismantled
BM020 | South_BM020_Swap_MVS | Si
BM050 | South_BM050_Swap_MVS | Si
BM059 | South_BM059_Swap_MVS | Si
BM087 | South_BM087_Swap_MVS | Si |  | 2025-10-01 | 2025-10-02 | 2025-09-30 | 2025-09-30 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-10-03 | 2025-11-18 | Arturo Gonzalo Antonio Cantu 00879903 | Aprobado por Nico Trubbo (18/11/2025)
BM231 | South_BM231_Swap_MVS | Si
BM307 | South_BM307_Swap_MVS | Si | [23 empty] | Dismantled
BM314 | South_BM314_Swap_MVS | Si | [23 empty] | PPI Approved
BM320 | South_BM320_Swap_MVS | Si
BM350 | South_BM350_Swap_MVS | Si | [8 empty] | 2025-09-01 | Arturo Gonzalo Antonio Cantu 00879903 | [13 empty] | Dismantled
BM359 | South_BM359_Swap_MVS | Si
BM360 | South_BM360_Swap_MVS | Si
BM369 | South_BM369_Swap_MVS | Si
BM376 | South_BM376_Swap_MVS | Si
BM397 | South_BM397_Swap_MVS | Si
BM401 | South_BM401_Swap_MVS | Si |  | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2026-05-21 | Joaquin Alejandro Luduena WX1488820 |  | 2026-05-22 | 2026-05-21 | Joaquin Alejandro Luduena WX1488820
BM404 | South_BM404_Swap_MVS | Si |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Joaquin Alejandro Luduena WX1488820 |  | 2026-06-09 |  | Joaquin Alejandro Luduena WX1488820
BM408 | South_BM408_Swap_MVS | Si | [18 empty] | Etapa 02 | 98 | SCMINS05-01 pos 01 | Sala TX, P.B. | 21 | Dismantled
BM424 | South_BM424_Swap_MVS | Si | [8 empty] | 2024-10-03 | Arturo Gonzalo Antonio Cantu 00879903 | [8 empty] | Etapa 01 |  |  |  |  | Swapped
BM507 | South_BM507_Swap_MVS | Si | [18 empty] | Etapa 02 | 98 | SCMINS05-01 pos 02 | Sala TX, P.B. | 21 | Dismantled
BM508 | South_BM508_Swap_MVS | Si | [18 empty] | Etapa 01 | 98 | SCMINS05-01 pos 03 | Sala TX, P.B. | 21 | Dismantled
BM509 | South_BM509_Swap_MVS | Si | [23 empty] | Dismantled
BM519 | South_BM519_Swap_MVS | Si | [18 empty] | Etapa 01 | 03 | LJTINS05-01 pos 01 | Sala TX, 1er Piso | 05 | Dismantled
BM527 | South_BM527_Swap_MVS | Si | [23 empty] | Ready for Dismantle
BM589 | South_BM589_Swap_MVS | Si |  | 2025-09-02 | 2025-09-03 | 2025-12-04 | 2025-12-04 | Miguel Angel Garcia Martinez 00881238 |  | 2025-09-04 | 2025-12-30 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM590 | South_BM590_Swap_MVS | Si
BM618 | South_BM618_Swap_MVS | Si
BM647 | South_BM647_Swap_MVS | Si |  | 2025-09-02 | 2025-09-03 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-09-04 | 2025-12-30 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM668 | South_BM668_Swap_MVS | Si |  | 2025-08-25 | 2025-08-26 | 2025-11-19 | 2025-11-19 | Miguel Angel Garcia Martinez 00881238 |  | 2025-08-27 | 2026-02-20 | Miguel Angel Garcia Martinez 00881238 | Aprobado por Nico Trubbo el 09/12/2025. R01 aprobada por Pablo Buono el 20/02/2026. | [12 empty] | Survey Pending
BM671 | South_BM671_Swap_MVS | Si |  | 2025-08-25 | 2025-08-26 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-08-27 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM672 | South_BM672_Swap_MVS | Si |  | 2025-08-25 | 2025-08-26 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-08-27 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238 | 02/01/2026: Aprobada R00 19/02/2026: Aprobada por Pablo Buono con modificaciones. | [12 empty] | PPI Approved
BM673 | South_BM673_Swap_MVS | Si |  | 2025-08-26 | 2025-08-27 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-08-28 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM674 | South_BM674_Swap_MVS | Si |  | 2025-08-25 | 2025-08-26 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-08-27 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM675 | South_BM675_Swap_MVS | Si |  | 2025-08-26 | 2025-08-27 | 2025-12-03 | 2025-12-03 | Miguel Angel Garcia Martinez 00881238 |  | 2025-08-28 | 2026-01-02 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM704 | South_BM704_Swap_MVS | Si
BM755 | South_BM755_Swap_MVS | Si |  | 2025-09-02 | 2025-09-03 | 2025-12-05 | 2025-12-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-09-04 | 2026-01-07 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
BM756 | South_BM756_Swap_MVS | Si |  | 2025-09-02 | 2025-09-03 | 2025-12-05 | 2025-12-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-09-04 | 2026-01-07 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Survey Pending
BM758 | South_BM758_Swap_MVS | Si |  | 2025-09-02 | 2025-09-03 | 2025-12-05 | 2025-12-05 | Miguel Angel Garcia Martinez 00881238 |  | 2025-09-04 | 2026-01-07 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | ML
BM770 | South_BM770_Swap_MVS | Si | [18 empty] | Etapa 01 | 06 | SDPISN05-01 pos 01 | Sala TX, P.B. | 21 | Dismantled
BM808 | South_BM808_Swap_MVS | Si | [18 empty] | Etapa 01 | 05 | MRMINS05-01 pos 04 | Sala TX, 2do Piso | 11 | Dismantled
BN190 | South_BN190_Swap_MVS | Si
BN200 | South_BN200_Swap_MVS | Si |  | 2025-11-03 | 2025-11-04 | 2025-11-10 | 2025-11-10 | Miguel Angel Garcia Martinez 00881238 |  | 2025-11-05 | 2025-12-22 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | Survey Pending
BN207 | South_BN207_Swap_MVS | Si |  | 2025-10-20 | 2025-11-03 | 2026-01-06 | 2026-01-06 | David Encina WX1367993 |  | 2025-11-04 | 2026-06-02 | David Encina WX1367993
BN223 | South_BN223_Swap_MVS | Si
BN892 | South_BN892_Swap_MVS | Si |  | 2026-01-21 | 2026-01-22 | 2026-02-05 | 2026-02-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-01-23 | 2026-04-28 | Miguel Angel Garcia Martinez 00881238
BN897 | South_BN897_Swap_MVS | Si
BO316 | South_BO316_Swap_MVS | Si
BT004 | South_BT004_Swap_MVS | Si
BT005 | South_BT005_Swap_MVS | Si
BT012 | South_BT012_Swap_MVS | Si
BT013 | South_BT013_Swap_MVS | Si
BT020 | South_BT020_Swap_MVS | Si
BT021 | South_BT021_Swap_MVS | Si | 0.87 | 2026-04-07 | 2026-04-08 | 2026-04-20 | 2026-04-20 | Tomas Ezequiel Sanchez WX1486917 | Design to be made with historical records received 2026-04-06 | 2026-04-10 | 2026-04-24 | Tomas Ezequiel Sanchez WX1486917
BT022 | South_BT022_Swap_MVS | Si
BT023 | South_BT023_Swap_MVS | Si
BT025 | South_BT025_Swap_MVS | Si
BT032 | South_BT032_Swap_MVS | Si
BT033 | South_BT033_Swap_MVS | Si
BT034 | South_BT034_Swap_MVS | Si
BT036 | South_BT036_Swap_MVS | Si
BT037 | South_BT037_Swap_MVS | Si
BT042 | South_BT042_Swap_MVS | Si | 1.53 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-03-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-06 | 2026-03-16 | Miguel Angel Garcia Martinez 00881238
BT043 | South_BT043_Swap_MVS | Si | 1.87 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-03-05 | Miguel Angel Garcia Martinez 00881238 |  | 2026-03-06 | 2026-03-16 | Miguel Angel Garcia Martinez 00881238
BT045 | South_BT045_Swap_MVS | Si
BT046 | South_BT046_Swap_MVS | Si
BT111 | South_BT111_Swap_MVS | Si
BT714 | South_BT714_Swap_MVS | Si
LP036 | South_LP036_Swap_MVS | Si | 1.87 |  |  | 2025-07-07 | 2025-07-07 | zhaofeng 00917583 |  |  | 2025-07-15 | Arturo Gonzalo Antonio Cantu 00879903 | RFI Ok
LP055 | South_LP055_Swap_MVS | Si
LP075 | South_LP075_Swap_MVS | Si |  | 2025-06-05 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Arturo Gonzalo Antonio Cantu 00879903 |  | 2025-06-16 | 2026-03-13 | Miguel Angel Garcia Martinez 00881238 | [13 empty] | PPI Approved
LP112 | South_LP112_Swap_MVS | Si
QC023 | South_QC023_Swap_MVS | Si | [23 empty] | Ready for Dismantle
QC056 | South_QC056_Swap_MVS | Si | [23 empty] | Ready for Dismantle
QC076 | South_QC076_Swap_MVS | Si | [8 empty] | 2025-06-25 | Abraham Jesus Salas Marfil 00237943 | [13 empty] | Ready for Dismantle
QC354 | South_QC354_Swap_MVS | Si | [23 empty] | Ready for Dismantle
QW038 | South_QW038_Swap_MVS | Si
SS082 | South_SS082_Swap_MVS | Si
IC022 | TF_IC022_Swap_MVS | Si
IC025 | TF_IC025_Swap_MVS | Si
| 2026W17-AMBA-Benefits-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-AMBA-Celltrex-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-AMBA-Constel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-AMBA-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-AMBA-Esmetic-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-AMBA-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-AMBA-Terabyte-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-MEDI-Celltrex-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W17-MEDI-Ersatel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Benefits-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Celltrex-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Cis-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Constel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Esmetic-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Interoptics-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-AMBA-Terabyte-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-MEDI-Celltrex-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-MEDI-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-MEDI-Ersatel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-MEDI-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-South-Cis-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-South-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W18-South-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W20-AMBA-Constel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W20-AMBA-Terabyte-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W20-MEDI-Cis-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W20-MEDI-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W20-South-Cis-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Celltrex-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Cis-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Constel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Esmetic-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-ICS-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Terabyte-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-AMBA-Tg2-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-MEDI-Celltrex-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-MEDI-Ersatel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-MEDI-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-South-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W21-South-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W22-AMBA-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W22-AMBA-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W22-MEDI-Cyac-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W22-MEDI-Ersatel-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W22-MEDI-L2g-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2026W22-South-Cis-Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS195 | AMBA_101_KS195_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN249 | AMBA_107_KN249_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN287 | AMBA_107_KN287_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN318 | AMBA_107_KN318_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN085 | AMBA_108_KN085_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN222 | AMBA_108_KN222_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN222 | AMBA_108_KN222_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN253 | AMBA_108_KN253_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN296 | AMBA_108_KN296_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN313 | AMBA_108_KN313_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN322 | AMBA_108_KN322_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO055 | AMBA_111_KO055_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO207 | AMBA_111_KO207_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN242 | AMBA_126_KN242_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KN251 | AMBA_127_KN251_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN210 | AMBA_129_CN210_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN252 | AMBA_144_CN252_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN172 | AMBA_146_CN172_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN236 | AMBA_146_CN236_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN810 | AMBA_147_CN810_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CU004 | AMBA_169_CU004_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS023 | AMBA_175_KS023_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS374 | AMBA_175_KS374_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS008 | AMBA_176_KS008_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS108 | AMBA_176_KS108_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS631 | AMBA_176_KS631_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS631 | AMBA_176_KS631_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS632 | AMBA_176_KS632_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS632 | AMBA_176_KS632_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS633 | AMBA_176_KS633_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS009 | AMBA_177_KS009_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS634 | AMBA_177_KS634_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS634 | AMBA_177_KS634_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS644 | AMBA_177_KS644_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS908 | AMBA_177_KS908_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS908 | AMBA_177_KS908_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS174 | AMBA_179_KS174_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS624 | AMBA_182_KS624_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS628 | AMBA_182_KS628_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS629 | AMBA_182_KS629_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS147 | AMBA_183_KS147_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS642 | AMBA_183_KS642_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS701 | AMBA_183_KS701_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS701 | AMBA_183_KS701_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS105 | AMBA_184_KS105_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS105 | AMBA_184_KS105_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS635 | AMBA_184_KS635_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS637 | AMBA_184_KS637_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS639 | AMBA_184_KS639_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS446 | AMBA_185_KS446_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS626 | AMBA_185_KS626_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS627 | AMBA_185_KS627_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS630 | AMBA_185_KS630_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS125 | AMBA_186_BS125_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS210 | AMBA_186_BS210_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS097 | AMBA_188_BS097_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS107 | AMBA_189_KS107_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS306 | AMBA_189_KS306_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS432 | AMBA_189_KS432_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS711 | AMBA_189_KS711_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS063 | AMBA_190_KS063_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS364 | AMBA_190_KS364_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS067 | AMBA_191_KS067_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS151 | AMBA_191_KS151_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS494 | AMBA_191_KS494_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS238 | AMBA_192_BS238_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS065 | AMBA_193_BS065_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS105 | AMBA_193_BS105_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS124 | AMBA_193_BS124_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS352 | AMBA_193_BS352_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS227 | AMBA_194_BS227_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS378 | AMBA_195_KS378_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS378 | AMBA_195_KS378_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS702 | AMBA_195_KS702_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS702 | AMBA_195_KS702_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS707 | AMBA_195_KS707_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS111 | AMBA_196_KS111_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS201 | AMBA_196_KS201_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS201 | AMBA_196_KS201_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS050 | AMBA_197_BS050_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS088 | AMBA_197_BS088_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS246 | AMBA_197_BS246_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS246 | AMBA_197_BS246_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS314 | AMBA_197_BS314_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS087 | AMBA_198_BS087_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS087 | AMBA_198_BS087_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS140 | AMBA_198_BS140_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS302 | AMBA_198_BS302_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS302 | AMBA_198_BS302_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS037 | AMBA_226_KS037_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS622 | AMBA_249_KS622_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS623 | AMBA_249_KS623_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS213 | AMBA_80_BS213_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KO044 | AMBA_86_KO044_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS200 | AMBA_90_KS200_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS334 | AMBA_91_KS334_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS142 | AMBA_96_KS142_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B059 | AMBA_A38-B059_Mod_TA | Si |  | N/A |  | N/A
A38-B318 | AMBA_A38-B318_Mod_TA | Si |  | N/A | 2026-05-26 | N/A | 2026-05-28 | David Encina WX1367993 |  | 2026-05-27 | 2026-06-01 | David Encina WX1367993
A41-A688 | AMBA_A41-A688_Mod_TA | Si |  | N/A |  | N/A
A41-B034 | AMBA_A41-B034_Mod_TA | Si |  | N/A |  | N/A
A41-B258 | AMBA_A41-B258_Mod_TA | Si |  | N/A |  | N/A
A41-B259 | AMBA_A41-B259_Mod_TA | Si |  | N/A |  | N/A
A41-B265 | AMBA_A41-B265_Mod_TA | Si |  | N/A |  | N/A
BB051 | AMBA_BB051_SWAP_MVS | Si
BB354 | AMBA_BB354_SWAP_MVS | Si |  | 2026-06-03 | 2026-06-04 | 2026-06-04 | 2026-06-04 | David Encina WX1367993 |  | 2026-06-05 |  | David Encina WX1367993
BC408 | AMBA_BC408_SWAP_MVS | Si
BH097 | AMBA_BH097_SWAP_MVS | Si
BM014 | AMBA_BM014_SWAP_MVS | Si
BM037 | AMBA_BM037_SWAP_MVS | Si
BM081 | AMBA_BM081_SWAP_MVS | Si
BM381 | AMBA_BM381_SWAP_MVS | Si
BM382 | AMBA_BM382_SWAP_MVS | Si
BM392 | AMBA_BM392_SWAP_MVS | Si
BM551 | AMBA_BM551_SWAP_MVS | Si
BM626 | AMBA_BM626_SWAP_MVS | Si
BM835 | AMBA_BM835_SWAP_MVS | Si
BM902 | AMBA_BM902_SWAP_MVS | Si
BN067 | AMBA_BN067_SWAP_MVS | Si
BN147 | AMBA_BN147_SSV_MVS | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN226 | AMBA_BN226_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BO223 | AMBA_BO223_SWAP_MVS | Si
BO408 | AMBA_BO408_SWAP_MVS | Si
BS094 | AMBA_BS094_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS246 | AMBA_BS246_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN186 | AMBA_CN186_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS014 | AMBA_CS014_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS090 | AMBA_CS090_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS008 | AMBA_KS008_SSV_MVS | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS009 | AMBA_KS009_SSV_MVS | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS018 | AMBA_KS018_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS111 | AMBA_KS111_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AllRegion_ClusterOPT_Apr_TLF |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AllRegion_ClusterOPT_Apr_TLF_V2 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AllRegion_ClusterOPT_May_TLF |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AllRegion_ClusterOPT_May_TLF_V2 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARBA0430 | BA_ARBA0430_FARM_Etapa1_MVS |  |  |  |  | 2026-06-04 | 2026-06-04 | David Encina WX1367993
ARBA0484 | BA_ARBA0484_FARM_Etapa1_MVS
ARBA0635 | BA_ARBA0635_FARM_Etapa01_MVS |  |  |  |  | 2026-05-08 | 2026-05-08 | David Encina WX1367993
ARBA1185 | BA_ARBA1185_FARM_Etapa1_MVS
BB011 | BA_BB011_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB076 | BA_BB076_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB077 | BA_BB077_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB173 | BA_BB173_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM308 | BA_BM308_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC022 | LP_DC022_SSV_MVS | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TC030 | MEDI_143_TC030_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TC030 | MEDI_143_TC030_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TC042 | MEDI_149_TC042_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TN304 | MEDI_149_TN304_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AN015 | MEDI_175_AN015_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XC622 | MEDI_48_XC622_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XN008 | MEDI_8_XN008_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC091 | MEDI_MC091_SWAP_MVS | Si | 0.53 |  |  | 2026-03-13 | 2026-03-13 | Tomas Ezequiel Sanchez WX1486917 |  |  |  | Tomas Ezequiel Sanchez WX1486917 | [13 empty] | Survey Pending
ARME0188 | MZ_ARME0188_FARM_Dismantle_MVS
ARME0837 | MZ_ARME0837_FARM_Dismantle_MVS
MC004 | MZ_MC004_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC048 | NQ_QC048_SSV_MVS | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC053 | NQ_QC053_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC105 | NQ_QC105_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARRN0006 | RN_ARRN0006_FARM_Etapa1_MVS |  |  |  |  | 2026-05-15 | 2026-05-15 | David Encina WX1367993
ARRN0052 | RN_ARRN0052_FARM_Etapa01_MVS
ARRN0338 | RN_ARRN0338_FARM_Etapa1_MVS |  |  |  |  | 2026-05-12 | 2026-05-12 | David Encina WX1367993
RS014 | RN_RS014_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS056 | RN_RS056_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FC032 | SL_FC032_SSV_MVS |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B120 | SUR_101_A38-B120_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B223 | SUR_101_A38-B223_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB101 | SUR_101_BB101_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB113 | SUR_101_BB113_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB336 | SUR_101_BB336_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB337 | SUR_101_BB337_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB338 | SUR_101_BB338_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB339 | SUR_101_BB339_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB340 | SUR_101_BB340_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB400 | SUR_101_BB400_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q001 | SUR_128_A30-Q001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q001 | SUR_128_A30-Q001_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q041 | SUR_128_A30-Q041_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q034 | SUR_130_A30-Q034_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q042 | SUR_130_A30-Q042_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC011 | SUR_131_QC011_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC349 | SUR_131_QC349_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q092 | SUR_132_A30-Q092_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q099 | SUR_133_A30-Q099_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q099 | SUR_133_A30-Q099_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q259 | SUR_133_A30-Q259_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q261 | SUR_133_A30-Q261_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q262 | SUR_133_A30-Q262_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F001 | SUR_153_A36-F001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F003 | SUR_153_A36-F003_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F046 | SUR_153_A36-F046_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F049 | SUR_153_A36-F049_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F061 | SUR_153_A36-F061_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F068 | SUR_153_A36-F068_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A36-F071 | SUR_153_A36-F071_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC005 | SUR_153_DC005_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC006 | SUR_153_DC006_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC022 | SUR_153_DC022_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC022 | SUR_153_DC022_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC115 | SUR_153_DC115_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DC310 | SUR_153_DC310_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A25-Z017 | SUR_15_A25-Z017_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A25-Z020 | SUR_15_A25-Z020_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A25-Z039 | SUR_15_A25-Z039_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VC001 | SUR_15_VC001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VC014 | SUR_15_VC014_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VC023 | SUR_15_VC023_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VC029 | SUR_15_VC029_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VC307 | SUR_15_VC307_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VC314 | SUR_15_VC314_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-F039 | SUR_163_A37-F039_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-F040 | SUR_163_A37-F040_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-F040 | SUR_163_A37-F040_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-F042 | SUR_163_A37-F042_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DE006 | SUR_163_DE006_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DE009 | SUR_163_DE009_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DE033 | SUR_163_DE033_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DE067 | SUR_163_DE067_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DE068 | SUR_163_DE068_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A652 | SUR_181_A41-A652_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A652 | SUR_181_A41-A652_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A653 | SUR_181_A41-A653_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A653 | SUR_181_A41-A653_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM600 | SUR_181_BM600_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM602 | SUR_181_BM602_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM603 | SUR_181_BM603_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A660 | SUR_186_A41-A660_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A688 | SUR_186_A41-A688_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A004 | SUR_193_A41-A004_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A562 | SUR_193_A41-A562_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B027 | SUR_193_A41-B027_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B029 | SUR_193_A41-B029_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B285 | SUR_193_A41-B285_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B470 | SUR_193_A41-B470_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B471 | SUR_193_A41-B471_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B498 | SUR_193_A41-B498_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B937 | SUR_193_A41-B937_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM066 | SUR_193_BM066_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM074 | SUR_193_BM074_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM307 | SUR_193_BM307_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM327 | SUR_193_BM327_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM366 | SUR_193_BM366_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM376 | SUR_193_BM376_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM397 | SUR_193_BM397_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM519 | SUR_193_BM519_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM590 | SUR_193_BM590_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A39-B304 | SUR_195_A39-B304_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A39-B456 | SUR_195_A39-B456_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A39-B780 | SUR_195_A39-B780_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A39-B862 | SUR_195_A39-B862_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BL001 | SUR_195_BL001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BL023 | SUR_195_BL023_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BL323 | SUR_195_BL323_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B052 | SUR_1_A38-B052_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B310 | SUR_1_A38-B310_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B320 | SUR_1_A38-B320_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B324 | SUR_1_A38-B324_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A780 | SUR_200_A41-A780_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A116 | SUR_201_A41-A116_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A42-A039 | SUR_202_A42-A039_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A42-B082 | SUR_202_A42-B082_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH045 | SUR_202_BH045_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH107 | SUR_203_BH107_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A25-Z041 | SUR_22_A25-Z041_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VW001 | SUR_22_VW001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VW005 | SUR_22_VW005_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VW006 | SUR_22_VW006_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VW033 | SUR_22_VW033_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VW046 | SUR_22_VW046_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VW303 | SUR_22_VW303_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH006 | SUR_239_BH006_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BH054 | SUR_239_BH054_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-B131 | SUR_247_A37-B131_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B314 | SUR_2_A38-B314_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B314 | SUR_2_A38-B314_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B315 | SUR_2_A38-B315_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B315 | SUR_2_A38-B315_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B321 | SUR_2_A38-B321_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B322 | SUR_2_A38-B322_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-A803 | SUR_310_A43-A803_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-A804 | SUR_310_A43-A804_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-A805 | SUR_310_A43-A805_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B067 | SUR_310_A43-B067_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B145 | SUR_310_A43-B145_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B151 | SUR_310_A43-B151_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B156 | SUR_310_A43-B156_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B647 | SUR_310_A43-B647_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A43-B907 | SUR_310_A43-B907_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B103 | SUR_328_A41-B103_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B289 | SUR_328_A41-B289_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B467 | SUR_328_A41-B467_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B983 | SUR_328_A41-B983_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM059 | SUR_328_BM059_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM509 | SUR_328_BM509_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BM770 | SUR_328_BM770_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB354 | SUR_3_BB354_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB355 | SUR_3_BB355_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-A110 | SUR_4_A38-A110_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B319 | SUR_4_A38-B319_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B412 | SUR_4_A38-B412_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J026 | SUR_501_A34-J026_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J104 | SUR_501_A34-J104_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J132 | SUR_501_A34-J132_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J034 | SUR_505_A34-J034_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J071 | SUR_505_A34-J071_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J210 | SUR_505_A34-J210_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC016 | SUR_505_JC016_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC023 | SUR_505_JC023_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC031 | SUR_505_JC031_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC036 | SUR_505_JC036_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC047 | SUR_505_JC047_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC048 | SUR_505_JC048_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC049 | SUR_505_JC049_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC052 | SUR_505_JC052_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC056 | SUR_505_JC056_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC338 | SUR_505_JC338_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FN032 | SUR_509_FN032_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O231 | SUR_514_A32-O231_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A32-O426 | SUR_514_A32-O426_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MO002 | SUR_514_MO002_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MO015 | SUR_514_MO015_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS002 | SUR_514_MS002_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS007 | SUR_514_MS007_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS011 | SUR_514_MS011_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS023 | SUR_514_MS023_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS028 | SUR_514_MS028_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS032 | SUR_514_MS032_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS035 | SUR_514_MS035_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS038 | SUR_514_MS038_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS041 | SUR_514_MS041_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS042 | SUR_514_MS042_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS044 | SUR_514_MS044_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS062 | SUR_514_MS062_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS063 | SUR_514_MS063_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS122 | SUR_514_MS122_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O006 | SUR_519_A33-O006_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O075 | SUR_523_A33-O075_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O076 | SUR_523_A33-O076_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O134 | SUR_523_A33-O134_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O149 | SUR_523_A33-O149_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O244 | SUR_523_A33-O244_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O734 | SUR_523_A33-O734_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MC397 | SUR_523_MC397_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O009 | SUR_524_A33-O009_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O017 | SUR_524_A33-O017_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O040 | SUR_524_A33-O040_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O041 | SUR_524_A33-O041_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O042 | SUR_524_A33-O042_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O044 | SUR_524_A33-O044_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O046 | SUR_524_A33-O046_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O098 | SUR_524_A33-O098_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O237 | SUR_524_A33-O237_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O238 | SUR_524_A33-O238_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O391 | SUR_524_A33-O391_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J070 | SUR_531_A34-J070_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J070 | SUR_531_A34-J070_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J096 | SUR_531_A34-J096_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J096 | SUR_531_A34-J096_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J128 | SUR_531_A34-J128_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J128 | SUR_531_A34-J128_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JN013 | SUR_531_JN013_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JS046 | SUR_531_JS046_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J057 | SUR_532_A34-J057_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A34-J085 | SUR_532_A34-J085_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC010 | SUR_532_JC010_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC018 | SUR_532_JC018_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC075 | SUR_532_JC075_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC303 | SUR_532_JC303_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC320 | SUR_532_JC320_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JC340 | SUR_532_JC340_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O054 | SUR_533_A33-O054_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O067 | SUR_533_A33-O067_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O070 | SUR_533_A33-O070_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O071 | SUR_533_A33-O071_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O102 | SUR_533_A33-O102_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A33-O419 | SUR_533_A33-O419_RSH_OPT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-A792 | SUR_5_A38-A792_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B058 | SUR_5_A38-B058_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R015 | SUR_63_A28-R015_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R017 | SUR_63_A28-R017_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R051 | SUR_63_A28-R051_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R051 | SUR_63_A28-R051_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R057 | SUR_63_A28-R057_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R068 | SUR_63_A28-R068_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R076 | SUR_63_A28-R076_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R137 | SUR_63_A28-R137_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R138 | SUR_63_A28-R138_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R139 | SUR_63_A28-R139_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R140 | SUR_63_A28-R140_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R141 | SUR_63_A28-R141_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R144 | SUR_63_A28-R144_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R160 | SUR_63_A28-R160_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R163 | SUR_63_A28-R163_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A28-R167 | SUR_63_A28-R167_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS003 | SUR_63_RS003_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS004 | SUR_63_RS004_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS005 | SUR_63_RS005_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS014 | SUR_63_RS014_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS014 | SUR_63_RS014_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS033 | SUR_63_RS033_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS033 | SUR_63_RS033_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS037 | SUR_63_RS037_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS040 | SUR_63_RS040_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS046 | SUR_63_RS046_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS048 | SUR_63_RS048_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS056 | SUR_63_RS056_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS056 | SUR_63_RS056_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS126 | SUR_63_RS126_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS126 | SUR_63_RS126_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS314 | SUR_63_RS314_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS008 | SUR_64_RS008_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS308 | SUR_64_RS308_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS089 | SUR_65_RS089_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS090 | SUR_65_RS090_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS091 | SUR_65_RS091_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS003 | SUR_74_QS003_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS003 | SUR_74_QS003_RSH_OPT_5G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS004 | SUR_74_QS004_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS007 | SUR_74_QS007_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS026 | SUR_74_QS026_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS027 | SUR_74_QS027_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS028 | SUR_74_QS028_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS029 | SUR_74_QS029_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS030 | SUR_74_QS030_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS031 | SUR_74_QS031_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS032 | SUR_74_QS032_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS304 | SUR_74_QS304_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS001 | SUR_79_QS001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QS013 | SUR_79_QS013_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QW001 | SUR_85_QW001_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QW002 | SUR_85_QW002_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QW017 | SUR_85_QW017_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RE019 | SUR_91_RE019_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RE020 | SUR_91_RE020_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RE021 | SUR_91_RE021_RSH_OPT_4G |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A24-V040 | South_A24-V040_Mod_TA | Si |  | N/A |  | N/A
A26-Z006 | South_A26-Z006_Mod_TA | Si |  | N/A |  | N/A
A30-Q001 | South_A30-Q001_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q003 | South_A30-Q003_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-Q099 | South_A30-Q099_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A30-R041 | South_A30-R041_Mod_TA | Si |  | N/A | 2026-05-28 | N/A | 2026-05-29 | Tomas Ezequiel Sanchez WX1486917 |  | 2026-06-01 |  | Tomas Ezequiel Sanchez WX1486917
A34-J031 | South_A34-J031_Mod_TA | Si |  | N/A |  | N/A
A37-B060 | South_A37-B060_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A37-B131 | South_A37-B131_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B315 | South_A38-B315_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B321 | South_A38-B321_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B322 | South_A38-B322_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A38-B323 | South_A38-B323_SSV_TA | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A39-B047 | South_A39-B047_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A40-B299 | South_A40-B299_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A40-B300 | South_A40-B300_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A467 | South_A41-A467_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A595 | South_A41-A595_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A649 | South_A41-A649_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A652 | South_A41-A652_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-A653 | South_A41-A653_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B015 | South_A41-B015_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B018 | South_A41-B018_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B023 | South_A41-B023_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B025 | South_A41-B025_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B028 | South_A41-B028_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B034 | South_A41-B034_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B266 | South_A41-B266_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B268 | South_A41-B268_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B269 | South_A41-B269_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B270 | South_A41-B270_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B272 | South_A41-B272_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B275 | South_A41-B275_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B276 | South_A41-B276_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B277 | South_A41-B277_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B282 | South_A41-B282_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B291 | South_A41-B291_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B292 | South_A41-B292_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B295 | South_A41-B295_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B298 | South_A41-B298_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B389 | South_A41-B389_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B438 | South_A41-B438_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B445 | South_A41-B445_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B464 | South_A41-B464_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B591 | South_A41-B591_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A41-B876 | South_A41-B876_SSV_TA |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BB307 | South_BB307_SSV_MVS | No |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QC051 | South_QC051_Swap_MVS | Si | 1.87 | 2026-04-23 | 2026-04-23 | 2026-05-06 | 2026-05-06 | Miguel Angel Garcia Martinez 00881238 |  | 2026-04-27 | 2026-05-18 | Miguel Angel Garcia Martinez 00881238
RC066 | South_RC066_SWAP_MVS | Si
RS020 | South_RS020_SWAP_MVS | Si |  | 2026-06-01 | 2026-06-01 |  |  | GSC |  | 2026-06-03
RS029 | South_RS029_SWAP_MVS | Si
UE002 | South_UE002_SWAP_MVS | Si
VC025 | South_VC025_SWAP_MVS | Si

## Enum (hidden)
Si
No
No
Yes
Etapa 01
Etapa 02
Etapa 03
Survey Pending
Survey Done
PPI Pending
PPI Approved
MR
ML
Dispatched
SubRack Installed
Installed with Issue
Installed
Ready for Dismantle
Swapped
Dismantled
N/A

## Subcontractor
Subcontractor Code | Subcontractor
HuaWei
402001 | INTEROPTICS S.A.
4O2114 | Insieme Tecnología S. A.
4O2115 | CELLTREX S. A.
Z002KL | CYAC SRL
Z00RE8 | TG2 S.R.L.
Z01QHB | ESMETIC ELECTROMECANICA SRL
Z032CY | MOBILE SERVICES INTERNATIONAL S.A.
Z06J2G | L2G TELECOM S.R.L.
Z06NUB | Benefits Sociedad Anonima
Z06ZN3 | CONSTEL SRL
Z06ZQ5 | TERABYTE SRL
Z07JY5 | CIS GROUP LATINOAMERICA SA
Z07OCJ | ERSATEL SOCIEDAD DE RESPONSABILIDAD LIMITADA